## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-31 |  |  | APPROVED OUTAGE LIST FOR DATED 31.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-30 13:54 | MR2507/0470 |  | 220KV_220 kV Chhindwara-Pandhurna | 220KV_CHHINDWARA | NON-OCCM-MP | Flash over disc replacement & J/c, A/h tightening | 31-07-2025 10:00:00 | 31-07-2025 16:00:00 | A.M.Shende | 7587951136 | ok
2 | 2025-07-25 16:41 | MR2507/0414 | Daily | 400KV_125 MVAr SHUNT REACTOR | 400KV_INDIRASAGAR | NON-OCCM-WR | MAINTENANCE WORK OF SAID ITEM | 29-07-2025 10:00:00 | 31-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | as per the voltage profile
3 | 2025-07-30 13:00 | MR2507/0469 |  | 220KV_220KV Main Bus No.-2 | 220KV_ITARSI | NON-OCCM-MP | Replacement of GG zebra conductor & String work | 31-07-2025 10:00:00 | 31-07-2025 17:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
4 | 2025-06-30 15:05 | MR2506/0621 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered
5 | 2025-06-30 15:54 | MR2506/0630 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
6 | 2025-07-30 15:33 | MR2507/0472 |  | 220KV_220KV BUS TIE | 400KV_KATNI4 | NON-OCCM-MP | TO ATTEND HOT POINT IN RPH CT CLAMP | 31-07-2025 10:00:00 | 31-07-2025 14:00:00 | SK CHATURVEDI | 9425806938 | ok
7 | 2025-07-27 14:12 | MR2507/0430 | Continuous | 132KV_132 KV Khurai- Sagar ckt | 132KV_KHURAI | NON-OCCM-MP | For modification work of above line | 27-07-2025 07:00:00 | 03-08-2025 18:00:00 | Sanjay singh thakur | 9425806936 | Continuous
8 | 2025-07-24 12:24 | MR2507/0380 | Continuous | 400KV_400 KV Main Bus-2nd | 400KV_MANDSOUR4 | NON-OCCM-MP | Overhead stringing work | 29-07-2025 09:00:00 | 05-08-2025 18:00:00 | J.P. Parmar | 9425806919 | Deffered
9 | 2025-07-28 18:36 | MR2507/0449 | Daily | 220KV_220 KV Narsinghpur-Chichli-Pipariya Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Rectification/replacement/work between Tower No-33 | 30-07-2025 09:00:00 | 05-08-2025 18:00:00 | Ashish Kumar | 9425805935 | Deffered due to s/d on Itarsi 220kv Main bus
10 | 2025-07-28 13:46 | MR2507/0440 |  | 220KV_Rajgarh (PGCIL) to Rajgarh (MPPTCL) CKT-1 | 220KV_RAJGARH DHAR | OCCM-MP | For Line maintenance work | 31-07-2025 10:00:00 | 31-07-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
11 | 2025-07-16 11:13 | MR2507/0210 | Continuous | 400KV_63 MVA 400 Kv/ 11&6.6 KV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay test,DCRM,CT testing,Air cell replacement | 31-07-2025 09:00:00 | 02-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
12 | 2025-07-23 17:12 | MR2507/0374 | Continuous | 400KV_90MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | OVERHAULLING OF 90MVA STATION TRANSFORMER-2 | 28-07-2025 09:30:00 | 06-08-2025 17:30:00 | Yogesh Chouhan | 7999328631 | Continuous
13 | 2025-07-30 16:56 | MR2507/0473 |  | 220KV_160MVA X-MER -II BHEL | 220KV_VIDISHA | OCCM-MP | for rectification work of suspected DC leakage | 31-07-2025 11:00:00 | 31-07-2025 17:00:00 | KC GOSWAMI | 9425804976 | ok, through sub ld
14 |  |  |  | 400KV-BINA-MP-BINA-4 | POWERGRID-WR2 (PGCIL) |  | Simultaneous ouatge of BINA - 400KV - BUS 1 & 400KV-BINA-MP-BINA-4 has been required for Bay-422 LBB Testing | 31-Jul-2025 | 09:00 | 31-Jul-2025 | 15:00 | ok
15 |  |  |  | BINA - 400KV - BUS 1 | POWERGRID-WR2 (PGCIL) |  | Simultaneous ouatge of BINA - 400KV - BUS 1 & 400KV-BINA-MP-BINA-4 has been required for Bay-422 LBB Testing | 31-Jul-2025 | 09:00 | 31-Jul-2025 | 15:00 | ok
16 |  |  |  | 400KV-INDORE-MP-ASOJ-1 | POWERGRID-WR2 (PGCIL) |  | PLCC digital protection coupler installation work & Line AMP Works, Dia to be kept open at both ends. | 31-Jul-2025 | 09:00 | 31-Jul-2025 | 18:00 | ok
17 |  |  |  | 220KV-RAJGARH-RAJGARH-MP-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 31-Jul-2025 | 08:00 | 31-Jul-2025 | 18:00 | ok, through sub ld
18 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 31-Jul-2025 | 08:00 | 31-Jul-2025 | 17:59 | ok
S/I SLDC JABALPUR