## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-22
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-16 18:55 | MR2506/0355 | Daily | 220KV_220 KV BAIRAGARH MUGALIYACHAP LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE-3 | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
4 | 2025-06-20 17:06 | MR2506/0429 | Daily | 132KV_132 kV Bijawar -Badamalhera line | 220KV_CHATARPUR | NON-OCCM-MP | OPGW installation work in line | 21-06-2025 07:00:00 | 22-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
5 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
6 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
7 | 2025-06-17 21:54 | MR2506/0387 | Continuous | 400KV_UNIT - 7 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-06-2025 06:00:00 | 30-06-2025 18:00:00 | Vinay Mishra | 9575074321 | as per system requirement
8 | 2025-06-12 16:27 | MR2506/0283 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
9 | 2025-06-17 18:15 | MR2506/0379 | Daily | 132KV_NIRANJANPUR - JETPURA LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
10 | 2025-06-17 18:13 | MR2506/0378 | Daily | 132KV_NORTHZONE - NIRANJANPUR LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
11 | 2025-06-17 18:05 | MR2506/0377 | Daily | 132KV_NORTHZONE - JETPURA LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
12 | 2025-06-12 15:54 | MR2506/0282 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
13 | 2025-06-19 14:03 | MR2506/0409 | Daily | 220KV_220 KV Sarni-Itarsi CKT- II LINE | 220KV_ITARSI | NON-OCCM-MP | Resagging work b/w loc.no. 192-213 | 20-06-2025 09:00:00 | 23-06-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
14 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | communication consent required for data outage
15 | 2025-06-20 11:59 | MR2506/0420 | Daily | 220KV_220 KV BHOPAL MUGALIYACHAAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | OPGW MAINTENANCE WORK | 21-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
16 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
17 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
18 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
19 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
20 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
21 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
22 | 2025-06-18 16:13 | MR2506/0401 | Continuous | 132KV_132kV Sidhi - Mauganj Ckt I&II | 220KV_SIDHI | NON-OCCM-MP | Strining Work | 19-06-2025 08:00:00 | 22-06-2025 18:00:00 | G.L Sahu | 9425805102 | Continuous
23 | 2025-06-17 17:47 | MR2506/0373 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
24 | 2025-06-17 17:49 | MR2506/0374 | Daily | 132KV_132 kV Tikamgarh IC 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
25 | 2025-06-21 09:53 | MR2506/0433 | Daily | 400KV_400 KV ASHTA-UJJAIN LINE DCDS(CKT 1&2) | 400KV_UJJAIN4 | OCCM-WR | ONLINE PERMIT WORK | 21-06-2025 10:00:00 | 25-06-2025 19:00:00 | KUMAR SACHINDRA SHARMA | 7415651054 | on hold, pl confirm the availability of telemetry data
26 |  | 249958 |  | 400KV-DAMOH-KATNI-1 | 400 | MP_SLDC | TOWER STRENGTHENING WORK | 19-Jun-2025 | 09:00 | 24-Jun-2025 | 17:00 | ok, 220kv Tikamgarh-Chattarpur ckt to be opened for load management
27 |  | 251467 |  | 400KV-SINGAJI-PITHAMPUR-1 | 400 | MP_SLDC | for tower strengthening works | 16-Jun-2025 | 08:00 | 30-Jun-2025 | 17:59 | Deffered
28 |  | 251468 |  | 400KV-SINGAJI-PITHAMPUR-2 | 400 | MP_SLDC | for tower strengthening works | 16-Jun-2025 | 08:00 | 30-Jun-2025 | 17:59 | Deffered
29 |  | 253397 |  | 220KV-INDORE-INDORE NORTH ZONE-1 | 220 | MP_SLDC | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 22-Jun-2025 | 07:00 | 22-Jun-2025 | 18:59 | ok, line to be in service
30 |  | 253409 |  | 220KV-INDORE-INDORE NORTH ZONE-2 | 220 | MP_SLDC | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 22-Jun-2025 | 07:00 | 22-Jun-2025 | 18:59 | ok, line to be in service