## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-16 | APPROVED OUTAGE LIST FOR DTD.16.09.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-12 15:03 | MR2509/0290 | Daily | 220KV_220 KV Anuppur- Kotmikala ckt-II | 220KV_ANUPPUR | NON-OCCM-MP | Resagging work at loc. 464-475 | 16-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | RESCHEDULED FOR 17.09.2025 & 18.09.2025
3 | 2025-09-15 16:02 | MR2509/0354 |  | 132KV_132 KV ASHTA-INTERCONNECTED CKT.NO.1ST | 400KV_ASHTA4 | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 16-09-2025 09:00:00 | 16-09-2025 12:00:00 | JITENDRA LOHANA | 9425804978 | SUB LD
4 | 2025-09-15 14:45 | MR2509/0342 |  | 132KV_132 kV MACT-E8 line | 220KV_BHOPAL | NON-OCCM-MP | Emergency tree cutting work | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | Ankit Mehroliya | 9425804506 | SUB LD
5 | 2025-09-12 18:47 | MR2509/0294 | Continuous | 400KV_500 MVA X-MER NO.1(T&R) | 400KV_BHOPAL4 | NON-OCCM-MP | Post mansoon Maintence work | 15-09-2025 09:00:00 | 16-09-2025 18:00:00 | AKRAM KHAN | 9425804695 | OK THROUGH SUB LD
6 | 2025-09-15 15:19 | MR2509/0346 |  | 220KV_160 MVA BHEL TRANSFORMER | 220KV_BINA | NON-OCCM-WR | POST MONSOON MAINTENANCE WORK | 16-09-2025 09:30:00 | 16-09-2025 18:00:00 | Er. LALIT SINGH | 9425806845 | OK
7 | 2025-09-15 15:41 | MR2509/0352 |  | 220KV_220KV Bina-Pichhore ckt. | 400KV_BINA4 | NON-OCCM-WR | B phase wave trap hot attend work and PMM work. | 16-09-2025 09:00:00 | 16-09-2025 17:00:00 | Mr.P.N.Namdeo | 7587951092 | OK THROUGH SUB LD
8 | 2025-09-15 15:05 | MR2509/0344 |  | 220KV_220 KV Bina-Sagar Ckt-1 | 400KV_BINA4 | NON-OCCM-MP | For f/o disc insulator replac. & other line maint. | 16-09-2025 09:00:00 | 16-09-2025 18:00:00 | Sanajy Singh Thakur | 9425806936 | OK
9 | 2025-09-14 13:00 | MR2509/0312 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 15-09-2025 08:00:00 | 20-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK FOR 15.09.2025 DAILY BASIS SD
10 | 2025-09-15 15:40 | MR2509/0351 |  | 220KV_160 MVA AREVA | 220KV_CHATARPUR | NON-OCCM-MP | for post monsoon maint | 16-09-2025 10:00:00 | 16-09-2025 18:00:00 | Brajendra Soni | 9131327770 | OK
11 | 2025-09-15 15:02 | MR2509/0343 |  | 220KV_KHANDWA-PG-CHHEGAON4_Ckt_1 | 400KV_CHHEGAON4 | NON-OCCM-MP | Line Isolator R Phase pad clamp CT side hot point | 16-09-2025 10:00:00 | 16-09-2025 15:00:00 | Shri Ganesh Mansare | 9425802441 | DEFERRED AS 220 KV KHANDA - NEPANAGAR ALREADY APPROVED AND WRPC CONSENT REQUIRED,
12 | 2025-09-15 12:40 | MR2509/0330 |  | 220KV_220 kV Chhegaon - Nimrani Ckt 2nd | 400KV_CHHEGAON4 | NON-OCCM-WR | For Jumper Cone Tightening & Other Line Maintenanc | 16-09-2025 09:00:00 | 16-09-2025 17:00:00 | C.H.Namdev | 9425802377 | OK THROUGH SUB LD
13 | 2025-09-15 12:37 | MR2509/0329 |  | 132KV_132KV Damoh-Garhakota Line | 220KV_DAMOH | NON-OCCM-MP | Line maintenance work | 16-09-2025 10:00:00 | 16-09-2025 18:00:00 | J.P. Asati | 9424445533 | OK
14 | 2025-09-15 15:23 | MR2509/0348 |  | 132KV_40 MVA T&R X-mer | 132KV_DAMOH1 | NON-OCCM-MP | POst monsoon maintenance | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | B K Sahu | 9425801433 | OK O&M TO BE INTIMATED
15 | 2025-09-14 13:01 | MR2509/0313 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 15-09-2025 08:00:00 | 20-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK FOR 15.09.2025 DAILY BASIS SD
16 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
17 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
18 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
19 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | RESCHEDULED FRO 11.09.2025 TO 30.09.2025
20 | 2025-09-15 13:37 | MR2509/0333 | Continuous | 132KV_132 kv katni panagar line | 132KV_KATNI | NON-OCCM-MP | Modification shifting work for NHAI | 15-09-2025 18:00:00 | 16-09-2025 12:00:00 | pankaj yadav | 9406713326 | OK, EI APPROVAL TO BE PROVIDED
21 | 2025-09-15 13:47 | MR2509/0335 | Continuous | 132KV_132 kv Katni-sleemnabad ckt 2nd line | 132KV_KATNI | NON-OCCM-MP | Modification shifting work for Nhai | 16-09-2025 12:00:00 | 17-09-2025 12:00:00 | pankaj yadav | 9406713326 | OK, AFTER REVIVAL OF 132 KV KATNI - PANAGAR CKT & EI APPROVAL TO BE PROVIDED PRIOR TO CHARGING
22 | 2025-09-15 13:49 | MR2509/0336 |  | 132KV_50 MVA TAL X-MER | 220KV_MAIHAR | NON-OCCM-MP | Post mansoon maintanance ant testing work | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | Arun kumar kol | 9425802368 | OK O&M TO BE INTIMATED
23 | 2025-09-15 15:08 | MR2509/0345 |  | 132KV_132KV Rajgarh Maqsudangarh Ckt. | 132KV_MAKSUDANGARH | NON-OCCM-MP | For DF/O Replacement & Other Line Maint. work | 16-09-2025 09:00:00 | 16-09-2025 17:00:00 | Akhilesh Singh | 8586865656 | SUB LD
24 | 2025-09-15 14:13 | MR2509/0339 |  | 220KV_160 MVA BBL TRANSFORMER 220/132/33KV | 220KV_NAGDA | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | VIKRAM DEHARIYA | 7000276050 | OK THROUGH SUB LD
25 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
26 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
27 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
28 | 2025-09-15 15:36 | MR2509/0349 |  | 132KV_50 MVA X-mer-II make TAL | 132KV_PETLAWAD | NON-OCCM-MP | for Post Monsoon Maintenance work | 16-09-2025 10:00:00 | 16-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
29 | 2025-09-15 13:06 | MR2509/0331 |  | 220KV_RAJGARH-PG-PITHAMPUR (SEC-III)_Ckt | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | Tan Delta measurement work of 220KV CTs work | 16-09-2025 09:00:00 | 16-09-2025 12:00:00 | Sh Mukesh Patil | 8120562072 | DEFERRED WRPC APPROVAL REQUIRED
30 | 2025-09-15 16:45 | MR2509/0357 |  | 220KV_220KV Bus Tie | 400KV_PITHAMPUR4 | NON-OCCM-MP | For Replace CB Trip Coil-II | 16-09-2025 11:00:00 | 16-09-2025 14:00:00 | Rajudas bairagi | 9425801532 | OK, BUT SEPERATE BUS OPERATION NOT CONSENTED SO ALL ELEMENTS TO BE SHIFTED ON ONE BUS DUE
31 | 2025-08-20 17:37 | MR2508/0263 |  | 400KV_400kV Pithampur-PGCIL Indore ckt-II | 400KV_PITHAMPUR4 | OCCM-MP | Tan delta testing & bay maintenance work | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | Sh. Rajudash bairagi | 9425801532 | RESCHEDULED FOR 24.09.2025
32 | 2025-09-12 14:34 | MR2509/0286 |  | 400KV_400KV_400KV Main bus-II | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tightening Greasing & cleaning work | 16-09-2025 10:00:00 | 16-09-2025 18:00:00 | Sh. Rajudash bairagi | 9425801532 | OK, THROUGH SUB LD
33 | 2025-09-15 16:18 | MR2509/0355 |  | 132KV_132kV Rajmilan - Janakpur Ckt | 132KV_RAJMILAN | NON-OCCM-MP | Disc Replacement work | 16-09-2025 09:00:00 | 16-09-2025 17:00:00 | G.L Sahu | 9425805102 | OK, Janakpur supply to be maintained through Anuppur
34 | 2025-09-15 12:32 | MR2509/0328 |  | 132KV_40 MVA X-MER-II (TELK) | 220KV_RATLAM | NON-OCCM-MP | for LV side CT replacement work. | 16-09-2025 09:00:00 | 16-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
35 | 2025-09-15 11:31 | MR2509/0325 |  | 220KV_SARNI BETUL PGCIL | 220KV_SARNI | OCCM-WR | Flash over disc replacement & other line maint. wo | 16-09-2025 09:00:00 | 16-09-2025 17:00:00 | SHIV KUMAR | 9425806917 | OK THROUGH SUB LD
36 | 2025-09-09 15:43 | MR2509/0208 |  | 220KV_220 kv Satna (MPPTCL) â¿¿ Ajaygarh line | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | Mr.RK Prajapati | 9407070182 | DEFERRED WRPC APPROVAL REQUIRED
37 | 2025-09-15 14:29 | MR2509/0340 |  | 220KV_220KV PGCIL Ckt -2 | 220KV_SEONI | OCCM-MP | Bay Maintenance & relay testing work | 16-09-2025 10:00:00 | 16-09-2025 17:00:00 | Shri C.S.Sanodiya | 9009798506 | REAL TIME
38 | 2025-09-15 12:00 | MR2509/0327 |  | 220KV_220KV Bus-coupler | 400KV_SINGHAJI TPS | NON-OCCM-MP | 220KV Bus-coupler checking work | 16-09-2025 09:00:00 | 16-09-2025 18:00:00 | Deepak Sharma | 8005696855 | OK, BUT SEPERATE BUS OPERATION NOT CONSENTED SO ALL ELEMENTS TO BE SHIFTED ON ONE BUS DUE
39 | 2025-09-15 15:39 | MR2509/0350 |  | 132KV_132 KV Udaipura-Tendukheda line Ckt-II | 132KV_TENDUKHEDA | NON-OCCM-MP | Flashover disc replacement work at loc.No.45/R-01 | 16-09-2025 10:00:00 | 16-09-2025 18:00:00 | Ashish Kumar | 9425805935 | OK THROUGH SUB LD
40 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
41 | 2025-09-15 11:33 | MR2509/0326 |  | 400KV_315 MVA X-mer Ist | 400KV_UJJAIN4 | NON-OCCM-WR | for testing and maintenance work | 16-09-2025 09:00:00 | 16-09-2025 18:00:00 | Santosh Chavrasia | 9425804677 | OK THROUGH SUB LD
42 | 2025-09-15 13:34 | MR2509/0332 |  | 220KV_160MVA X-MER-III BHEL | 220KV_VIDISHA | OCCM-MP | POST MONSOON MAINTENANCE WORK | 16-09-2025 09:00:00 | 16-09-2025 18:00:00 | KC GOSWAMI | 9425804976 | OK THROUGH SUB LD
43 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
44 | 2025-09-15 13:34 |  |  | 220KV-KHANDWA-NEPANAGAR-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 16-Sep-2025 | 08:00 | 16-Sep-2025 | 18:00 | OK THROUGH SUB LD | OK
45 | 2025-09-15 13:34 |  |  | 220KV-INDORE-UJJAIN-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 16-Sep-2025 | 08:00 | 16-Sep-2025 | 18:00 | OK THROUGH SUB LD
46 | 2025-09-15 13:34 |  |  | 220KV-SEONI-MP-SEONI-PG-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 16-Sep-2025 | 09:00 | 16-Sep-2025 | 18:00 | REAL TIME
47 | 2025-09-15 13:34 |  |  | 220KV-BETUL-SARNI-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 16-Sep-2025 | 09:00 | 16-Sep-2025 | 17:00 | OK THROUGH SUB LD
48 | 2025-09-15 13:34 |  |  | 220KV-BHANPURA-MODAK-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 16-Sep-2025 | 08:00 | 16-Sep-2025 | 18:00 | OK THROUGH SUB LD
49 | 2025-09-15 13:34 |  |  | 400KV/220KV JABALPUR-ICT-2 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 16-Sep-2025 | 09:00 | 17-Sep-2025 | 17:00 | OK
50 | 2025-09-15 13:34 |  |  | 400KV-BHOPAL-MP-BINA-MP-1 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 16-Sep-2025 | 09:00 | 16-Sep-2025 | 18:00 | OK.LINE ALREADY UNDER OUTAGE
51 | 2025-09-15 13:34 |  |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | OCCM-WR | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 16-Sep-2025 | 08:00 | 16-Sep-2025 | 17:59 | OK
52 | 2025-09-15 13:34 |  |  | SATPURA - 400KV - BUS 2 |  | OCCM-WR | For replacemnet of Bus-2 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-ITARSI-1 is required) | 16-Sep-2025 | 09:00 | 19-Sep-2025 | 20:00 | OK
53 | 2025-09-15 13:34 |  |  | 400KV-SATPURA-ITARSI-1 |  | OCCM-WR | For replacemnet of Bus-2 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) And CT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO | 16-Sep-2025 | 09:00 | 19-Sep-2025 | 20:00 | OK
54 | [11 empty] | S/I , SLDC MPPTCL JABALPUR.
55
56
57