## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-21 |  |  | APPROVED OUTAGE LIST FOR DTD.21.09.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-20 12:43 | MR2509/0497 |  | 132KV_40 mva x-mer make ABB-1 | 220KV_ASHOKNAGAR | NON-OCCM-MP | HOT POINT ATTEND WORK | 21-09-2025 11:00:00 | 21-09-2025 15:00:00 | RAKESH SUMAN | 7587951093 | sub ld
2 | 2025-09-20 14:29 | MR2509/0503 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
3 | 2025-09-20 14:29 | MR2509/0504 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
4 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
5 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
6 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
7 | 2025-09-20 15:16 | MR2509/0506 | Continuous | 132KV_132 kv katni sleemnabad ckt 2 | 132KV_KATNI | NON-OCCM-MP | Modification work | 21-09-2025 09:00:00 | 23-09-2025 18:00:00 | pankaj yadav | 9406713326 | ok, EI approval required while charging
8 | 2025-09-20 11:19 | MR2509/0495 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-Ist | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 21-09-2025 09:00:00 | 23-09-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok, 132kv Baihar-Balaghat ckt, 132kv Waraseoni-Katangi ckt to be opened for load management, timely normalisation required
9 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
10 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
11 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
12 | 2025-09-20 12:51 | MR2509/0499 |  | 132KV_50 MVA BBL X-mer | 132KV_PATERA | NON-OCCM-MP | post monsoon maintenace | 21-09-2025 09:00:00 | 21-09-2025 14:00:00 | B K Sahu | 9425801433 | ok
13 | 2025-09-20 13:40 | MR2509/0500 |  | 132KV_132 KV Shahpura-Shrinagar DP Line | 132KV_SHAHPURA | NON-OCCM-MP | Flashover Disc replacement work at loc.No.170/B-Ph | 21-09-2025 10:00:00 | 21-09-2025 18:00:00 | Ashish Kumar | 9425805935 | ok, T&C and discom to be informed
14 | 2025-09-20 13:41 | MR2509/0501 |  | 132KV_132/33 KV 40 MVA BHEL X-MER | 220KV_SIDHI | NON-OCCM-MP | HV SIDE R,Y,&B PHASE C.T. REPLECEMENT WORK | 21-09-2025 09:00:00 | 21-09-2025 17:00:00 | S.K. SHAHU | 9425613436 | ok
15 | 2025-09-20 13:45 | MR2509/0502 |  | 132KV_132 KV SIDHI- MAUGANJ CKT-IST | 220KV_SIDHI | NON-OCCM-MP | FOR SEFTY CLEARENCE DUE TO 40 MVA BHEL C.T. REPLEC | 21-09-2025 09:00:00 | 21-09-2025 15:00:00 | S.K. SHAHU | 9425613436 | ok
16 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
17 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE