## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-11 |  |  | APPROVED OUTAGE LIST FOR DTD.11.07.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-10 16:29 | MR2507/0146 |  | 132KV_Shutdown (H/T) of 132 KV Amarpatan-Jhinna DCSS line | 132KV_AMARPATAN | NON-OCCM-WR | purpose of bay shifting work | 11-07-2025 10:00:00 | 11-07-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | shall be forwarded through T&C , also provide the FTC status of new bay
2 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
5 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
6 | 2025-07-10 14:39 | MR2507/0140 |  | 132KV_132KV ANUPPUR-DONGRITAL CKT | 132KV_DONGRITAL | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 11-07-2025 09:00:00 | 11-07-2025 12:00:00 | G.L SAHU | 9425805102 | ok
7 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
8 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
9 | 2025-07-10 15:18 | MR2507/0143 |  | 132KV_132kv 63mva xmer make bhel | 132KV_KANWAN | OCCM-MP | For replacement differential relay | 11-07-2025 10:00:00 | 11-07-2025 17:00:00 | Poshkar kushwaha | 9425813990 | sub ld
10 | 2024-11-20 16:45 | MR2411/0434 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
11 | 2024-11-20 16:47 | MR2411/0435 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 07-07-2025 09:00:00 | 12-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Continuous
12 | 2025-07-01 15:42 | MR2507/0010 | Continuous | 132KV_132 KV Khurai-Sagar | 132KV_KHURAI | NON-OCCM-MP | Modification/Shifting of 132 KV Khurai-Sagar | 02-07-2025 07:00:00 | 12-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
13 | 2025-07-10 14:03 | MR2507/0139 |  | 220KV_220KV Mandsour-Daloda-I | 400KV_MANDSOUR4 | OCCM-MP | 220KV Mandsour-Daloda-I Additional relay connectin | 11-07-2025 10:00:00 | 11-07-2025 17:00:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
14 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
15 | 2025-07-10 11:07 | MR2507/0135 |  | 132KV_132kV Keolari Nainpur | 132KV_NAINPUR | NON-OCCM-MP | Replacement of flashover disc insulator | 11-07-2025 14:00:00 | 11-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
16 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
17 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
18 | 2025-07-10 16:15 | MR2507/0144 |  | 132KV_132KV_BINA -RAJGHAT | 132KV_RAJGHAT | OCCM-MP | TESTING OF CT,CVT AND BKR | 11-07-2025 08:00:00 | 11-07-2025 19:00:00 | HARINANDAN DOHARE | 9340119307 | ok, through sub ld
19 | 2025-07-10 16:18 | MR2507/0145 |  | 132KV_132kV_ PICHHORE-RAJGHAT | 132KV_RAJGHAT | OCCM-MP | TESTING OF CT,CVT, AND BKR | 11-07-2025 08:00:00 | 11-07-2025 19:00:00 | HARINANDAN DOHARE | 9340119307 | shall be availed after normalisation of 132KV_BINA -RAJGHAT
20 | 2025-07-10 15:00 | MR2507/0142 |  | 132KV_132KV ANUPPUR-Rajmilan ckt | 132KV_RAJMILAN | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 11-07-2025 13:00:00 | 11-07-2025 17:00:00 | G.L SAHU | 9425805102 | line is in different configuration now
21 | 2025-07-01 16:13 | MR2507/0015 | Continuous | 400KV_400 KV MAIN BUS 2 | 400KV_SAGAR | OCCM-MP | FOR EXTENSION OF MAIN BUS 2 | 10-07-2025 09:00:00 | 11-07-2025 17:00:00 | ANIL MAHOR | 9425805149 | Deffered, not in WR list
22 | 2025-07-10 11:05 | MR2507/0134 |  | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of flashover dics insulator | 11-07-2025 10:00:00 | 11-07-2025 13:00:00 | S.K. Nadekar | 9425806848 | ok
23 | 2025-07-10 12:39 | MR2507/0137 |  | 132KV_132kv Tikamgarh-Interconnector | 220KV_TIKAMGARH | NON-OCCM-MP | 132kv CT Shifting & Overhead stringing work | 11-07-2025 08:00:00 | 11-07-2025 17:00:00 | Sameer Parte | 9575673359 | ok, o&m shall be infomed
24 | 2025-07-10 11:46 | MR2507/0136 |  | 220KV_220 KV Ujjain-Nagda Ckt-1st | 400KV_UJJAIN4 | NON-OCCM-MP | DPR 2nd relay installation &bay maintenance | 11-07-2025 10:00:00 | 11-07-2025 17:00:00 | Mr. Santosh Chavrasia | 942584677 | ok, through sub ld
25 | 2025-07-10 11:46 |  |  | 400KV/220KV ITARSI-ICT-2 |  | OCCM-WR | AMP of ICT#2 and Transformer Bay 208T, Dia to be kept open at both sides. | 11-Jul-2025 | 09:00 | 11-Jul-2025 | 20:00 | ok
26 | 2025-07-10 11:46 |  |  | 220KV-SEONI-MP-SEONI-PG-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 11-Jul-2025 | 09:00 | 11-Jul-2025 | 18:00 | real time
27 | 2025-07-10 11:46 |  |  | 220KV-INDORE-UJJAIN-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 11-Jul-2025 | 08:00 | 11-Jul-2025 | 18:00 | real time
28 | 2025-07-10 11:46 |  |  | 220KV-BETUL-PANDURNA-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 11-Jul-2025 | 08:00 | 11-Jul-2025 | 18:00 | real time
29 | 2025-07-10 11:46 |  |  | 220KV-KHANDWA-OMKARESHWAR-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK | 11-Jul-2025 | 08:00 | 11-Jul-2025 | 18:00 | real time
S/I, SLDC MPPTCL JBP.