## APPROVED SHUTDOWN
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-05 | APPROVED OUTAGE LIST FOR DATED 05.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 12:03 | MR2510/0056 | Daily | 220KV_220 kV Adampur-Hoshangabad line | 220KV_ADAMPUR | NON-OCCM-MP | Defective Disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
2 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | availability of data to be ensured by communication
3 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | availability of data to be ensured by communication
4 | 2025-10-04 14:50 | MR2510/0093 |  | 132KV_132 kV Shahdol-Dindori Circuit I | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW with new OPGW | 05-10-2025 07:00:00 | 05-10-2025 14:00:00 | Jitendra Tiwari | 9425805298 | ok
5 | 2025-10-04 12:27 | MR2510/0086 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 20 of lilo to 71 | 05-10-2025 09:00:00 | 10-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | as opportunity s/d
6 | 2025-10-04 14:27 | MR2510/0090 |  | 33KV_33KV MAIN BUS | 132KV_MANSAKRA | NON-OCCM-MP | 33KV MAIN BUS ISOLATOR MAINTENANCE WORK | 05-10-2025 08:00:00 | 05-10-2025 12:00:00 | ABHISHEK MISHRA | 9425801440 | o&m consent required
7 | 2025-10-02 15:27 | MR2510/0050 | Continuous | 220KV_220/132 Kv 160MVA BHEL 3 X-mer | 220KV_NARSINGHPUR | NON-OCCM-MP | Replacement of CB,PI&Mainbus isolator erection | 03-10-2025 09:00:00 | 08-10-2025 17:00:00 | Dinesh Kumar Kushwaha | 9425182413 | Continuous
8 | 2025-10-04 16:04 | MR2510/0096 |  | 132KV_50mva TAL -make transformer | 132KV_NIWARI | NON-OCCM-MP | Post mansoon maintenance | 05-10-2025 10:00:00 | 05-10-2025 16:00:00 | Pushpendra Kumar soni | 9425806398 | ok
9 | 2025-10-04 11:49 | MR2510/0084 |  | 220KV_160 MVA Xmer-3 | 220KV_PIPARIYA | NON-OCCM-WR | For post moonson maintenance work | 05-10-2025 09:00:00 | 05-10-2025 17:00:00 | B K Jhariya | 9425806831 | ok
10 | 2025-10-04 14:06 | MR2510/0088 |  | 220KV_220 KV MAIN BUS | 220KV_PITHAMPUR-II (SEC-I) | NON-OCCM-WR | 160 MVA X-MER NO,02 B PHASE MAIN BUS | 05-10-2025 08:00:00 | 05-10-2025 10:00:00 | RAJUDASH BAIRAGE | 9425801532 | ok, through sub ld, o&m shall be informed
11 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | availability of data to be ensured by communication
12 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | availability of data to be ensured by communication
13 | 2025-10-04 12:29 | MR2510/0087 |  | 400KV_400 KV MAIN BUS-I | 400KV_SATPURA TPS | NON-OCCM-MP | Attending hot points & alignment work of Y-Phase | 05-10-2025 09:30:00 | 05-10-2025 17:30:00 | YASHWANT WARATHE | 9425611046 | send emergency proposal to WRLDC for approval
14 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
15 |  |  |  | 132KV-VSTPS-WAIDHAN-1 | 132KV-VSTPS-WAIDHAN-1 |  | Annual Bay Maitenanace & Testing/ CRP replacement | 04-Oct-2025 | 08:08 | 11-Oct-2025 | 18:00 | real time
S/I SLDC JABALPUR