## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-08 |  |  | APPROVED OUTAGE LIST FOR DATED 08.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | LINE END (IN CASE OF LINE) | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma |  | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | WRPC APPROVAL REQUIRED
2 | 2025-09-03 12:14 | MR2509/0069 |  | 220KV_160 MVA XMER NO. 3 MAKE BBL | 220KV_BAIRAGARH | NON-OCCM-MP | Shutdown for post monsoon maintenance |  | 08-09-2025 09:00:00 | 08-09-2025 18:00:00 | Waiting | AMBARISH SHRIPAD JOSHI | 7587951085 | OK THROUGH SUB LD
3 | 2025-09-03 12:15 | MR2509/0070 |  | 220KV_160 MVA XMER NO. 3 MAKE BBL | 220KV_BAIRAGARH | NON-OCCM-MP | Shutdown for post monsoon maintenance |  | 08-09-2025 09:00:00 | 08-09-2025 18:00:00 | Waiting | AMBARISH SHRIPAD JOSHI | 7587951085 | -
4 | 2025-09-07 15:07 | MR2509/0163 |  | 132KV_40 MVA X-MER MAKE BBL | 132KV_BARMAN | NON-OCCM-MP | Postmonsoon maintenance & testing work |  | 08-09-2025 10:00:00 | 08-09-2025 18:00:00 | Waiting | Er K.K. Choure | 9425801357 | OK
5 | 2025-09-06 15:08 | MR2509/0153 | Daily | 132KV_132 kV Shahdol-Birsingpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW |  | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK
6 | 2025-09-06 08:08 | MR2509/0141 |  | 33KV_33KV MAIN BUS | 132KV_BISNOOR | NON-OCCM-MP | 33KV MAIN BUS ISOLATOR HOT POINT ATTENDING WORK |  | 08-09-2025 11:00:00 | 08-09-2025 14:00:00 | Waiting | ER SANJAY KUMAR PAWAR | 9425802293 | OK
7 | 2025-09-07 12:04 | MR2509/0155 |  | 220KV_160 MVA-III X-Mer | 400KV_CHHEGAON4 | NON-OCCM-MP | Post monsoon maintenance |  | 08-09-2025 10:00:00 | 08-09-2025 18:00:00 | Waiting | Shri Ganesh Mansare | 9425802441 | OK THROUGH SUB LD
8 | 2025-09-06 11:49 | MR2509/0148 |  | 132KV_132 kV Chhindwara-Khapaswami | 132KV_CHHINDWARA1 | NON-OCCM-MP | Old disc replacement & Bird guard provide |  | 08-09-2025 09:00:00 | 08-09-2025 17:00:00 | Waiting | A.M.Shende | 7587951136 | OK
9 | 2025-09-06 12:43 | MR2509/0149 |  | 132KV_50 MVA XMER BBL | 132KV_DEORI | NON-OCCM-MP | Post monsoon maintenance and testing work |  | 08-09-2025 11:00:00 | 08-09-2025 18:00:00 | Waiting | P D GOUTAM | 9425808329 | OK
10 | 2025-09-06 15:08 | MR2509/0154 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | Replacement of damaged OPGW |  | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK IF DATA REROUTING & CONFIRMATION FROM COMMUNICATION
11 | 2025-09-06 14:06 | MR2509/0151 |  | 132KV_132 Gourjhamar-Deori line (Radial feeder) | 132KV_GOURJHAMAR | NON-OCCM-MP | Line maintenance work |  | 08-09-2025 11:00:00 | 08-09-2025 18:00:00 | Waiting | J.P. Asati | 9424445533 | OK
12 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | WRPC APPROVAL REQUIRED
13 | 2025-09-06 11:15 | MR2509/0146 |  | 132KV_132 KV Itarsi-Hoshangabad I | 220KV_ITARSI | NON-OCCM-MP | Flash over disc replacement work |  | 08-09-2025 10:00:00 | 08-09-2025 17:00:00 | Waiting | Ashutosh Rai | 9425806902 | SUB LD
14 | 2025-06-30 16:18 | MR2506/0637 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK |  | 08-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED WRPC APPROVAL REQUIRED
15 | 2025-06-30 15:35 | MR2506/0627 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK |  | 08-09-2025 09:00:00 | 13-09-2025 08:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED WRPC APPROVAL REQUIRED
16 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | SUB LD
17 | 2025-09-07 13:20 | MR2509/0162 |  | 220KV_220kv badod 1 | 220KV_SUWASRA2 | NON-OCCM-MP | Providing M2 DPR relay work |  | 08-09-2025 09:00:00 | 08-09-2025 18:00:00 | Waiting | SUNIL PANWAR | 9425804939 | OK THROUGH SUB LD
18 | 2025-09-06 10:38 | MR2509/0144 |  | 220KV_220 KV Suwasara - Bhanpura line | 220KV_SUWASRA2 | NON-OCCM-MP | OPGW Stringing Work |  | 08-09-2025 10:00:00 | 08-09-2025 14:00:00 | Waiting | Ravindra Kumar Marskole | 9425814080 | DEFERRED, DATA REROUTING REQUIRED & CONFIRMATION FROM COMMUNICATION REQUIRED
19 | 2025-09-06 10:42 | MR2509/0145 |  | 220KV_220 KV Badod - Suwasara Ckt- 1 Line | 220KV_SUWASRA2 | NON-OCCM-MP | For OPGW Strining Work |  | 08-09-2025 10:00:00 | 08-09-2025 14:00:00 | Waiting | Ravindra Kumar Marskole | 9425814080 | DEFERRED, DATA REROUTING REQUIRED & CONFIRMATION FROM COMMUNICATION REQUIRED
20 | 2025-09-07 12:39 | MR2509/0156 |  | 220KV_220kv Tikamgarh -damoh (mpptcl)line | 220KV_TIKAMGARH | NON-OCCM-MP | Bay maintenance |  | 08-09-2025 10:00:00 | 08-09-2025 15:00:00 | Waiting | Pushpendra Kumar soni | 9425806398 | OK
21 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER |  | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Accepted | B.C JOSHI | 7587951137 | CONTINUE, FTC TO BE COMPLETED PRIOR TO CHARGING
22 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER |  | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Waiting | B.C JOSHI | 7587951137 | CONTINUE, FTC TO BE COMPLETED PRIOR TO CHARGING
23 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE |  | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | Accepted | RAJESH TIWARI | 7898239595 | CONTINUE
24 |  |  |  | 400KV-BADNAWAR-RAJGARH-2 | POWERGRID-WR2 (PGCIL),MADHYA PRADESH,GUJARAT |  | For Attending Hotspot in Line Isolator of Line Bay, Non auto mode of ckt 1 is required . Dia to be kept open at both ends. |  | 08-Sep-2025 | 10:00 | 08-Sep-2025 | 17:00 |  | OK THROUGH SUB LD
25 |  |  |  | 220KV-ITARSI-MP-ITARSI-1 | MADHYA PRADESH |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. |  | 08-Sep-2025 | 07:00 | 08-Sep-2025 | 17:00 |  | OK THROUGH SUB LD
26 |  |  |  | 220KV-MORENA-SABALGARH-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS |  | 08-Sep-2025 | 09:00 | 08-Sep-2025 | 17:00 |  | OK THROUGH SUB LD
27 |  |  |  | 220KV-SATNA-MAIHAR-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS |  | 08-Sep-2025 | 10:00 | 08-Sep-2025 | 17:00 |  | OK LOAD ON 132 KV SATNA - UNCHEHRA CKR & 132 KV SATNA - SATNA II CKT SHALL BE MONITORED AND IF REQUUIRED 132 KV MAIHAR - SATNA II CKT & 132 KV MAIHAR - UNCHEHRA CKT TO BE OPENED
28 |  |  |  | 220KV-BHANPURA-RANPUR-1 | POWERGRID-NR,NLDC,MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS |  | 08-Sep-2025 | 08:00 | 08-Sep-2025 | 18:00 |  | OK THROUGH SUB LD
S/I SLDC JABALPUR