## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-03
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-02 15:15 | MR2509/0048 |  | 220KV_220kv badnagar feeder -I | 400KV_BADNAWAR | NON-OCCM-WR | installation of double DPR work | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | Er. Abhishek verma | 9340855901 | OK THROUGH SUB LD
3 | 2025-09-02 13:27 | MR2509/0039 |  | 220KV_220KV BAROD-SUWASRA CKT-II | 220KV_BADOD | NON-OCCM-WR | DUE TO HOT POINT ATTENDING WORK & POST MONSOON MAI | 03-09-2025 10:30:00 | 03-09-2025 16:00:00 | ER Y.K.RATHORE | 9425804968 | OK THROUGH SUB LD
4 | 2025-09-02 13:22 | MR2509/0038 |  | 132KV_BETUL MULTAI | 220KV_BETUL | NON-OCCM-MP | Flash over disc replacement & other line main. wor | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | SHIV KUMAR | 9425806917 | SUB LD
5 | 2025-09-02 15:10 | MR2509/0046 |  | 132KV_132 kV Shahdol-Birsinghpur Circuit II | 220KV_BIRSINGHPUR | NON-OCCM-MP | essential shutdown on following line is needed to | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
6 | 2025-09-02 17:01 | MR2509/0060 |  | 132KV_132 kV Borgaon-Sausar RTS | 132KV_BOREGAON | NON-OCCM-MP | Flash over tension disc replace & Bird guard provi | 03-09-2025 10:00:00 | 03-09-2025 15:00:00 | A.M.Shende | 7587951136 | OK
7 | 2025-09-02 16:23 | MR2509/0057 |  | 132KV_132 kv chhatarpur-khajuraho ckt-II | 220KV_CHATARPUR | NON-OCCM-MP | FOR REPLACEMENT OF OLD DPR RELAY | 03-09-2025 13:00:00 | 03-09-2025 17:00:00 | Brajendra soni | 9131327770 | OK, 132 KV CHHATARPUR - KHAJURAHO TAP LAVKUSHNAGAR CKT TO BE IN SERVICE
8 | 2025-08-31 14:58 | MR2508/0437 | Continuous | 132KV_132 KV Chhatarpur-khajuraho Tap Lavkushnagar | 220KV_CHATARPUR | NON-OCCM-MP | for CT Tan delta measurement work | 01-09-2025 14:00:00 | 30-09-2025 17:30:00 | Brajendra Soni | 9131327770 | DEFERRED DUE TO SD ON 132KV CHHATARPUR - KHAJURAHO CKT - II
9 | 2025-09-02 16:19 | MR2509/0055 |  | 220KV_160 mva areva xmer | 220KV_CHATARPUR | NON-OCCM-MP | for replacement of old 132 kv incoming side panel | 03-09-2025 08:00:00 | 03-09-2025 12:00:00 | Brajendra soni | 9131327770 | OK
10 | 2025-09-02 16:22 | MR2509/0056 |  | 132KV_132 kv chhatarpur-khajuraho ckt-II | 220KV_CHATARPUR | NON-OCCM-MP | FOR REPLACEMENT OF OLD DPR RELAY | 03-09-2025 13:00:00 | 03-09-2025 17:00:00 | Brajendra soni | 9131327770 | OK, 132 KV CHHATARPUR - KHAJURAHO TAP LAVKUSHNAGAR CKT TO BE IN SERVICE
11 | 2025-09-02 13:00 | MR2509/0035 |  | 220KV_Daloda Mandsaur- II | 220KV_DALODA | NON-OCCM-MP | DTPC Connection work. | 03-09-2025 12:00:00 | 03-09-2025 14:00:00 | ER. Shailendra Bourasi | 990724645 | OK THROUGH SUB LD, AFTER REVIVAL OF THE OTHER CIRCUIT
12 | 2025-09-02 12:54 | MR2509/0034 |  | 220KV_Daloda Mandsaur-I | 220KV_DALODA | NON-OCCM-MP | DTPC Work. | 03-09-2025 10:00:00 | 03-09-2025 12:00:00 | Er. Shailendra Bourasi | 9907246485 | OK THROUGH SUB LD, AFTER REVIVAL OF THE OTHER CIRCUIT
13 | 2025-09-02 13:07 | MR2509/0037 |  | 220KV_220KV Daloda-Jaora | 220KV_DALODA | NON-OCCM-MP | DTPC Connection | 03-09-2025 14:00:00 | 03-09-2025 16:00:00 | ER. Shailendra Bourasi | 9907246485 | OK THROUGH SUB LD, AFTER REVIVAL OF THE OTHER CIRCUIT
14 | 2025-09-02 15:11 | MR2509/0047 |  | 132KV_132/33kv 50MVA BBL x-mer | 132KV_DINDORI | NON-OCCM-MP | LV side y-ph.damage conductor between CT to Breake | 03-09-2025 10:00:00 | 03-09-2025 13:00:00 | Vijay Kumar.sahu | 9893349422 | OK
15 | 2025-09-02 13:01 | MR2509/0036 |  | 132KV_40MVA XMER(TELK) | 132KV_GOURJHAMAR | NON-OCCM-MP | Post monsoon maintenance and testing work | 03-09-2025 11:00:00 | 03-09-2025 18:00:00 | P D goutam | 9425808329 | OK
16 | 2025-09-02 16:23 | MR2509/0058 |  | 220KV_220 KV Hoshangabad Mandideep Line | 220KV_HOSHANGABAD | NON-OCCM-MP | For LBB Testing | 03-09-2025 11:00:00 | 03-09-2025 15:00:00 | V.P.DWIVEDI | 9425804799 | OK THROUGH SUB LD
17 | 2025-09-02 11:35 | MR2509/0032 |  | 132KV_132 KV Itarsi-Hoshangabad Ckt- I | 220KV_HOSHANGABAD | NON-OCCM-MP | Flash over disc replacement work | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | Ashutosh Rai | 9425806902 | SUB LD
18 | 2025-08-29 11:42 | MR2508/0399 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
19 | 2025-08-30 10:24 | MR2508/0413 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 30-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
20 | 2025-09-01 09:57 | MR2509/0001 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line. | 220KV_INDORE-SZ | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 01-09-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
21 | 2025-08-29 13:01 | MR2508/0403 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
22 | 2025-08-31 11:39 | MR2508/0427 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 31-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
23 | 2025-09-02 09:58 | MR2509/0030 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 02-09-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING & COMMUNICATION CONFIRMATION REQUIRED
24 | 2025-08-28 13:25 | MR2508/0379 |  | 220KV_220KV Itarsi(MPPTCL) - PGCIL no.2 | 220KV_ITARSI | OCCM-MP | Rep of 220KV CTs | 03-09-2025 07:00:00 | 03-09-2025 19:00:00 | J.D.Khoria | 9425804975 | DEFERRED, WRPC CONSENT REQUIRED
25 | 2025-09-02 16:41 | MR2509/0059 |  | 132KV_132 kV Jabalpur- Madhotal ckt-II | 220KV_JABALPUR | NON-OCCM-MP | Damaged conductor repair at loc. 40-41 B Ph | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
26 | 2025-09-02 15:53 | MR2509/0053 |  | 132KV_40MVA APEX X-mer | 132KV_KATNI | NON-OCCM-MP | To attend oil leakage from OLTC | 03-09-2025 11:00:00 | 03-09-2025 17:00:00 | Yogesh patel | 9770256350 | OK O&M TO BE INTIMATED
27 | 2025-06-30 16:15 | MR2506/0636 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
28 | 2025-06-30 15:33 | MR2506/0626 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
29 | 2025-09-02 16:07 | MR2509/0054 |  | 220KV_160 MVA X-MER IMP | 220KV_KOTAR | OCCM-MP | OIL TOPPING AND LEKAGE ATTENDING WORK | 03-09-2025 14:00:00 | 03-09-2025 16:00:00 | ARUN KUMAR KOL | 8319677721 | OK
30 | 2025-09-02 15:25 | MR2509/0051 |  | 132KV_Marhotal â¿¿Jabalpur ckt-2 | 132KV_MADHOTAL | NON-OCCM-MP | CT replacement work due to high tandelta problem | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | A.K. Pandey | 9424645081 | OK, PROTECTION UNDERTAKING TO BE SUBMITTED PRIOR TO CHARGING
31 | 2025-09-02 15:31 | MR2509/0052 |  | 33KV_33 KV Main bus and both x-mer | 220KV_MAIHAR | NON-OCCM-MP | attending 33 kv main bus sec. isolator hot point | 03-09-2025 09:00:00 | 03-09-2025 11:00:00 | Arun kumar | 9425802368 | O&M CONSENT REQUIRED
32 | 2025-09-02 13:41 | MR2509/0040 |  | 132KV_Shutdown (H/T) of 132 kv Katra-Mangawan DCSS line | 132KV_MANGAWAN | NON-OCCM-WR | purpose of flash over disc replacement & other mai | 03-09-2025 09:00:00 | 03-09-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | OK
33 | 2025-09-02 14:17 | MR2509/0044 |  | 50MVA_132/33KV_TAL_Xmer_2 | 132KV_PHOOLBAGH GIS | NON-OCCM-MP | Post monsoon maintenance and testing work | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | RAKSHA CHAPARRIYA | 6265080313 | SUB LD
34 | 2025-09-02 13:49 | MR2509/0041 |  | 400KV_400kV Pithampur-Badnawar Ckt-I | 400KV_PITHAMPUR4 | NON-OCCM-MP | pad clamp replace on R- Phase Line side isolator | 03-09-2025 09:00:00 | 03-09-2025 18:00:00 | Sh. Rajudash bairagi | 9425801532 | OK THROUGH SUB LD
35 | 2025-09-02 15:18 | MR2509/0049 |  | 220KV_220 kV Birsingpur TPS-Shahdol Circuit | 400KV_SGTPS | NON-OCCM-MP | essential shutdown on following line is needed to | 03-09-2025 10:00:00 | 03-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
36 | 2025-09-02 11:43 | MR2509/0033 |  | 400KV_SINGHAJI-TPS-II-PITHAMPUR4_Ckt_3 | 400KV_SINGHAJI-TPS-II | NON-OCCM-MP | PMU Installation work by MPPTCL | 03-09-2025 10:00:00 | 03-09-2025 18:00:00 | Mr. Sharad Tiwari | 7987469237 | OK THROUGH SUB LD
37 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK THROUGH SUB LD
38 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
39 |  |  |  | MPPGCL SILPARA | MACHINES S/D |  | TRASH RACK CLEANING | 2025-09-03 10:00 | 2025-09-03 17:30 |  |  | AS PER SYSTEM REQUIREMENT
40 |  |  | Continuous | 132 KV JABALPUR SHAHPURA | 132 KV JABALPUR SHAHPURA |  | LOC. NO. 5 TAWAR REPLACE WORK | 28.08.25 10:00 | 06.09.2025 19:00 |  |  | CONTINUE
41 |  |  |  | 132 KV SIDHI-MAUGANJ CKT-I | 220 KV S/S SIDHI |  | LINE MAINTENANCE WORK | 2025-09-03 10:00 | 03-0-2025 17:00 |  |  | DEFERRED, FOR 1 DAY DUE TO S/D OF 132 KV KATRA MANGAWAN
42 |  | 260568 |  | 220KV-SHUJALPUR-SHUJALPUR-MP-1 | 220 | Daily | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 03-Sep-2025 | 09:00 | 17:00 |  | OK THROUGH SUB LD
43 |  | 262516 |  | 220KV-ANNUPUR-KOTMIKALA-2 | 220 | Daily | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 03-Sep-2025 | 08:00 | 17:59 |  | OK
44 |  | 261455 |  | 400KV-SSP-RAJGARH-1 | 400 | Daily | For Y-Phase CVT Replaement of Line, Non auto mode of ckt 2 is required . Dia to be kept open at both ends. | 03-Sep-2025 | 09:30 | 18:00 |  | OK THROUGH SUB LD
45 |  | 260626 |  | 400KV-SATPURA-ITARSI-1 | 400 | Continous | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) AND CT Oil sampling at Itarsi And CVT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO | 02-Sep-2025 | 09:00 | 20:00 |  | CONTINUE
46 |  | 260627 |  | SATPURA - 400KV - BUS 1 | 400 | Continous | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-ITARSI-1 is required) | 02-Sep-2025 | 09:00 | 20:00 |  | CONTINUE