## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-03
Control Area : | ALL | Circle : | ALL |  | APPROVED SHUTDOWN LIST FOR 03.08.25
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-29 10:54 | MR2507/0453 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | Deffered by site
2 | 2025-07-27 14:12 | MR2507/0430 | Continuous | 132KV_132 KV Khurai- Sagar ckt | 132KV_KHURAI | NON-OCCM-MP | For modification work of above line | 27-07-2025 07:00:00 | 03-08-2025 18:00:00 | Sanjay singh thakur | 9425806936 | Continuous
3 | 2025-08-02 12:37 | MR2508/0019 |  | 132KV_132KV Mandsaur Interconnector circuit IInd | 132KV_MANDSOUR | NON-OCCM-MP | For Maintenance work | 03-08-2025 10:00:00 | 03-08-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
4 | 2025-07-24 12:24 | MR2507/0380 | Continuous | 400KV_400 KV Main Bus-2nd | 400KV_MANDSOUR4 | NON-OCCM-MP | Overhead stringing work | 29-07-2025 09:00:00 | 05-08-2025 18:00:00 | J.P. Parmar | 9425806919 | 400kv Main bus 1 is approved for 3-4Aug, WRLDC code to be taken
5 | 2025-07-29 10:59 | MR2507/0454 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | for replacement existing of 24 Fibre OPGW by 48 Fi | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | Deffered by site
6 | 2025-07-28 18:36 | MR2507/0449 | Daily | 220KV_220 KV Narsinghpur-Chichli-Pipariya Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Rectification/replacement/work between Tower No-33 | 30-07-2025 09:00:00 | 05-08-2025 18:00:00 | Ashish Kumar | 9425805935 | communication data availability to be confirmed
7 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
8 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
9 | 2025-07-16 11:07 | MR2507/0209 | Continuous | 500MVA_400/220KV_BHEL_Xmer | 400KV_SGTPS | NON-OCCM-MP | Relay testing,Air cell replacement,DCRM and testin | 01-08-2025 08:00:00 | 06-08-2025 18:00:00 | Pramod Mishra | 8989973149 | Continuous
10 | 2025-08-01 10:04 | MR2508/0001 | Continuous | 220KV_220 KV/11&6.6 kV, 63 MVA Station Trf-5A | 400KV_SGTPS | NON-OCCM-MP | testing of numerical relay, DCRM of Bkr,aircell re | 01-08-2025 09:00:00 | 04-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
11 |  |  |  | MANDSAUR-MP - 400KV - BUS 1 |  | MADHYA PRADESH | for isolator alignment work, bus extension and high bus overhead stringing work for installation of new 500MVA ICT | 2025-08-03 09:00 | 2025-08-04 17:59 |  |  | ok, through sub ld, All elements to be in service with BUS 2. In N-1 case all elements will trip. Load to be managed by SLDC MP.
12 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 |  | MAHARASHTRA | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 2025-08-03 07:00 | 2025-08-04 18:59 |  |  | PK, A/R in N/A, Line will be in service.
S/I, SLDC , MPPTCL,JBP