## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-22 |  |  | APPROVED OUTAGE LIST FOR DTD.22.09.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-21 09:59 | MR2509/0516 |  | 400KV_315 MVA X-MER NO.1ST MAKE CGL | 400KV_ASHTA4 | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 22-09-2025 08:00:00 | 22-09-2025 17:00:00 | JITENDRA LOHANA | 9425804978 | Deffered due to s/d on Bhopal ICT
2 | 2025-09-15 14:04 | MR2509/0337 | Continuous | 400KV_315 MVA X-MER NO.3 (BHEL) | 400KV_BHOPAL4 | NON-OCCM-MP | POSTTMONSOON MAINTENENCE | 22-09-2025 09:00:00 | 23-09-2025 18:00:00 | AKRAM KAHN | 9425804695 | ok, through sub ld
3 | 2025-09-20 14:29 | MR2509/0503 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
4 | 2025-09-21 14:56 | MR2509/0527 |  | 132KV_132 kV Chhatarpur â¿¿ Khajuraho Ckt-1 Tap Lovkushnagar Line | 220KV_CHATARPUR | NON-OCCM-MP | AH,VD Tightening & other line maintenance work | 22-09-2025 10:00:00 | 22-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
5 | 2025-09-21 15:59 | MR2509/0530 |  | 220KV_220kv Chhindwara -Pandhurna feeder | 220KV_CHHINDWARA | OCCM-MP | F/o disc insulator replacement work | 22-09-2025 09:00:00 | 22-09-2025 17:00:00 | A.M Shende | 8319697216 | ok
6 | 2025-09-20 14:29 | MR2509/0504 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
7 | 2025-09-21 15:32 | MR2509/0528 |  | 132KV_132KV Anuppur-Dongrital ckt | 132KV_DONGRITAL | NON-OCCM-MP | disc replacement work | 22-09-2025 09:00:00 | 22-09-2025 17:00:00 | G.L SAHU | 9425805102 | ok
8 | 2025-09-21 12:15 | MR2509/0523 |  | 220KV_220 kv 160 MVA x-mer - 1st BHEL | 220KV_GUNA | NON-OCCM-MP | B phase isolator claimp hot point CB to isolator | 22-09-2025 11:30:00 | 22-09-2025 15:00:00 | Sagar singh Dhakad | 9589205697 | ok, through sub ld
9 | 2025-09-20 17:01 | MR2509/0507 |  | 132KV_132 KV Hoshangabad-Khatpura | 220KV_HOSHANGABAD | NON-OCCM-MP | Changing jumper at location No. 24 Y phase | 22-09-2025 10:00:00 | 22-09-2025 17:00:00 | Ashutosh Rai | 9425806902 | sub ld
10 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
11 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
12 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
13 | 2025-09-21 10:21 | MR2509/0517 |  | 132KV_INCOMMING OF 160MVA TRANSFORMER-III&IV | 220KV_INDORE-SZ | NON-OCCM-MP | ATTEND HOT POINT ON 132 KV MAIN BUS SECTION-II | 22-09-2025 06:00:00 | 22-09-2025 10:00:00 | DHARMENDRA KUSHWAHA | 9425802801 | ok, Through sub ld, discom to be informed
14 | 2025-09-18 17:36 | MR2509/0457 | Continuous | 400KV_315MVA ICT-2 | 400KV_INDORE4 | NON-OCCM-MP | Post monsoon mainteance | 22-09-2025 09:00:00 | 23-09-2025 17:00:00 | atul paradkar | 9425804929 | ok, through sub ld
15 | 2025-09-08 14:47 | MR2509/0183 |  | 220KV_220KV Itarsi (MPPTCL)-PGCIL Itarsi No.2 | 220KV_ITARSI | OCCM-MP | Replacement of CTs | 22-09-2025 07:00:00 | 22-09-2025 19:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
16 | 2025-09-20 17:49 | MR2509/0510 |  | 160MVA_220/132KV_BHEL_X'mer_1 | 400KV_JULWANIYA4 | NON-OCCM-MP | Post monsoon maintenance & testing work | 22-09-2025 09:00:00 | 22-09-2025 17:30:00 | ER. Ravindra Patil | 8305612190 | ok, through sub ld
17 | 2025-09-19 13:56 | MR2509/0474 |  | 132KV_50MVA BBL Transformer No. 2 | 132KV_KATANGI | NON-OCCM-MP | Post Mansoon maintenance | 22-09-2025 10:00:00 | 22-09-2025 17:00:00 | Seema Dongre | 9425807247 | o&m consent required
18 | 2025-09-20 15:16 | MR2509/0506 | Continuous | 132KV_132 kv katni sleemnabad ckt 2 | 132KV_KATNI | NON-OCCM-MP | Modification work | 21-09-2025 09:00:00 | 23-09-2025 18:00:00 | pankaj yadav | 9406713326 | EI approval required
19 | 2025-09-20 11:19 | MR2509/0495 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-Ist | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 21-09-2025 09:00:00 | 23-09-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok, 132kv Balaghat-Baihar ckt and 132kv Waraseoni-Katangi ckt to be opened for load management
20 | 2025-09-21 11:04 | MR2509/0520 |  | 132KV_132/33 KV 40 MVA Xmer BHEL | 132KV_LAUNDI | NON-OCCM-MP | for Post Monsoon Maintenance | 22-09-2025 09:00:00 | 22-09-2025 13:00:00 | Brajendra Soni | 9131327770 | ok
21 | 2025-09-21 11:06 | MR2509/0521 |  | 132KV_132/33 KV 50 MVA Xmer TA | 132KV_LAUNDI | NON-OCCM-MP | for post monsoon Maintenance | 22-09-2025 14:00:00 | 22-09-2025 18:00:00 | Brajendra Soni | 9131327770 | ok
22 | 2025-09-21 10:36 | MR2509/0519 |  | 220KV_220kV PGCIL - Malanpur ckt-I | 220KV_MALANPUR | OCCM-MP | Line Maintenance work | 22-09-2025 10:00:00 | 22-09-2025 17:00:00 | Pankaj Kumar | 9425805317 | ok, through sub ld
23 | 2025-09-21 08:44 | MR2509/0515 |  | 160MVA_220/132KV_BHEL_X'mer | 220KV_NEPANAGAR | NON-OCCM-MP | Post mansoon maintenance work | 22-09-2025 11:00:00 | 22-09-2025 17:00:00 | M. K. Pawar | 9425805191 | ok, through sub ld
24 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
25 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
26 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
27 | 2025-09-20 14:56 | MR2509/0505 |  | 132KV_132 kV Pandhurna-Multai | 220KV_PANDHURNA | NON-OCCM-MP | Flash over disc replaced and Bird guard provide | 22-09-2025 09:00:00 | 22-09-2025 18:00:00 | A.M.Shende | 7587951136 | ok, through sub ld
28 | 2025-09-21 13:53 | MR2509/0525 |  | 132KV_40 MVA-I Transformer | 132KV_PETLAWAD | NON-OCCM-MP | for Post Monsoon maintenace work | 22-09-2025 10:00:00 | 22-09-2025 18:00:00 | Er Varsingh mohoniya | 9425803496 | sub ld
29 | 2025-09-21 14:24 | MR2509/0526 |  | 132KV_40MVA Xmer-1 BBL | 132KV_REWA1 | NON-OCCM-MP | PMM | 22-09-2025 10:00:00 | 22-09-2025 18:00:00 | Kanishka Singh | 9425804656 | ok
30 | 2025-09-20 10:47 | MR2509/0494 |  | 132KV_132kV Seoni Lakhnadon SC Feeder | 220KV_SEONI | NON-OCCM-MP | Work for replacement of flashover disc insulator | 22-09-2025 10:00:00 | 22-09-2025 17:00:00 | S.K. Nadekar | 9425806848 | ok
31 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
32 | 2025-09-19 16:38 | MR2509/0489 |  | 220KV_160 MVA X-MER-IIIrd (Make BHEL-IInd) | 220KV_UJJAIN | NON-OCCM-MP | Post monsoon maintenance and testing work | 22-09-2025 09:00:00 | 22-09-2025 17:00:00 | B.C JOSHI | 7587951137 | Deffered due to s/d on 160MVA NGEF
33 | 2025-09-21 10:27 | MR2509/0518 |  | 220KV_160MVA X-MER-II BHEL | 220KV_VIDISHA | OCCM-MP | POST MANSOON MAINTENANCE WORK | 22-09-2025 09:00:00 | 22-09-2025 18:00:00 | KC GOSAWMI | 9425804976 | ok, through sub ld
34 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | completed
35 | 2025-09-21 10:27 |  |  | 400KV/220KV SATNA-ICT-2 |  | OCCM-WR | AMP Works, Dia to be kept open at both sides. | 22-Sep-2025 | 09:00 | 22-Sep-2025 | 18:00 | ok
36 | 2025-09-21 10:27 |  |  | DAMOH - 220KV - BUS 2 |  | OCCM-WR | Simultaneous outage of DAMOH - 220KV - BUS 2 and BUS COUPLER BAY is required for Retrofitting of CGL CB in Bus coupler BAY | 22-Sep-2025 | 09:00 | 22-Sep-2025 | 18:00 | ok
37 | 2025-09-21 10:27 |  |  | 400KV-BHOPAL-MP-ITARSI-1 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 22-Sep-2025 | 09:00 | 22-Sep-2025 | 18:00 | real time
38 | 2025-09-21 10:27 |  |  | 400KV-BADNAWAR-RAJGARH-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 22-Sep-2025 | 08:00 | 22-Sep-2025 | 18:00 | real time
39 | 2025-09-21 10:27 |  |  | 220KV-GWALIOR-MALANPUR-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 22-Sep-2025 | 09:00 | 22-Sep-2025 | 17:00 | ok, through sub ld
40 | 2025-09-21 10:27 |  |  | 220KV-ITARSI-MP-ITARSI-2 |  | OCCM-WR | replacement of All existing 3No’s CT’s having CTR-1200/1A with new 1600/1A CT’s at 220KV Substation MPPTCL Itarsi | 22-Sep-2025 | 07:00 | 22-Sep-2025 | 19:59 | ok, through sub ld
41 | 2025-09-21 10:27 |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  | OCCM-WR | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 22-Sep-2025 | 07:00 | 22-Sep-2025 | 23:59 | ok
42 | 2025-09-21 10:27 |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  | OCCM-WR | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 22-Sep-2025 | 07:00 | 22-Sep-2025 | 19:59 | ok
S/I, SLDC MPPTCL JABALPUR