## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-14 |  |  | APPROVED OUTAGE LIST FOR DTD.14.06.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-05 11:27 | MR2506/0089 | Daily | 132KV_132 kV Seoni-Amarwara | 132KV_AMARWARA | NON-OCCM-MP | PID defective disc insulator replacement | 06-06-2025 08:00:00 | 15-06-2025 18:00:00 | A.M.Shende | 7587951136 | ok,
2 | 2025-06-11 15:25 | MR2506/0251 |  | 220KV_220 KV Anuppur-Kotmikala Circuit II | 220KV_ANUPPUR | NON-OCCM-MP | For low ground Clearance maintenance between Span | 14-06-2025 08:00:00 | 14-06-2025 18:00:00 | Jitendra Tiwari | 9425805298 | Deffered, not in WRPC approval list
3 | 2025-06-13 14:55 | MR2506/0296 |  | 132KV_132 kV Anuppur-Kotma Circuit II | 220KV_ANUPPUR | NON-OCCM-MP | Replace of broken disc & other line maint. | 14-06-2025 10:00:00 | 14-06-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok, o&m to be informed
4 | 2025-06-12 11:11 | MR2506/0261 | Daily | 400KV_400 KV ASHTA UJJAIN LINE 1, 2 | 400KV_ASHTA4 | NON-OCCM-MP | LIVE LINE PERMIT FOR FIBER MAINTENANCE SPLICING | 12-06-2025 09:00:00 | 20-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
5 | 2025-06-13 16:56 | MR2506/0301 |  | 132KV_132kv Badnagar - Berchha line | 220KV_BADNAGAR | NON-OCCM-MP | for PSS maintenance activity work | 14-06-2025 09:00:00 | 14-06-2025 17:00:00 | Kumar Vishal | 9425805018 | sub ld
6 | 2025-06-13 11:02 | MR2506/0289 |  | 132KV_132kV Baihar-Mandla Line | 132KV_BAIHAR | NON-OCCM-MP | Work For Emergency Tree Cutting & Other Line Maint | 14-06-2025 10:00:00 | 14-06-2025 17:00:00 | S.K. BHALADHARE | 9425807264 | ok
7 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
8 | 2025-06-12 09:07 | MR2506/0260 | Daily | 220KV_220 KV Bina- Pichhore & 220 KV Bina- Datia Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW work By M/s ZTT | 12-06-2025 07:00:00 | 18-06-2025 19:00:00 | Satish Kumar Bhagat & Sanjay Singh Thakur | 9425806916 | ok, line to be in service
9 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
10 | 2025-06-13 16:07 | MR2506/0300 |  | 132KV_132kV Gwalior(shithouli) - Hastinapur ckt-I | 220KV_GWALIOR-II | NON-OCCM-MP | Line Maintenance work | 14-06-2025 10:00:00 | 14-06-2025 17:00:00 | Pankaj Kumar | 9425805319 | sub ld
11 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
12 | 2025-06-02 17:12 | MR2506/0039 | Continuous | 400KV_U#03 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE OF SAID UNIT | 03-06-2025 06:00:00 | 15-06-2025 18:00:00 | SHRI VINAI MISHRA | 9575074321 | as per system requirement
13 | 2025-06-07 15:56 | MR2506/0146 | Daily | 220KV_220 kv NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 09-06-2025 07:00:00 | 18-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered, not in WRPC approval list
14 | 2025-06-07 16:07 | MR2506/0147 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 09-06-2025 07:00:00 | 18-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered, not in WRPC approval list
15 | 2025-06-05 18:29 | MR2506/0120 | Daily | 220KV_220KV North Zone â¿¿ Hatuniya (PGCIL) Ckt.-1 & 2 Line | 220KV_INDORE-NZ | NON-OCCM-MP | E/W replacement work by 24 Fibre OPGW Wire | 06-06-2025 07:00:00 | 15-06-2025 19:00:00 | A.R.KANEL | 9425805217 | Deffered, not in WRPC approval list
16 | 2025-05-31 14:48 | MR2505/0647 | Daily | 220KV_220 Southzone - Jaitpura | 220KV_INDORE-SZ | NON-OCCM-MP | Hotline Work permit (PTW) | 01-06-2025 07:00:00 | 15-06-2025 19:00:00 | A.R. KANEL | 9525805217 | ok, line to be in service
17 | 2025-05-31 14:15 | MR2505/0645 | Daily | 220KV_(20KV INDORE (400KV) - MAGLIYA LINE | 400KV_INDORE4 | NON-OCCM-MP | Hotline work permit (PTW) | 01-06-2025 07:00:00 | 15-06-2025 19:00:00 | A.R. KANEL | 9525805217 | ok, line to be in service
18 | 2025-05-23 18:38 | MR2505/0487 | Continuous | 220KV_NARSINGHPUR-JABALPUR_Ckt_2 | 220KV_JABALPUR | NON-OCCM-MP | BUNCHING OF 132KV JBP SHAHPURA WITH220 KV JBP NSP | 26-05-2025 09:00:00 | 20-06-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Deffered by site
19 | 2025-06-13 11:29 | MR2506/0290 |  | 132KV_40 MVA ABB X-MER | 132KV_KATNI | NON-OCCM-MP | 33KV Structure Aluminum Painting Work | 14-06-2025 07:00:00 | 14-06-2025 09:00:00 | YOGESH PATEL | 9425808211 | ok
20 | 2025-04-12 15:54 | MR2504/0337 | Continuous | 400KV_400KV KATNI DAMOH | 400KV_KATNI4 | NON-OCCM-MP | For Strenghtening Continues work . | 09-06-2025 09:00:00 | 14-06-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deferred
21 | 2025-04-12 16:01 | MR2504/0338 | Continuous | 220KV_220KV KATNI DAMOH | 400KV_KATNI4 | NON-OCCM-MP | For Strenghtening Continues work . | 09-06-2025 09:00:00 | 14-06-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deferred
22 | 2025-06-12 12:51 | MR2506/0265 | Daily | 220KV_220KV Daloda-Mandsaur | 220KV_NEEMUCH | NON-OCCM-MP | OPGW OTDR testing & OPGW Splicing | 13-06-2025 08:30:00 | 17-06-2025 18:30:00 | Gaurav Goyal | 9425805120 | ok, line to be in service, data affected to be filled manually for report preparation by SLDC CR
23 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
24 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered by site
25 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered by site
26 | 2025-06-13 13:33 | MR2506/0292 |  | 132KV_132kv Sabalgarh joura Ckt | 220KV_SABALGARH | NON-OCCM-MP | Line Maintenance work | 14-06-2025 09:00:00 | 14-06-2025 17:00:00 | Suraj Pawar | 9425814079 | sub ld
27 | 2025-06-13 13:54 | MR2506/0293 | Continuous | 132KV_132kv Viajypur Solar Plant | 220KV_SABALGARH | NON-OCCM-MP | testing of Line CT and PT, SF6 breaker | 14-06-2025 19:00:00 | 15-06-2025 05:00:00 | Suraj Pawar | 9425814079 | sub ld
28 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
29 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
30 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
31 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
32 | 2025-04-17 17:34 | MR2504/0479 |  | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
33 | 2025-04-17 17:34 |  |  | 220KV-GWALIOR-MAHALGAON-1 |  | OCCM-WR | FOR BAY MAINTENANCE & TESTING WORK | 14-Jun-2025 | 09:00 | 14-Jun-2025 | 17:00 | real time
34 | 2025-04-17 17:34 |  |  | 220KV-BETUL-PANDURNA-1 |  | OCCM-WR | FOR CONDUCTOR RE-SAGGING WORKS IN VARIOUS SECTION | 14-Jun-2025 | 08:00 | 14-Jun-2025 | 18:00 | real time
35 | 2025-04-17 17:34 |  |  | 400KV-DAMOH-KATNI-1 |  | OCCM-WR | TOWER STRENGTHENING WORK | 09-Jun-2025 | 09:00 | 14-Jun-2025 | 18:00 | deffered
S/I, SLDC MPPTCL JABALPUR