## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-25 |  | APPROVED OUTAGE LIST FOR DATED 25.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-24 12:10 | MR2509/0634 |  | 132KV_132KV Amarwara-Seoni line. | 132KV_AMARWARA | NON-OCCM-MP | LA Shifting Work | 25-09-2025 10:00:00 | 25-09-2025 17:00:00 | S.K.OKTE | 7587951132 | ok
2 | 2025-09-24 13:49 | MR2509/0647 |  | 132KV_40 MVA BBL | 132KV_BADAMALHERA | NON-OCCM-MP | for post monsoon maintenance | 25-09-2025 14:00:00 | 25-09-2025 18:00:00 | Brajendra Soni | 9131327770 | ok
3 | 2025-09-24 13:08 | MR2509/0640 |  | 132KV_50 MVA Transformer BBL | 132KV_BADAMALHERA | NON-OCCM-MP | For Post Monsoon Maintenance | 25-09-2025 09:00:00 | 25-09-2025 13:00:00 | Brajendra Soni | 9131327770 | ok
4 | 2025-09-24 11:51 | MR2509/0628 |  | 132KV_63 MVA X-MER BBL MAKE | 132KV_BARMAN | NON-OCCM-MP | Postmonsoon maintenance & testing work | 25-09-2025 10:30:00 | 25-09-2025 18:00:00 | Er K.K. Choure | 9425801357 | ok
5 | 2025-09-24 12:35 | MR2509/0637 |  | 132KV_Betul Multai | 220KV_BETUL | NON-OCCM-MP | Flash over disc replacement & other line maint wor | 25-09-2025 10:00:00 | 25-09-2025 17:00:00 | SHIV KUMAR | 9425806917 | sub ld
6 | 2025-09-22 12:57 | MR2509/0546 | Continuous | 400KV_315 MVA X-MER NO.3 | 400KV_BHOPAL4 | NON-OCCM-MP | POSTTMONSOON MAINTENENCE | 25-09-2025 09:00:00 | 26-09-2025 18:00:00 | AKRAM KAHN | 9425804695 | Deffered due to Bina ICT s/d
7 | 2025-09-24 15:41 | MR2509/0658 |  | 132KV_40 MVA (BBL-I) X-MER-II | 220KV_BINA | NON-OCCM-MP | POST MONSOON MAINTENANCE AND 33KV CT REPLACEMENT W | 25-09-2025 09:00:00 | 25-09-2025 18:00:00 | LALIT SINGH | 9425806845 | ok, o&m shall be informed
8 | 2025-09-24 13:21 | MR2509/0642 |  | 400KV_400/220 kV,315MVA X;mer-I(EMCO) | 400KV_BINA4 | NON-OCCM-MP | Post Monsoon maintenance work | 25-09-2025 09:00:00 | 25-09-2025 18:00:00 | Er. Parmnand Namdeo | 7587951092 | ok, through sub ld
9 | 2025-09-20 14:29 | MR2509/0503 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
10 | 2025-09-24 13:59 | MR2509/0649 | Daily | 315MVA_400/220KV__X'mer_2 | 400KV_CHHEGAON4 | NON-OCCM-MP | For post monsoon | 25-09-2025 10:00:00 | 26-09-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | ok, through sub ld
11 | 2025-09-20 18:35 | MR2509/0513 | Daily | 220KV_220KV DAMOH - DAMOH IC IIIRD CKT | 220KV_DAMOH | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered not in WR list
12 | 2025-09-24 14:19 | MR2509/0654 |  | 220KV_220 KV main Bus -l | 220KV_DATIA | NON-OCCM-MP | 160 mva-l Main bus isolator jaw hot point attend | 25-09-2025 10:00:00 | 25-09-2025 16:00:00 | Raksha Chaparia | 6265080313 | ok, through sub ld
13 | 2025-09-20 14:29 | MR2509/0504 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
14 | 2025-09-24 16:11 | MR2509/0662 |  | 132KV_132KV Anuppur-Dongrital ckt | 132KV_DONGRITAL | NON-OCCM-MP | disc replacement work | 25-09-2025 08:30:00 | 25-09-2025 17:00:00 | G.L SAHU | 9425805102 | ok
15 | 2025-09-23 11:51 | MR2509/0578 |  | 132KV_132 KV Guna - GAIL (Vijaipur) line | 220KV_GUNA | NON-OCCM-MP | Shifting work | 25-09-2025 09:00:00 | 25-09-2025 18:00:00 | Er. Sunny Kumar | 9425806888 | sub ld, before charging Metering, SCADA to be confirmed
16 | 2025-09-24 12:24 | MR2509/0635 |  | 132KV_63MVA Transformer Make BBL | 132KV_HATTA | NON-OCCM-MP | Post monsoon maintinance & Testing | 25-09-2025 11:00:00 | 25-09-2025 17:00:00 | B.K. Sahu | 9425805177 | ok
17 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
18 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
19 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
20 | 2025-09-22 12:42 | MR2509/0544 | Continuous | 400KV_315 MVA, 400/220 KV ICT-IV (Make-EMCO | 400KV_INDORE4 | NON-OCCM-MP | For post monsoon maintenance work. | 24-09-2025 09:00:00 | 25-09-2025 17:00:00 | Er.Atul Paradkar | 9425804929 | Continuous
21 | 2025-09-24 12:10 | MR2509/0633 |  | 132KV_132/33KV 50MVA X-MER | 220KV_ITARSI | NON-OCCM-MP | Post Monsoon maintanence & testing work | 25-09-2025 11:00:00 | 25-09-2025 17:00:00 | J.D.Khoria | 9425804975 | sub ld
22 | 2025-09-24 12:35 | MR2509/0636 |  | 132KV_132KV 63 MVA X-mer (EMCO) | 220KV_JULWANIYA | NON-OCCM-MP | Post monsoon maintenance work | 25-09-2025 10:00:00 | 25-09-2025 15:00:00 | SH. G.P. MISHRA Sir | 9425806931 | sub ld
23 | 2025-09-24 14:16 | MR2509/0653 |  | 132KV_20 MVA XMER NGEF 1 | 132KV_KATANGI | NON-OCCM-MP | Post Monsoon Maintenance Work | 25-09-2025 10:00:00 | 25-09-2025 17:00:00 | Seema Dongre | 9425807247 | ok
24 | 2025-09-23 11:02 | MR2509/0575 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-Ist | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 25-09-2025 08:00:00 | 26-09-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok
25 | 2025-09-24 14:40 | MR2509/0655 |  | 220KV_160MVA X-MER AREVA | 220KV_KOTAR | OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 25-09-2025 11:00:00 | 25-09-2025 17:00:00 | ARUN KUMAR KOL | 8319677721 | ok
26 | 2025-09-19 16:49 | MR2509/0491 |  | 220KV_132 kV Kotar â¿¿ Kaima (RTS) line | 220KV_KOTAR | NON-OCCM-MP | Line maintenance work | 25-09-2025 11:00:00 | 25-09-2025 14:30:00 | Mr. R.K. Prajapati | 9407007018 | ok
27 | 2025-09-24 12:06 | MR2509/0632 |  | 400KV_315MVA ICT-4 Transformer Make -TELK | 400KV_NAGDA4 | NON-OCCM-MP | Post monsoon maintenance and testing work | 25-09-2025 09:00:00 | 25-09-2025 18:00:00 | Sunil Bamniya | 9425820045 | ok, through sub ld, ICT-2 shall be in service
28 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
29 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
30 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
31 | 2025-09-24 15:55 | MR2509/0660 |  | 132KV_40MVA Xmer BHEL | 220KV_PANDHURNA | NON-OCCM-MP | Post mansoon maintenance | 25-09-2025 11:00:00 | 25-09-2025 17:00:00 | Sanjay shende | 9425811447 | ok
32 | 2025-09-09 17:04 | MR2509/0220 | Continuous | 132KV_PENCH-KANHAN_Ckt | 132KV_PENCH | NON-OCCM-WR | Overhauling of CB & replacement of Faulty CT | 25-09-2025 09:00:00 | 26-09-2025 16:00:00 | Arun Mungole | 8329756200 | Deffered not in WR list
33 | 2025-09-23 10:37 | MR2509/0573 |  | 220KV_Pithampur sec-3 to Rajgarh (PGCIL) ckt | 220KV_PITHAMPUR (SEC-III) | OCCM-MP | For Line maitenance work | 25-09-2025 10:00:00 | 25-09-2025 16:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
34 | 2025-09-23 10:42 | MR2509/0574 |  | 220KV_Pithampur Sec-3 to Dhar ckt | 220KV_PITHAMPUR (SEC-III) | OCCM-MP | for line maitenance work | 25-09-2025 10:00:00 | 25-09-2025 16:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
35 | 2025-09-24 16:10 | MR2509/0661 |  | 400KV_400kV Bustie & 400kV Main bus-I | 400KV_PITHAMPUR4 | NON-OCCM-MP | Main bus-I Isolator Alignment of 400kV PGCIL-I | 25-09-2025 10:00:00 | 25-09-2025 18:00:00 | Sh Rajudash bairagi | 9425801532 | Deffered due to 220KV_Pithampur Sec-3 to Dhar ckt and 220KV_Pithampur sec-3 to Rajgarh (PGCIL) ckt s/d
36 | 2025-09-24 16:13 | MR2509/0663 |  | 400KV_400kV PGCIL Ckt-I | 400KV_PITHAMPUR4 | NON-OCCM-MP | relay testing and bay maintenance work | 25-09-2025 11:00:00 | 25-09-2025 18:00:00 | Sh Rajudash bairagi | 9425801532 | Deffered not in WR list
37 | 2025-09-24 13:34 | MR2509/0644 |  | 132KV_50 MVA X-MER-I (BBL) | 220KV_RATLAM | NON-OCCM-MP | for Post Monsoon Maintenance And Testing work. | 25-09-2025 09:00:00 | 25-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
38 | 2025-09-24 11:12 | MR2509/0627 |  | 220KV_160 MVA x mer BHEL | 220KV_REWA | NON-OCCM-MP | Post monsoon maintenance, testing work | 25-09-2025 11:00:00 | 25-09-2025 18:00:00 | Kanishka singh | 9425804656 | real time as per load management
39 | 2025-09-20 18:32 | MR2509/0512 | Daily | 220KV_220KV DAMOH - SAGAR PGCIL IIND CKT. | 400KV_SAGAR | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered not in WR list
40 | 2025-09-24 15:03 | MR2509/0656 |  | 220KV_160 MVA X-mer -III CGL make | 220KV_SHUJALPUR | OCCM-MP | for Post monsoon maintenance & Testing w | 25-09-2025 09:00:00 | 25-09-2025 18:00:00 | nitin Verma | 9981559007 | ok, through sub ld
41 | 2025-09-24 12:52 | MR2509/0638 |  | 220KV_BHANPURA-SUWASRA2_Ckt | 220KV_SUWASRA2 | NON-OCCM-MP | PROVIDING M2 DPR RELAY | 25-09-2025 10:00:00 | 25-09-2025 17:00:00 | SUNIL PAWAR | 9425804939 | ok, through sub ld
42 | 2025-09-24 14:12 | MR2509/0651 |  | 220KV_220 KV Suwasara - Bhanpura line | 220KV_SUWASRA2 | OCCM-MP | Line Maintenance Work | 25-09-2025 10:00:00 | 25-09-2025 17:00:00 | Ravindra Kumar Marskole | 9425814080 | ok, as opportunity s/d
43 | 2025-09-24 13:55 | MR2509/0648 |  | 132KV_132 KV Udaipura-Tendukheda Line Ckt-I | 132KV_TENDUKHEDA | NON-OCCM-MP | Flashover disc replacement work at loc.No.48/R-01 | 25-09-2025 10:00:00 | 25-09-2025 18:00:00 | Ashish Kumar | 9425805935 | sub ld
44 | 2025-09-24 13:42 | MR2509/0645 |  | 132KV_132 kV Tikamgarh - Diguada Ckt. Ist Line | 220KV_TIKAMGARH | NON-OCCM-MP | Emergency T/C and other line maintenance work | 25-09-2025 10:00:00 | 25-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
45 | 2025-09-24 15:05 | MR2509/0657 |  | 220KV_160 MVA XMER BHEL | 220KV_UDAIPURA | NON-OCCM-MP | Post monsoon maintenance | 25-09-2025 10:00:00 | 25-09-2025 18:00:00 | Er. Pankaj Hariyale | 9827202680 | ok, through sub ld
46 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
47 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Completed
48 |  |  |  | 400KV-BHOPAL-MP-ITARSI-2 |  |  | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 25-Sep-2025 | 09:00 | 25-Sep-2025 | 18:00 | real time
49 |  |  |  | 400KV-SEONI-KIRNAPUR-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 25-Sep-2025 | 09:00 | 25-Sep-2025 | 18:00 | real time
50 |  |  |  | 220KV-KHANDWA-CHHEGAON-2 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 25-Sep-2025 | 08:00 | 25-Sep-2025 | 18:00 | real time
51 |  |  |  | 220KV-PITHAMPUR-RAJGARH-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 25-Sep-2025 | 08:00 | 25-Sep-2025 | 18:00 | ok, through sub ld
52 |  |  |  | 132KV-SHEOPUR-KHANDAR-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 25-Sep-2025 | 09:00 | 25-Sep-2025 | 17:00 | real time
53 |  |  |  | 400KV-DAMOH-BIRSINGPUR-1 |  |  | AMP Work of of Line terminal equipment and its BAY, Non auto mode of ckt 2 is required . Dia to be kept open at both ends. | 25-Sep-2025 | 08:00 | 25-Sep-2025 | 20:00 | ok
54 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 25-Sep-2025 | 07:00 | 25-Sep-2025 | 23:59 | ok
55 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  |  | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 25-Sep-2025 | 07:00 | 25-Sep-2025 | 19:59 | ok
S/I SLDC JABALPUR