## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-24
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-23 11:08 | MR2509/0577 |  | 132KV_63 MVA X-MER BBL | 132KV_ARON | NON-OCCM-MP | POST MANSOON MAINTENANCE | 24-09-2025 11:00:00 | 24-09-2025 17:00:00 | RAKESH SUMAN | 7587951093 | sub ld
2 | 2025-09-23 12:06 | MR2509/0579 |  | 400KV_315MVA X-mer No-2 CGL | 400KV_ASHTA4 | NON-OCCM-MP | Post- monsoon maintenance & measurement of tan del | 24-09-2025 08:00:00 | 24-09-2025 17:00:00 | Jitendra Lohana | 9425804978 | ok, through sub ld
3 | 2025-09-23 13:03 | MR2509/0585 |  | 132KV_50 MVA BBL | 132KV_BADAMALHERA | NON-OCCM-MP | for Post Monsoon Maint & Testing | 24-09-2025 09:00:00 | 24-09-2025 13:00:00 | Brajendra Soni | 9131327770 | ok
4 | 2025-09-23 13:05 | MR2509/0586 |  | 132KV_40 MVA BBL | 132KV_BADAMALHERA | NON-OCCM-MP | For Post Monsoon Maintenance & Testing | 24-09-2025 14:00:00 | 24-09-2025 18:00:00 | Brajendra Soni | 9131327770 | ok
5 | 2025-09-23 16:04 | MR2509/0612 |  | 220KV_220KV Badnawar-Ratlam Ckt-1st | 400KV_BADNAWAR | NON-OCCM-MP | Installation of Double DPR & Testing work | 24-09-2025 10:00:00 | 24-09-2025 17:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
6 | 2025-09-23 15:48 | MR2509/0611 |  | 220KV_220KV Barwaha Itarsi feeder | 220KV_BARWAHA | NON-OCCM-MP | Main-2 DPR Relay Testing & Commissioning work | 24-09-2025 09:00:00 | 24-09-2025 17:00:00 | Er.Imran Beg | 9425805200 | ok, through sub ld
7 | 2025-09-23 13:27 | MR2509/0588 |  | 132KV_132 kV Bhopal-Bairagarh Ckt II Tap to Lalghati line | 220KV_BHOPAL | NON-OCCM-MP | Emergency tree cutting work | 24-09-2025 11:00:00 | 24-09-2025 17:00:00 | Rahul Malviya | 9425804506 | sub ld
8 | 2025-09-23 15:09 | MR2509/0601 |  | 220KV_BUS NO. 1 | 220KV_BHOPAL | NON-OCCM-WR | stringing of overhead Conductor | 24-09-2025 09:00:00 | 24-09-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
9 | 2025-09-23 15:04 | MR2509/0599 |  | 220KV_160MVA X-Mer No 3 | 220KV_BHOPAL | NON-OCCM-WR | post monsoon maintenance | 24-09-2025 09:00:00 | 24-09-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
10 | 2025-09-23 15:14 | MR2509/0602 |  | 315MVA_400/220KV_CGL_X'mer_3 | 400KV_BINA4 | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 24-09-2025 09:00:00 | 24-09-2025 18:00:00 | Er. Parmanand namdeo | 7587951092 | ok, through sub ld
11 | 2025-09-20 14:29 | MR2509/0503 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
12 | 2025-09-23 12:58 | MR2509/0584 |  | 132KV_132 kV Pandhurna-Borgaon | 132KV_BOREGAON | NON-OCCM-MP | F/o disc replaced and bird guard provide | 24-09-2025 10:00:00 | 24-09-2025 18:00:00 | A.M.Shende | 7587951136 | ok
13 | 2025-09-23 15:25 | MR2509/0603 |  | 220KV_160 MVA BBL NO. 2nd | 220KV_CHAPDA | NON-OCCM-WR | post mosoon maint. | 24-09-2025 08:00:00 | 24-09-2025 17:00:00 | Er. s. k. sharma | 9424027597 | ok, through sub ld
14 | 2025-09-23 14:26 | MR2509/0595 |  | 132KV_132 kV Chhatarpur â¿¿ Bijawar ckt. 1st Tap Nowgaon Line | 220KV_CHATARPUR | NON-OCCM-MP | AH, VD Tightening & other line maintenance work | 24-09-2025 10:00:00 | 24-09-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
15 | 2025-09-22 10:57 | MR2509/0534 | Daily | 315MVA_400/220KV_CGL_X'mer_1 | 400KV_CHHEGAON4 | NON-OCCM-MP | POST MANSOON MAINT. WORK | 23-09-2025 10:00:00 | 24-09-2025 18:00:00 | SHRI GANESH MANSARE | 9425802441 | ok, through sub ld
16 | 2025-09-20 18:35 | MR2509/0513 | Daily | 220KV_220KV DAMOH - DAMOH IC IIIRD CKT | 220KV_DAMOH | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered, not in WR list
17 | 2025-09-22 11:51 | MR2509/0540 |  | 220KV_Dhar to Rajgarh (PGCIL) circuit | 220KV_DHAR | OCCM-MP | for line maintenance work | 24-09-2025 10:00:00 | 24-09-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
18 | 2025-09-20 14:29 | MR2509/0504 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 21-09-2025 09:00:00 | 27-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
19 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
20 | 2025-09-23 15:36 | MR2509/0610 |  | 220KV_160 MVA TRANSFORMER -II MAKE BHEL | 220KV_INDORE-II (JETPURA) | NON-OCCM-WR | POST MONSOON MAINTENANCE & TESTING WORK | 24-09-2025 10:00:00 | 24-09-2025 17:00:00 | DEEPAK GUPTA | 9425803845 | ok, through sub ld
21 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
22 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
23 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | RESCHEDULED FRO 11.09.2025 TO 30.09.2025
24 | 2025-09-22 12:42 | MR2509/0544 | Continuous | 400KV_315 MVA, 400/220 KV ICT-IV (Make-EMCO | 400KV_INDORE4 | NON-OCCM-MP | For post monsoon maintenance work. | 24-09-2025 09:00:00 | 25-09-2025 17:00:00 | Er.Atul Paradkar | 9425804929 | ok, through sub ld, after normalisation of ICT 2
25 | 2025-09-23 13:53 | MR2509/0591 |  | 220KV_220KV 160MVA X-MER No.-01 | 220KV_ITARSI | NON-OCCM-MP | Post Monsoon maintanence & testing work | 24-09-2025 09:00:00 | 24-09-2025 17:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
26 | 2025-09-23 13:45 | MR2509/0590 |  | 132KV_50MVA X-MER(BBL) | 132KV_KHIMLASA | NON-OCCM-MP | Post Monsoon Maintenance Work | 24-09-2025 09:00:00 | 24-09-2025 17:00:00 | Mr. P.N.Namdeo | 7587951092 | ok, o&m shall be informed
27 | 2025-09-23 14:12 | MR2509/0593 |  | 132KV_40MVA BBL Transfomer No. 2 | 132KV_LAKHNADONE | NON-OCCM-MP | Post Mansoon Maintenance Work | 24-09-2025 10:00:00 | 24-09-2025 17:00:00 | SEEMA DONGRE | 9425807247 | ok
28 | 2025-09-23 13:10 | MR2509/0587 |  | 400KV_315 MVA Transformer-II make CGL | 400KV_MANDSOUR4 | OCCM-MP | Post Monsoon Maintenance & Testing Work | 24-09-2025 08:00:00 | 24-09-2025 18:00:00 | C P Dhakad | 7587951067 | ok, through sub ld
29 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
30 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
31 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | sub ld
32 | 2025-09-23 12:25 | MR2509/0580 |  | 132KV_BBL X-MER-1 | 132KV_PAWAI | NON-OCCM-MP | Post mansoon maintenance | 24-09-2025 11:00:00 | 24-09-2025 17:00:00 | RN UPADHYAY | 9425802349 | o&m consent required
33 | 2025-09-23 16:10 | MR2509/0621 |  | 220KV_160 MVA X-MER BBL II | 220KV_PITHAMPUR-II (SEC-I) | NON-OCCM-WR | POST MANSOON MAINTENCE | 24-09-2025 10:00:00 | 24-09-2025 17:00:00 | RAJUDASH BAIRAGI | 9425801532 | ok, through sub ld
34 | 2025-09-23 16:23 | MR2509/0622 |  | 400KV_400kV Main bus-II | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tightening, Greasing,cleaning & Isolator alignment | 24-09-2025 10:00:00 | 24-09-2025 18:00:00 | Sh. Rajudash bairagi | 9425801532 | ok, through sub ld
35 | 2025-09-23 14:18 | MR2509/0594 |  | 132KV_132KV Rajmilan-Janakpur ckt | 132KV_RAJMILAN | NON-OCCM-MP | disc replacement work | 24-09-2025 08:30:00 | 24-09-2025 17:00:00 | G.L SAHU | 9425805102 | ok
36 | 2025-09-23 14:56 | MR2509/0598 |  | 132KV_63 MVA X-MER-III (BBL) | 220KV_RATLAM | NON-OCCM-MP | for Post Monsoon Maintenance & Testing work. | 24-09-2025 09:00:00 | 24-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
37 | 2025-09-23 15:32 | MR2509/0609 |  | 220KV_220 kv 160 mva BHEL Xmer | 220KV_REWA | NON-OCCM-MP | post monsoon maintenance & testing work | 24-09-2025 11:00:00 | 24-09-2025 18:00:00 | Kanishka Singh | 9425804656 | real time
38 | 2025-09-20 18:32 | MR2509/0512 | Daily | 220KV_220KV DAMOH - SAGAR PGCIL IIND CKT. | 400KV_SAGAR | OCCM-MP | FOR OPGW INSTALLATION WORK | 23-09-2025 07:00:00 | 30-09-2025 19:00:00 | M.M. BAIG | 9425805067 | Deffered, not in WR list
39 | 2025-09-23 14:46 | MR2509/0597 |  | 132KV_63 MVA Z-MAR EMCO | 132KV_SAGAR1 | NON-OCCM-MP | POST MANSOON MAINTINANCE | 24-09-2025 09:30:00 | 24-09-2025 17:00:00 | S K HAJARI | 9425620010 | ok
40 | 2025-09-22 11:26 | MR2509/0536 |  | 220KV_220 kv Satna (MPPTCL) â¿¿ Ajaygarh line. | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | 24-09-2025 11:00:00 | 24-09-2025 17:00:00 | Mr R.K. Prajapati | 9407070182 | real time
41 | 2025-09-23 14:05 | MR2509/0592 |  | 220KV_160 MVA X-MER 2nd | 220KV_SHIVPURI | NON-OCCM-MP | AIR CELL Commissioning and relay testing work. | 24-09-2025 11:00:00 | 24-09-2025 17:00:00 | AE. Rohit Yadav | 8120064160 | ok, through sub ld
42 | 2025-09-23 12:29 | MR2509/0581 |  | 220KV_160 MVA X-mer -II BHEL Make | 220KV_SHUJALPUR | OCCM-MP | postmonsoon maintenance & Testing work | 24-09-2025 09:00:00 | 24-09-2025 18:00:00 | Bhupendra Rane | 9406551225 | ok, through sub ld
43 | 2025-09-23 14:41 | MR2509/0596 |  | 132KV_132KV Sidhi-Deosar ckt-II | 220KV_SIDHI | NON-OCCM-MP | Flash over disc replaement | 24-09-2025 10:00:00 | 24-09-2025 17:00:00 | G.L SAHU | 9425805102 | ok
44 | 2025-09-23 12:48 | MR2509/0583 |  | 220KV_160MVA XMER | 220KV_UDAIPURA | NON-OCCM-MP | Post monsoon maintenance work | 24-09-2025 10:00:00 | 24-09-2025 18:00:00 | Er. Pankaj Hariyale | 9827202680 | ok, through sub ld
45 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | CONTINUE
46 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | completed
47 |  |  |  | 160 MVA ICT 2 AT BEGUMGANJ SS | 220 KV /132 KV /33 KV BEGUMGANJ S/S |  | OIL LEAKAGE ATTENDING WORK IN 33 KV R PHASE TARTIARY BUSHING | 15:00 | 17:00 |  |  | SHALL BE GIVEN AFTER NORMALISTION UDAIPUR XMAR SS
48 |  | 261279 |  | 400KV-BALCO (MRSDS)-BIRSINGPUR-1 | 400 | POWERGRID_WR2 | AMP Work of of Line terminal equipment & Associated LR and its BAY, Non auto mode of ckt 1 is required . Dia to be kept open at both ends. | 24-Sep-2025 | 08:00 | 24-Sep-2025 | 20:00
49 |  | 260608 |  | 220KV-GWALIOR-MALANPUR-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Sep-2025 | 09:00 | 24-Sep-2025 | 17:00 | real time
50 |  | 260609 |  | 220KV-SEONI-PG-CHINDWARA-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Sep-2025 | 09:00 | 24-Sep-2025 | 18:00 | real time
51 |  | 260610 |  | 220KV-RAJGARH-DHAR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Sep-2025 | 08:00 | 24-Sep-2025 | 18:00 | ok, through sub ld
52 |  | 260611 |  | 220KV-REWA-SINDHI-MP-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 24-Sep-2025 | 10:00 | 24-Sep-2025 | 17:00 | real time
53 |  | 266099 |  | 400KV-INDORE-PITHAMPUR-2 | 400 | MP_SLDC | Tan-Delta testing and bay maintenance work | 24-Sep-2025 | 08:00 | 24-Sep-2025 | 18:59 | real time
54 |  | 265834 |  | 220KV-INDORE-INDORE NORTH ZONE-1 | 220 | MP_SLDC | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 24-Sep-2025 | 07:00 | 24-Sep-2025 | 23:59 | ok
55 |  | 265854 |  | 220KV-INDORE-INDORE NORTH ZONE-2 | 220 | MP_SLDC | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 24-Sep-2025 | 07:00 | 24-Sep-2025 | 19:59 | ok
56
57