## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-12
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-05 11:27 | MR2506/0089 | Daily | 132KV_132 kV Seoni-Amarwara | 132KV_AMARWARA | NON-OCCM-MP | PID defective disc insulator replacement | 06-06-2025 08:00:00 | 15-06-2025 18:00:00 | A.M.Shende | 7587951136 | Deffered due to s/d on 160MVA x-merat Chhindwara
2 | 2025-06-11 12:52 | MR2506/0238 |  | 220KV_160 MVA X- MER BBL | 220KV_ASHOKNAGAR | NON-OCCM-MP | NEUTRAL COPPER STRIP REPLACE | 12-06-2025 11:00:00 | 12-06-2025 16:00:00 | RAKESH SUMAN | 9713958042 | ok, through sub ld
3 | 2025-06-11 11:33 | MR2506/0233 |  | 400KV_400/220/33KV 315MVA BHEL Transformer | 400KV_BADNAWAR | NON-OCCM-MP | Pre monsoon maintanance & testing work | 12-06-2025 09:00:00 | 12-06-2025 18:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
4 | 2025-06-11 11:27 | MR2506/0232 |  | 132KV_132kV Baihar-Birsa Line | 132KV_BAIHAR | NON-OCCM-MP | Work for Replacement of PID Defective Disc & TC | 12-06-2025 10:00:00 | 12-06-2025 14:00:00 | S.K. BHALADHARE | 9425807264 | ok
5 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
6 | 2025-06-11 13:15 | MR2506/0241 |  | 220KV_220 KV Bina-Sagar Ckt-1 | 400KV_BINA4 | NON-OCCM-MP | For line maintenance work | 12-06-2025 09:00:00 | 12-06-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Deffered due to s/d on 400KV-SAGAR-SATNA ckt
7 | 2025-06-11 13:42 | MR2506/0242 |  | 220KV_220 kV Bina-I/C III line | 400KV_BINA4 | NON-OCCM-MP | Premon-soon maintenance and TCH relay replacement | 12-06-2025 09:00:00 | 12-06-2025 18:00:00 | Er. Parmanand Namdeo | 7587351092 | ok, through sub ld
8 | 2025-06-11 13:15 | MR2506/0239 |  | 220KV_220 KV BUDHNI PGCIL(ITARSI) 1ST CKT | 220KV_BUDHNI | NON-OCCM-WR | COMMISNING & MAINTENANCE WORK DTPC | 12-06-2025 11:00:00 | 12-06-2025 17:00:00 | S.P.S TOMAR SIR | 9425801629 | Deffered, not approved by WRPC
9 | 2025-06-11 15:01 | MR2506/0248 |  | 400KV_400Kv Chhegaon-Julwaniya Ckt-I | 400KV_CHHEGAON4 | NON-OCCM-MP | For Auto Reclose Feature Relay Testing work | 12-06-2025 10:00:00 | 12-06-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | ok, through sub ld
10 | 2025-06-11 15:21 | MR2506/0250 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 220KV_CHHINDWARA | NON-OCCM-MP | 132KV INCOMER Y PHASE CT REPLACEMENT WORK. | 12-06-2025 09:00:00 | 12-06-2025 18:00:00 | A A QURESHI | 9425804318 | real time
11 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | sub ld
12 | 2025-06-11 15:13 | MR2506/0249 |  | 132KV_132 kV Shahdol-Dindori Circuit I | 132KV_DINDORI | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 12-06-2025 10:00:00 | 12-06-2025 17:00:00 | Jitendra Tiwari | 9425805298 | Deffered due to s/d on Kirnapur ICT
13 | 2025-06-11 14:30 | MR2506/0246 |  | 220KV_160MVAX-MER -1 MAKE ALSTOM | 220KV_GANJBASODA | NON-OCCM-MP | LBB REALY TEASTING WORK | 12-06-2025 11:00:00 | 12-06-2025 16:00:00 | P VERMA | 8253003873 | ok, through sub ld
14 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
15 | 2025-06-02 17:12 | MR2506/0039 | Continuous | 400KV_U#03 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE OF SAID UNIT | 03-06-2025 06:00:00 | 15-06-2025 18:00:00 | SHRI VINAI MISHRA | 9575074321 | as per system requirement
16 | 2025-06-07 15:56 | MR2506/0146 | Daily | 220KV_220 kv NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 09-06-2025 07:00:00 | 18-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered, not approved by WRPC
17 | 2025-06-07 16:07 | MR2506/0147 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 09-06-2025 07:00:00 | 18-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered, not approved by WRPC
18 | 2025-06-05 18:29 | MR2506/0120 | Daily | 220KV_220KV North Zone â¿¿ Hatuniya (PGCIL) Ckt.-1 & 2 Line | 220KV_INDORE-NZ | NON-OCCM-MP | E/W replacement work by 24 Fibre OPGW Wire | 06-06-2025 07:00:00 | 15-06-2025 19:00:00 | A.R.KANEL | 9425805217 | Deffered, not approved by WRPC
19 | 2025-05-31 14:48 | MR2505/0647 | Daily | 220KV_220 Southzone - Jaitpura | 220KV_INDORE-SZ | NON-OCCM-MP | Hotline Work permit (PTW) | 01-06-2025 07:00:00 | 15-06-2025 19:00:00 | A.R. KANEL | 9525805217 | ok, line to be in service
20 | 2025-05-31 14:15 | MR2505/0645 | Daily | 220KV_(20KV INDORE (400KV) - MAGLIYA LINE | 400KV_INDORE4 | NON-OCCM-MP | Hotline work permit (PTW) | 01-06-2025 07:00:00 | 15-06-2025 19:00:00 | A.R. KANEL | 9525805217 | ok, line to be in service
21 | 2025-05-23 18:38 | MR2505/0487 | Continuous | 220KV_NARSINGHPUR-JABALPUR_Ckt_2 | 220KV_JABALPUR | NON-OCCM-MP | BUNCHING OF 132KV JBP SHAHPURA WITH220 KV JBP NSP | 26-05-2025 09:00:00 | 20-06-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Deffered by site
22 | 2025-06-11 14:01 | MR2506/0244 |  | 400KV_500 MVA Transformer | 400KV_JULWANIYA4 | NON-OCCM-MP | Relay replacement | 12-06-2025 12:00:00 | 12-06-2025 14:00:00 | M. K. More | 8817566466 | ok, through sub ld
23 | 2025-04-12 15:54 | MR2504/0337 | Continuous | 400KV_400KV KATNI DAMOH | 400KV_KATNI4 | NON-OCCM-MP | For Strenghtening Continues work . | 09-06-2025 09:00:00 | 14-06-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
24 | 2025-04-12 16:01 | MR2504/0338 | Continuous | 220KV_220KV KATNI DAMOH | 400KV_KATNI4 | NON-OCCM-MP | For Strenghtening Continues work . | 09-06-2025 09:00:00 | 14-06-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
25 | 2025-06-11 15:25 | MR2506/0254 |  | 400KV_125MVAR BUS Reactor | 400KV_KATNI4 | NON-OCCM-MP | For Pre-Monsoon Maintenance work | 12-06-2025 10:00:00 | 12-06-2025 17:00:00 | SK chaturvedi | 9425806938 | ok
26 | 2025-06-11 15:25 | MR2506/0253 |  | 400KV_400/132/33 KV 100 MVA X-MER No-01 BHEL | 400KV_KIRNAPUR | NON-OCCM-MP | For OLTC Oil filtration and Pre-monsoon maint. | 12-06-2025 07:00:00 | 12-06-2025 20:00:00 | D. S. Walkey | 9425804578 | ok, s/d to be completed on time
27 | 2025-06-10 10:24 | MR2506/0200 | Continuous | 132KV_132KV RCN Kothiya LIne | 132KV_KOTHIYA | NON-OCCM-MP | Testing of line CT/ PT, SF6 breaker maint. work | 11-06-2025 19:00:00 | 12-06-2025 05:00:00 | Anup Kumar Dange | 9425814073 | sub ld
28 | 2025-06-10 15:58 | MR2506/0223 |  | 132KV_132/33 KV 50 MVA TAL X-MER | 132KV_MADWAS | OCCM-MP | High Tan-Delta HV Neutral Bushing Replacement Work | 12-06-2025 08:00:00 | 12-06-2025 18:00:00 | SHRI V. K. PANIKA | 9425804643 | ok
29 | 2025-06-06 12:14 | MR2506/0124 | Continuous | 132KV_20 MVA GEC X-MER | 132KV_MANERI | NON-OCCM-MP | Attending of heavy oil leakage of bushing & OLTC | 09-06-2025 09:00:00 | 13-06-2025 18:00:00 | S.K.JAIN | 9425801623 | Continuous
30 | 2025-06-11 14:12 | MR2506/0245 |  | 220KV_Nagda-Nagra ckt-2 | 400KV_NAGDA4 | NON-OCCM-MP | 3 nos LA replacement work. | 12-06-2025 10:00:00 | 12-06-2025 17:00:00 | Sunil Bamniya | 9425820045 | ok, through sub ld
31 | 2025-06-11 16:02 | MR2506/0257 |  | 220KV_220KV Narsinghpur -Sukha ckt-II | 220KV_NARSINGHPUR | NON-OCCM-MP | Hot point attending work of Y-phase CT Dro. jumper | 12-06-2025 14:00:00 | 12-06-2025 18:00:00 | Dinesh Kumar Kushwaha | 9425182413 | ok
32 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per system requirement
33 | 2025-06-11 12:30 | MR2506/0235 |  | 160MVA_220/132KV_BHEL_X'mer_3 | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | For TCH Relay Replacement Work | 12-06-2025 09:00:00 | 12-06-2025 17:00:00 | sh. Rajudas Bairagi | 9425801532 | real time
34 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered by site
35 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered by site
36 | 2025-06-09 16:09 | MR2506/0189 |  | 400KV_400KV Rajgarh PG -SSP Ckt-2 | 400KV_RAJGARH-PG | OCCM-WR | line maintinance work | 12-06-2025 08:00:00 | 12-06-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
37 | 2025-06-11 12:16 | MR2506/0234 |  | 400KV_400kv Sagar-Satna Lilo Line (PGCIL) | 400KV_SAGAR | OCCM-MP | Line Maintenance work | 12-06-2025 09:00:00 | 12-06-2025 18:00:00 | J.P. Asati | 9424445533 | ok
38 | 2025-06-11 14:54 | MR2506/0247 |  | 132KV_50 MVA BBL XMER | 132KV_SAGAR1 | NON-OCCM-MP | HV AND LV NEUTRAL COPPER STRIP REPLACEMENT | 12-06-2025 08:00:00 | 12-06-2025 12:00:00 | SRAJAN SISODIYA | 9425804341 | ok
39 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
40 | 2025-06-09 17:01 | MR2506/0198 |  | 132KV_132kV Seoni Nainpur SC | 132KV_SEONI1 | NON-OCCM-MP | Work for tightening J/C, A/H, V/D | 12-06-2025 09:00:00 | 12-06-2025 18:00:00 | S.K. Nadekar | 9425806848 | Deffered due to s/d on Kirnapur ICT
41 | 2025-06-11 12:46 | MR2506/0236 |  | 220KV_BHOPAL-I | 220KV_SHUJALPUR | OCCM-MP | 220 KV CT & CVT tan delta testing work | 12-06-2025 08:00:00 | 12-06-2025 12:00:00 | Nitin Verma | 9981559007 | ok, through sub ld
42 | 2025-06-11 12:50 | MR2506/0237 |  | 220KV_BHOPAL-II nd | 220KV_SHUJALPUR | OCCM-MP | 220 KV CT & CVT tan delta testing work | 12-06-2025 13:00:00 | 12-06-2025 17:00:00 | Nitin verma | 9981559007 | ok, through sub ld
43 | 2025-06-11 16:42 | MR2506/0259 | Continuous | 220KV_220 KV Jabalpur no -1 DPR RELAY testing &other related work | 220KV_SUKHA | NON-OCCM-MP | 220 kv jabalpur no.1 DPR RELAY TESTING &OTHER WORK | 12-06-2025 00:00:00 | 13-06-2025 00:00:00 | Ashish sonkeshariya | 7587951153 | ok, line to be in service through TBC
44 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
45 | 2025-04-17 17:34 | MR2504/0479 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
46 |  | 249964 |  | 400KV-SAGAR-SATNA-1 | 400 | MP_SLDC | FOR LINE MAINTENANCE WORK | 12-Jun-2025 | 09:00 | 12-Jun-2025 | 18:00 | ok
47 |  | 249965 |  | 400KV-SSP-RAJGARH-2 | 400 | MP_SLDC | FOR LINE MAINTENANCE WORK | 12-Jun-2025 | 08:00 | 12-Jun-2025 | 18:00 | ok
48 |  | 249991 |  | 220KV-HOSHANGABAD-ITARSI-2 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT 220KV S/S HOSHANGABAD | 12-Jun-2025 | 10:00 | 12-Jun-2025 | 18:00 | real time
49
50
51
52
53
54
55
56
57