## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-26 |  |  | APPROVED OUTAGE LIST FOR DTD 26.06.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-16 18:55 | MR2506/0355 | Daily | 220KV_220 KV BAIRAGARH MUGALIYACHAP LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE-3 | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-23 09:45 | MR2506/0456 | Daily | 220KV_220 kv Bairagarh Ashta | 220KV_BAIRAGARH | NON-OCCM-MP | OPGW MAINTENANCE WORK | 23-06-2025 09:00:00 | 30-06-2025 09:00:00 | Nitin Reshwal | 9425804890 | ok, line to be in service
4 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
5 | 2025-06-22 12:03 | MR2506/0444 | Continuous | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | X-mer shifting from existing location to Wooden sl | 23-06-2025 10:00:00 | 27-06-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
6 | 2025-06-23 19:11 | MR2506/0485 |  | 400KV_400 KV BHOPAL-ITARSI CKT NO-1 | 400KV_BHOPAL4 | NON-OCCM-MP | Tan Delta & Capacitance Measurement & DPR Relay Te | 26-06-2025 10:00:00 | 26-06-2025 18:00:00 | AKRAM KHAN | 9425804695 | Deferred, not in WR list
7 | 2025-06-25 14:40 | MR2506/0534 |  | 132KV_CHHINDWARA-BICHHUA_Ckt | 132KV_BICHHUA | NON-OCCM-MP | B PHASE CT OIL LEAKAGE ATTEND WORK. | 26-06-2025 12:00:00 | 26-06-2025 14:00:00 | A A QURESHI | 9425804318 | ok
8 | 2025-06-23 09:15 | MR2506/0455 | Continuous | 220KV_220 KV BUSCOUPLER & 220 MAIN BUS -2 | 400KV_BINA4 | NON-OCCM-MP | FOR ERECTION OF STRUCTURE AND STRINGING | 24-06-2025 10:00:00 | 27-06-2025 17:00:00 | ANIL MAHOR | 9425805149 | Continuous
9 | 2025-06-25 15:52 | MR2506/0539 |  | 132KV_132 kV Hatta - Bijawar Line | 220KV_CHATARPUR | NON-OCCM-MP | Flash Over disc replacement and other line maint. | 26-06-2025 11:00:00 | 26-06-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
10 | 2025-06-25 16:23 | MR2506/0545 |  | 400KV_400Kv Main Bus-I | 400KV_CHHEGAON4 | NON-OCCM-MP | 400Kv Bus-Tie R Phase Hot Point Attending Work | 26-06-2025 10:00:00 | 26-06-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | WRLDC approval required for emeregncy outage
11 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
12 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
13 | 2025-06-17 21:54 | MR2506/0387 | Continuous | 400KV_UNIT - 7 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-06-2025 06:00:00 | 30-06-2025 18:00:00 | Vinay Mishra | 9575074321 | as per system requirement
14 | 2025-06-20 19:03 | MR2506/0431 | Continuous | 400KV_400 KV BUS 2 | 400KV_INDIRASAGAR | NON-OCCM-MP | SF 6 CB maintenance work | 24-06-2025 10:00:00 | 28-06-2025 17:00:00 | SANJAY PATEL | 9424050443 | Continuous
15 | 2025-06-17 18:03 | MR2506/0376 | Daily | 220KV_NORTHZONE - HATUNIYA (PGCIL) CKT -2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
16 | 2025-06-17 18:15 | MR2506/0379 | Daily | 132KV_NIRANJANPUR - JETPURA LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | sub ld
17 | 2025-06-17 18:13 | MR2506/0378 | Daily | 132KV_NORTHZONE - NIRANJANPUR LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | sub ld
18 | 2025-06-17 18:00 | MR2506/0375 | Daily | 220KV_NORTHZONE - HATUNIYA (PGCIL) CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
19 | 2025-06-17 18:05 | MR2506/0377 | Daily | 132KV_NORTHZONE - JETPURA LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | sub ld
20 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
21 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
22 | 2025-06-24 11:48 | MR2506/0489 | Daily | 220KV_220 KV SARNI-ITARSI III LINE | 220KV_ITARSI | NON-OCCM-MP | Resagging work b/w loc.no. 199-218 | 25-06-2025 09:00:00 | 27-06-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
23 | 2025-06-25 14:42 | MR2506/0535 |  | 400KV_400kV Main Bus-I & 500MVA X-mer-III T&R | 400KV_JULWANIYA4 | NON-OCCM-MP | Pentograph Isolator alignment work,CSD relay test | 26-06-2025 09:00:00 | 26-06-2025 18:00:00 | Er. Manoj More | 8817566466 | ok, through sub ld
24 | 2025-06-24 17:43 | MR2506/0523 | Daily | 400KV_500MVA X-mer (T&R) | 400KV_JULWANIYA4 | NON-OCCM-MP | CSD Relay Commissioning work | 25-06-2025 09:00:00 | 26-06-2025 17:00:00 | Er. Ravindra Patil | 8305612190 | ok, through sub ld
25 | 2025-06-25 16:16 | MR2506/0544 |  | 220KV_220KV Kanwan-Dhar 1st | 220KV_KANWAN2 | NON-OCCM-MP | For DTPC commissioning Work | 26-06-2025 12:00:00 | 26-06-2025 17:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
26 | 2025-06-25 16:29 | MR2506/0546 |  | 132KV_132 KV KATNI PANAGAR LINE | 132KV_KATNI | NON-OCCM-MP | Replacment for fo disc. | 26-06-2025 10:00:00 | 26-06-2025 17:00:00 | Pankaj yadav | 9406713326 | ok
27 | 2024-11-20 16:32 | MR2411/0430 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | real time
28 | 2024-11-20 16:36 | MR2411/0431 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | real time
29 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | Communication consent required for data outage
30 | 2025-06-20 11:59 | MR2506/0420 | Daily | 220KV_220 KV BHOPAL MUGALIYACHAAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | OPGW MAINTENANCE WORK | 21-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
31 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deferred
32 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deferred
33 | 2025-06-25 12:26 | MR2506/0531 |  | 220KV_220KV Bus-Coupler | 220KV_RATANGARH | NON-OCCM-WR | Pre-monsoon maintenance work | 26-06-2025 11:00:00 | 26-06-2025 15:00:00 | S.H. Mansuri | 7587951068 | ok, through sub ld, no element shall be on bus coupler during s/d
34 | 2025-06-25 13:37 | MR2506/0532 |  | 220KV_220/132/33 kv, 160 MVA X-MER-III rd (BHEL) | 220KV_RATLAM | NON-OCCM-MP | for ten delta measurment work | 26-06-2025 09:00:00 | 26-06-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
35 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
36 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
37 | 2025-06-25 11:52 | MR2506/0530 |  | 220KV_220KV Damoh-Sagar 2nd Ckt. LIne (PGCIL) | 400KV_SAGAR | OCCM-MP | Line Maintenance work | 26-06-2025 09:00:00 | 26-06-2025 18:00:00 | J.P. Asati | 9424445533 | ok
38 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
39 | 2025-05-21 18:42 | MR2505/0455 |  | 400KV_400KV/220KV/33KV ICT BAY | 400KV_SATPURA TPS | NON-OCCM-MP | Work of routine testing general checking & mainten | 26-06-2025 09:00:00 | 26-06-2025 18:00:00 | S.S. THAKUR | 9425611244 | ok
40 | 2025-06-25 14:05 | MR2506/0533 |  | 132KV_132kV Seoni Katangi Feeder | 132KV_SEONI1 | NON-OCCM-MP | Replacement of flashover disc insulator | 26-06-2025 10:00:00 | 26-06-2025 17:00:00 | S.K. Nadekar | 9425806848 | real time
41 | 2025-06-20 12:24 | MR2506/0422 | Continuous | 220KV_Bay no 21 tie cum bus coupler breaker | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 kv circuit breaker | 23-06-2025 08:00:00 | 26-06-2025 16:00:00 | S Banerjee | 9424352880 | Continuous
42 | 2025-06-25 15:54 | MR2506/0540 |  | 220KV_220KV SIDHI-REWA CKT | 220KV_SIDHI | NON-OCCM-MP | Flash over disc replacement | 26-06-2025 10:00:00 | 26-06-2025 13:00:00 | G.L SAHU | 9425805102 | ok
43 | 2025-06-25 15:57 | MR2506/0541 |  | 220KV_220KV SIDHI-ATPS | 220KV_SIDHI | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 26-06-2025 14:00:00 | 26-06-2025 17:00:00 | G.L SAHU | 9425805102 | ok
44 | 2025-06-22 13:36 | MR2506/0448 | Continuous | 132KV_132KV SIDHI-MAUGANJ CKT-1&2 | 220KV_SIDHI | NON-OCCM-MP | TOWER MODIFICATION &SHIFTING WORK | 23-06-2025 08:00:00 | 26-06-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
45 | 2025-06-25 15:06 | MR2506/0537 |  | 132KV_132 KV Sironj-Lateri Ckt. | 132KV_SIRONJ | NON-OCCM-MP | Hot line work permit for F/o replacement | 26-06-2025 12:00:00 | 26-06-2025 14:00:00 | Sanjay Singh Thakur | 9425806936 | sub ld
46 | 2025-06-17 17:47 | MR2506/0373 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
47 | 2025-06-17 17:49 | MR2506/0374 | Daily | 132KV_132 kV Tikamgarh IC 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
48 |  |  |  | 220KV-DAMOH-SAGAR-2 |  | MADHYA PRADESH | FOR LINE MAINTENANCE WORK | 09:00 | 2025-06-26 18:00 | ckt-1 to be in service. No other element shall be effected. Wr2 to be informed. Load to be managed by SLDC MP |  | ok
49 |  |  |  | 220KV-PANDURNA-KALMESHWAR-1 |  | MADHYA PRADESH,MAHARASHTRA | FOR LINE MAINTENANCE WORK | 09:00 | 2025-06-26 18:00 | All other lines at Pandurna/Kalmeshwar to be in service with AR enabled. SLDC MH to be informed. Load to be managed by SLDC MP/MH. |  | real time
50 |  |  |  | 400KV-DAMOH-KATNI-1 |  | MADHYA PRADESH,MAHARASHTRA | TOWER STRENGTHENING WORK | 09:00 | 2025-06-26 18:00 | "All other lines at Damoh/Katni to be in service with AR enabled. No other element shall be effected. care to be taken. WR2 to be informed " |  | real time
51 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 |  | 132KV-DHARNI-NEPANAGAR-1 | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 8:00 | 2025-06-26 17:59 | A/R in NA, Line to be in service |  | OK
52 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  | MADHYA PRADESH | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 07:00 | 2025-06-26 18:59 | A/R in NA, Line to be in service |  | OK
53 |  |  |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  | MADHYA PRADESH | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 07:00 | 2025-06-26 18:59 | A/R in NA, Line to be in service |  | OK
S/I, SLDC, MPPTCL