## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-16 |  |  | 2025-06-16
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-11 15:27 | MR2506/0255 |  | 220KV_220 kV Anuppur-Kotmikala Circuit II | 220KV_ANUPPUR | NON-OCCM-MP | For low ground Clearance maintenance between Span | 16-06-2025 08:00:00 | 16-06-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ckt 1 is approved in WR list
2 | 2025-06-12 11:11 | MR2506/0261 | Daily | 400KV_400 KV ASHTA UJJAIN LINE 1, 2 | 400KV_ASHTA4 | NON-OCCM-MP | LIVE LINE PERMIT FOR FIBER MAINTENANCE SPLICING | 12-06-2025 09:00:00 | 20-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
4 | 2025-06-15 14:10 | MR2506/0321 |  | 132KV_HALF MAIN BUS TOWARDS 160 MVA BHEL XMER SIDE | 220KV_BINA | NON-OCCM-MP | Y PHASE TWIN ZEBRA CONDUCTOR RPELACMENT | 16-06-2025 09:00:00 | 16-06-2025 17:00:00 | ER LALIT SINGH | 9425806845 | ok,through sub ld, after load management
5 | 2025-06-12 09:07 | MR2506/0260 | Daily | 220KV_220 KV Bina- Pichhore & 220 KV Bina- Datia Ckt | 400KV_BINA4 | NON-OCCM-MP | Hot line PTW for OPGW work By M/s ZTT | 12-06-2025 07:00:00 | 18-06-2025 19:00:00 | Satish Kumar Bhagat & Sanjay Singh Thakur | 9425806916 | ok, line to be in service
6 | 2025-06-15 16:10 | MR2506/0328 |  | 132KV_132KV BICHHUA FEEDER | 220KV_CHHINDWARA | NON-OCCM-MP | F/O DISCK REPLACEMENT LOC.04 | 16-06-2025 10:00:00 | 16-06-2025 14:00:00 | AM SHENDE | 7587951136 | ok
7 | 2025-06-15 15:42 | MR2506/0327 |  | 132KV_132kv chhindwara saori feeder | 220KV_CHHINDWARA | NON-OCCM-MP | f/o disc replacement at loc 17 | 16-06-2025 10:00:00 | 16-06-2025 14:00:00 | A.M.SHENDE | 7587951136 | o&m consent required
8 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
9 | 2025-06-15 14:21 | MR2506/0322 |  | 220KV_220KV GANJ BASODA- BHOPAL CKT | 220KV_GANJBASODA | NON-OCCM-MP | DISTANCE PEOTECTION RELAY REPLACEMENT WORK | 16-06-2025 10:00:00 | 16-06-2025 18:00:00 | PUSHPENDRA VERMA | 9425804364 | Deffered due to s/d on bus at 220kv Bina
10 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
11 | 2025-06-15 12:37 | MR2506/0317 |  | 220KV_220 KV Hoshangabad Mandideep Line | 220KV_HOSHANGABAD | NON-OCCM-MP | Commissioning of Main2 DPR | 16-06-2025 10:00:00 | 16-06-2025 17:00:00 | V.P.DWIVEDI | 9425804799 | real time
12 | 2025-06-12 16:27 | MR2506/0283 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service, through sub ld
13 | 2025-06-12 15:54 | MR2506/0282 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service, through sub ld
14 | 2025-05-23 18:38 | MR2505/0487 | Continuous | 220KV_NARSINGHPUR-JABALPUR_Ckt_2 | 220KV_JABALPUR | NON-OCCM-MP | BUNCHING OF 132KV JBP SHAHPURA WITH220 KV JBP NSP | 26-05-2025 09:00:00 | 20-06-2025 18:00:00 | RAJESH TIWARI | 7898239595 | Deffered by site
15 | 2025-06-15 07:40 | MR2506/0312 |  | 132KV_SHUTDOWN ON 40MVA APEX X-MER AT 132KV S/S KATNI | 132KV_KATNI | NON-OCCM-MP | Structure Aluminum Painting Work | 16-06-2025 07:00:00 | 16-06-2025 09:00:00 | YOGESH PATEL | 9425808211 | ok
16 | 2025-06-14 17:25 | MR2506/0311 |  | 132KV_132 kv katni panagar line | 132KV_KATNI | NON-OCCM-MP | For maintenance work . | 16-06-2025 10:00:00 | 16-06-2025 18:00:00 | pankaj yadav | 9406713326 | ok
17 | 2024-11-20 16:15 | MR2411/0427 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Deffered
18 | 2024-11-20 16:18 | MR2411/0428 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 16-06-2025 09:00:00 | 21-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | Deffered
19 | 2025-06-15 11:31 | MR2506/0314 |  | 400KV_400/132/33 KV 100 MVA X-MER No-03 CGL | 400KV_KIRNAPUR | NON-OCCM-MP | For Pre-monsoon maintenance works | 16-06-2025 09:00:00 | 16-06-2025 18:00:00 | D. S. Walkey | 9425804578 | ok, timely completion required
20 | 2025-06-13 15:06 | MR2506/0297 |  | 132KV_132 KV AUX.BUS AT S/S MADWAS | 132KV_MADWAS | NON-OCCM-MP | Due to high bus stringing work at s/s Madwas | 16-06-2025 08:00:00 | 16-06-2025 13:00:00 | J.N.SINGH | 9425802388 | ok
21 | 2025-06-15 12:52 | MR2506/0318 |  | 220KV_220KV NARMADAPURAM BAY ON B/COUPER | 220KV_MANDIDEEP | OCCM-MP | RELAY TESTING WORK | 16-06-2025 11:00:00 | 16-06-2025 18:00:00 | A.K. VERMA | 9425801324 | ok, line to be in service through TBC
22 | 2025-06-14 11:35 | MR2506/0306 |  | 132KV_132kV Nainpur-Baihar Line | 132KV_NAINPUR | NON-OCCM-MP | Tightening Work of Jumper Cone & Emergency TC Work | 16-06-2025 10:00:00 | 16-06-2025 17:00:00 | SHRIDHAR KUMAR BHALADHARE | 9425807264 | Deffered due to s/d on Kirnapur ICT
23 | 2025-06-15 14:29 | MR2506/0323 |  | 220KV_220 Kv Nalkheda-Rajgarh-2 line | 220KV_NALKHEDA | NON-OCCM-WR | Additional DPR-2 Installation and pre monsoon Main | 16-06-2025 10:00:00 | 16-06-2025 17:00:00 | VK Gupta | 9425801214 | ok, through sub ld
24 | 2025-06-12 12:51 | MR2506/0265 | Daily | 220KV_220KV Daloda-Mandsaur | 220KV_NEEMUCH | NON-OCCM-MP | OPGW OTDR testing & OPGW Splicing | 13-06-2025 08:30:00 | 17-06-2025 18:30:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
25 | 2025-06-09 15:58 | MR2506/0188 | Continuous | 220KV_Generating Unit No. 06 | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual maintenance | 10-06-2025 10:00:00 | 24-06-2025 18:00:00 | Sh. Pankaj Sharma | 7898703187 | as per the system requirement
26 | 2025-06-14 13:29 | MR2506/0309 |  | 220KV_220 kV Panagar- Birsinghpur | 220KV_PANAGAR | NON-OCCM-MP | Disc F/o change at loc. 412 (T) Top Ph | 16-06-2025 09:00:00 | 16-06-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
27 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | on hold, shall be confirmed tomorrow
28 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | on hold, shall be confirmed tomorrow
29 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
30 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
31 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
32 | 2025-06-15 13:13 | MR2506/0319 | Daily | 220KV_220 kv Sarni Handia | 220KV_SARNI | NON-OCCM-MP | Resagging work b/w loc.no. 192 to213 | 16-06-2025 09:00:00 | 18-06-2025 18:00:00 | Ashutosh rai | 9425806902 | ok, through sub ld
33 | 2025-05-21 18:20 | MR2505/0450 | Continuous | 400KV_400KV ASHTA LINE-I | 400KV_SATPURA TPS | NON-OCCM-MP | Maintenance & testing of bay Equipment | 16-06-2025 09:00:00 | 18-06-2025 18:00:00 | S.S THAKUR | 9425611244 | deffered
34 | 2025-06-13 09:54 | MR2506/0287 | Continuous | 220KV_Birsinghpur- Manpur fdr. | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 KV circuit breaker | 16-06-2025 08:00:00 | 19-06-2025 16:00:00 | s banerjee | 9424352880 | deffered, due to outage of 400kv Brs-Damh ckt
35 | 2025-06-14 12:00 | MR2506/0307 |  | 220KV_220 KV Sukha-Narsinghpur Line Ckt-II | 220KV_SUKHA | NON-OCCM-MP | Pre - Monsoon Maintenance work flashover disc repl | 16-06-2025 10:00:00 | 16-06-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
36 | 2025-04-17 17:31 | MR2504/0478 | Daily | 132KV_132 kV Tikamgarh IC - 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | MPPTCL Chhatarpur | 942580499 | ok, line to be in service
37 | 2025-04-17 17:34 | MR2504/0479 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Installation work | 18-04-2025 07:00:00 | 19-06-2025 19:00:00 | Manoj Kumar Tiwari | 942580499 | ok, line to be in service
38 | 2025-06-15 13:32 | MR2506/0320 |  | 132KV_40 MVA BBL-make-Make Transformer | 220KV_TIKAMGARH | NON-OCCM-MP | Replacement of neutral copper strip | 16-06-2025 09:00:00 | 16-06-2025 14:00:00 | Pushpendra Kumar soni | 9425806398 | ok
39 | 2025-06-15 12:00 | MR2506/0316 |  | 40MVA_132/33KV_BBL_X'mer_3 | 132KV_WAIDHAN | NON-OCCM-MP | 03 NOS. 132KV CT REPLACEMENT WORK | 16-06-2025 09:00:00 | 16-06-2025 17:00:00 | G.S KHAIRWAR | 9584321714 | ok
40 |  | 251467 |  | 400KV-SINGAJI-PITHAMPUR-1 |  | WR-OCCM | for tower strengthening works | 16-06-2025 08:00:00 | 30-06-2025 17:59:00 |  |  | On Hold Shall Be Confirmed Tomorrow Ok. Ckt-1,2 Outage is proposed simultaneously .400KV-SINGAJI-PITHAMPUR-3 & 4 (Sensitivity of 29%) and 400KV-SINGAJI-Chegaon(Sensitiviity of 26%) to be in service with A/R enabled. If required 400kV Chhegaon Rajgarh PG may be open to control loading as suggested by SLDC MP. In case of contingency load to be managed by SLDC MP.No S/D to be given in 220KV side at Singaji during S/D by period by SLDC MP. In case of contingency load to be managed by SLDC MP
41 |  | 251468 |  | 400KV-SINGAJI-PITHAMPUR-2 |  | WR-OCCM | for tower strengthening works | 16-06-2025 08:00:00 | 30-06-2025 17:59:00 |  |  | On Hold Shall Be Confirmed Tomorrow Ok. Ckt-1,2 Outage is proposed simultaneously .400KV-SINGAJI-PITHAMPUR-3 & 4 (Sensitivity of 29%) and 400KV-SINGAJI-Chegaon(Sensitiviity of 26%) to be in service with A/R enabled. If required 400kV Chhegaon Rajgarh PG may be open to control loading as suggested by SLDC MP. In case of contingency load to be managed by SLDC MP.No S/D to be given in 220KV side at Singaji during S/D by period by SLDC MP. In case of contingency load to be managed by SLDC MP
42 |  | 249966 |  | 400KV-BADNAWAR-RAJGARH-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 16-06-2025 08:00:00 | 16-06-2025 18:00:00 |  |  | Real Time Ok.400kV RAJGARH-PG -BADNAWAR-MP -T2 Sensitivity of 55.03% and All other lines at Badnawar - 400KV and RAJGARH - 400KV to be in service with A/R Enabled
43 |  | 249999 |  | 220KV-ITARSI-MP-ITARSI-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT 220KV S/S ITARSI | 16-06-2025 07:00:00 | 16-06-2025 17:00:00 |  |  | Real Time All other lines at Itarsi-MP to be in service with AR enabled. No other element shall be effected. Load to be managed by SLDC MP. WR-2 to be informed.
44 |  | 250000 |  | 220KV-MORENA-MORENA-MP-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 16-06-2025 09:00:00 | 16-06-2025 17:00:00 |  |  | Real Time All other lines at Morena to be in service with AR enabled. No other element shall be effected. Morena (Adani) to be informed. Load to be managed by SLDC MP
45 |  | 250001 |  | 220KV-SEONI-MP-SEONI-PG-2 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 16-06-2025 09:00:00 | 16-06-2025 18:00:00 |  |  | Real Time All other liens at Seoni-MP I to be in service. WR1 to be informed. Load to be managed by SLDC MP
46 |  | 250002 |  | 220KV-BETUL-PANDURNA-1 |  | WR-OCCM | FOR CONDUCTOR RE-SAGGING WORKS IN VARIOUS SECTION | 16-06-2025 08:00:00 | 16-06-2025 18:00:00 |  |  | Real Time All other lines at Pandurna to be in service with AR enabled. SLDC MH to be informed. Load to be managed by SLDC MP/MH
47 |  | 250018 |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 16-06-2025 09:00:00 | 16-06-2025 17:00:00 |  |  | OK All other lines at Annuppur/Kotmikala to be in service with AR enabled. Load to be managed by SLDC MP/CG
48 |  | 249652 |  | 400KV/220KV REWA-ICT-3 |  | WR-OCCM | Commissioning of CSD, During testing, ICT will be charged and discharged few times | 16-06-2025 10:00:00 | 16-06-2025 18:00:00 |  |  | OK All other ICT's at Rewa to be in service. SLDC MP /RE generators to be informed. Sensitivity on ICT 1.2(42 % each).
49 |  | 253391 |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  | WR-OCCM | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 16-06-2025 07:00:00 | 16-06-2025 18:59:00 |  |  | OK Line To Be In ServiceA/R in N/A, Line will be in service.
50 |  | 253403 |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  | WR-OCCM | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 16-06-2025 07:00:00 | 16-06-2025 18:59:00 |  |  | OK Line To Be In ServiceA/R in N/A, Line will be in service.