## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-08 |  |  | APPROVED OUTAGE LIST FOR DTD.08.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-07 13:58 | MR2508/0108 |  | 220KV_220 kV Amarkantak-Sidhi Circuit | 220KV_AMARKANTAK | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 08-08-2025 10:00:00 | 08-08-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-08-07 15:24 | MR2508/0113 |  | 132KV_132kV Balaghat-Laburra Line | 132KV_BALAGHAT | NON-OCCM-MP | F/O Disc Replacement & Other Maintenance Work | 08-08-2025 10:00:00 | 08-08-2025 14:00:00 | S.K.BHALADHARE | 9425807264 | ok
3 | 2025-08-01 17:06 | MR2508/0013 | Continuous | 400KV_400 kV TIE CB of 315 MVA X-mer-II (BHEL) | 400KV_BINA4 | NON-OCCM-MP | Replacement of C&R panel of 400 kV TIE CB | 04-08-2025 09:00:00 | 08-08-2025 17:00:00 | Parmanand namdeo | 7587951092 | Continuous
4 | 2025-08-06 18:54 | MR2508/0098 |  | 132KV_132KV MAIN BUS | 220KV_CHHINDWARA | NON-OCCM-MP | 132KV MAIN BUS TO ISOLATOR JUMPER REPLACEMENT WORK | 08-08-2025 09:00:00 | 08-08-2025 12:00:00 | A A QURESHI | 9425804318 | ok, shall be given after load shifting
5 | 2025-08-07 11:38 | MR2508/0104 |  | 33KV_33 KV main bus section -l | 132KV_DATIA1 | NON-OCCM-MP | Main bus damage jumper replacement | 08-08-2025 10:00:00 | 08-08-2025 13:00:00 | Atul shakya | 9425806928 | sub ld
6 | 2025-08-07 11:00 | MR2508/0102 |  | 220KV_220 KV Gujarkhedi - Mandsaur Ckt.-I | 220KV_GUJARKHEDI | NON-OCCM-MP | OPGW Stringing Work | 08-08-2025 10:00:00 | 08-08-2025 13:00:00 | Ravindra Kumar Marskole | 9425814080 | ok, through sub ld
7 | 2025-07-29 10:54 | MR2507/0453 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | communication consent required for data re routing
8 | 2025-08-07 14:38 | MR2508/0110 |  | 220KV_JULWANIYA4-JULWANIYA_Ckt_2 | 400KV_JULWANIYA4 | NON-OCCM-MP | For both end CT tan delta measurement & bay main.w | 08-08-2025 09:30:00 | 08-08-2025 16:30:00 | Er. Ravindra Patil | 8305612190 | ok, through sub ld
9 | 2025-08-07 15:16 | MR2508/0112 |  | 220KV_220KV Julwania -Julwania I/C Ckt-2 line | 400KV_JULWANIYA4 | NON-OCCM-MP | Jumper tightening & other line maintenance work. | 08-08-2025 09:30:00 | 08-08-2025 16:30:00 | Dinesh More | 9425806860 | as opportunity s/d
10 | 2025-08-07 12:15 | MR2508/0105 |  | 33KV_33KV Main Bus | 132KV_KATANGI | NON-OCCM-MP | To attend Red Hot point on 33KV Main Bus Clamp | 08-08-2025 09:00:00 | 08-08-2025 10:00:00 | Seema Dongre | 9425807247 | ok for x-mers
11 | 2025-06-30 16:04 | MR2506/0631 | Continuous | 220KV_220KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 04-08-2025 09:00:00 | 09-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
12 | 2025-06-30 15:11 | MR2506/0622 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 04-08-2025 09:00:00 | 09-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
13 | 2025-08-04 15:34 | MR2508/0043 | Continuous | 400KV_125MVAR BUS REACTOR | 400KV_MANDSOUR4 | OCCM-MP | 400KV MAIN BUS-1&2 BUS CVT KEPT OFF | 05-08-2025 09:00:00 | 08-08-2025 18:00:00 | RAJESH BHURIA | 9425806920 | as per the voltage profile
14 | 2025-07-29 10:59 | MR2507/0454 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | for replacement existing of 24 Fibre OPGW by 48 Fi | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | communication consent required for data re routing
15 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
16 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
17 | 2025-08-07 12:29 | MR2508/0106 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 220KV_REWA | NON-OCCM-MP | Y Phase 132 Kv CT leakge & hot Point | 08-08-2025 11:00:00 | 08-08-2025 16:00:00 | Kanisk Singh | 9425804656 | real time
18 | 2025-08-07 13:20 | MR2508/0107 | Continuous | 400KV_500 MVA, 400/220 kV ICT | 400KV_SGTPS | NON-OCCM-MP | Testing of NR, DCRM of Bkr, CT testing, aircell re | 08-08-2025 08:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | ok
19 | 2025-08-07 14:37 | MR2508/0109 |  | 132KV_132kv Sidhi-Mauganj circuit -I | 220KV_SIDHI | NON-OCCM-MP | Flash over disc replacement | 08-08-2025 10:00:00 | 08-08-2025 17:00:00 | G.L sahu | 9425805102 | deffered due to rewa x-mer s/d
20 | 2025-07-23 17:35 | MR2507/0376 | Continuous | 400KV_Interconnecting Transformer-II 400KV/220KV | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of ICT-II | 04-08-2025 09:30:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | deffered
21 | 2025-08-01 18:48 | MR2508/0015 | Continuous | 400KV_90 MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of Station Transformer-2 | 04-08-2025 09:00:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | Continuous
22 | 2025-08-07 14:57 | MR2508/0111 |  | 400KV_400 kV Ujjain-Nagda Ckt-2nd | 400KV_UJJAIN4 | NON-OCCM-MP | FOTE Panel wiring& Commissioning work | 08-08-2025 11:00:00 | 08-08-2025 14:00:00 | Santosh Chavrasia | 9425804677 | ok, through sub ld
23 | 2025-08-07 14:57 |  |  | 220KV-BINA-SHIVPURI-1 |  | OCCM WR | FOR LINE MAINTENANCE WORK | 08-Aug-2025 | 09:00 | 08-Aug-2025 | 17:00 | real time
24 | 2025-08-07 14:57 |  |  | 220KV-SATNA-MP-SATNA-2 |  | OCCM WR | FOR LINE MAINTENANCE WORK | 08-Aug-2025 | 10:00 | 08-Aug-2025 | 17:00 | real time
25 | 2025-08-07 14:57 |  |  | MANDSAUR-MP - 400KV - BUS 2 |  | OCCM WR | for isolator alignment work, bus extension and high bus overhead stringing work for installation of new 500MVA ICT | 08-Aug-2025 | 08:00 | 08-Aug-2025 | 17:59 | ok, through sub ld
26 | 2025-08-07 14:57 |  |  | 220KV-GWALIOR-GWALIOR-II-2 |  | OCCM WR | FOR BAY MAINTENANCE & TESTING WORK | 08-Aug-2025 | 09:00 | 08-Aug-2025 | 17:00 | real time
27 | 2025-08-07 14:57 |  |  | bus coupler outage | 400 KV SSTPS | NON-OCCM | MAINT. WORK | 08-Aug-2025 | 09:00 | 08-Aug-2025 | 17:00 | OK
S/I ,SLDC JABALPUR MP