## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-31
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-29 17:13 | MR2510/0683 | Daily | 132KV_40 MVA BBL Xmer | 132KV_AMARPATAN | NON-OCCM-MP | for replacement of isolator | 30-10-2025 10:00:00 | 31-10-2025 16:00:00 | Arun Kumar | 9131207339 | ok
2 | 2025-10-30 15:42 | MR2510/0693 |  | 132KV_132 KV all feeder and 132 and 33 KV main bus | 132KV_AMARPATAN | NON-OCCM-MP | reconnection jumper of 40 MVA BBL Xmer | 31-10-2025 13:00:00 | 31-10-2025 16:00:00 | Arun Kumar | 9131207339 | ok
3 | 2025-10-30 10:58 | MR2510/0685 |  | 63MVA_132/33KV_BBL_Xmer_1 | 132KV_AMARWARA | NON-OCCM-MP | Post monsoon maintenance work. | 31-10-2025 10:00:00 | 31-10-2025 17:00:00 | S.K.OKTE | 7587951132 | ok
4 | 2025-10-30 16:03 | MR2510/0694 |  | 220KV_220 KV ASHTA-BAIRAGARH FEEDER | 400KV_ASHTA4 | NON-OCCM-MP | RELAY TESTING WORK | 31-10-2025 11:00:00 | 31-10-2025 17:00:00 | JITENDRA LOHANA | 9425804978 | ok, through sub ld
5 | 2025-10-16 17:16 | MR2510/0478 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | M.M. BAIG | 9425805067 | deffered
6 | 2025-10-30 11:19 | MR2510/0687 |  | 220KV_220KV PGCIL No.-02 | 220KV_ITARSI | OCCM-MP | Bay Maintenance work | 31-10-2025 07:00:00 | 31-10-2025 17:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
7 | 2025-10-30 10:45 | MR2510/0684 |  | 220KV_220 KV Itarsi-Handia II | 220KV_ITARSI | NON-OCCM-MP | For replacement of Single to Double Disc Ins.work | 31-10-2025 09:00:00 | 31-10-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
8 | 2025-10-30 12:14 | MR2510/0688 |  | 220KV_220KV Julwania - Kukshi DCDS Ckt-1 line | 400KV_JULWANIYA4 | NON-OCCM-MP | F/O disc insulator rep. & Add. bird exc. prevent. | 31-10-2025 10:00:00 | 31-10-2025 17:00:00 | Dinesh More | 9425806860 | ok, through sub ld
9 | 2025-09-18 13:12 | MR2509/0414 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | deffered
10 | 2025-10-30 14:42 | MR2510/0692 |  | 220KV_220/132KV 160MVA X-Mer-II BHEL | 220KV_NIMRANI | NON-OCCM-MP | Post Monsoon Maintenance work | 31-10-2025 10:00:00 | 31-10-2025 17:00:00 | Er.Pradip Patidar | 9981046192 | ok, through sub ld
11 | 2025-10-30 11:12 | MR2510/0686 |  | 160MVA_220/132KV_BHEL_X'mer | 220KV_PANAGAR | NON-OCCM-MP | post mansoon maint. work | 31-10-2025 10:00:00 | 31-10-2025 18:00:00 | H L koshta | 7587951105 | ok
12 | 2025-10-30 16:20 | MR2510/0695 |  | 132KV_132 KV Rampur Baghelan feeder | 132KV_SATNA1 | NON-OCCM-MP | cleaning CT and LA clamp tightening work | 31-10-2025 12:00:00 | 31-10-2025 14:00:00 | Vishal bhaladhare | 9425804690 | ok
13 | 2025-09-05 17:39 | MR2509/0127 | Continuous | 400KV_400KV Sarni-Ashta line-II | 400KV_SATPURA TPS | NON-OCCM-MP | Work of complete overhauling & testing of 400KV br | 30-10-2025 09:00:00 | 01-11-2025 18:00:00 | YASHWANT WARATHE | 9425611046 | deffered
14 | 2025-10-30 13:23 | MR2510/0689 |  | 132KV_132/33KV 40MVA X-MER BHEL | 132KV_TEJGARH | NON-OCCM-MP | POST MONSOON MAINTENANCE AND TESTING WORK | 31-10-2025 10:00:00 | 31-10-2025 18:00:00 | RAHUL GAJBHIYE | 9425801304 | ok
15 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous