## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-26 |  |  | APPROVED OUTAGE LIST FOR DATED 26.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-25 15:49 | MR2507/0412 |  | 33KV_33kv main bus | 220KV_ANUPPUR | NON-OCCM-MP | hot point & jumper replacement work | 26-07-2025 06:00:00 | 26-07-2025 09:00:00 | sunil kumar bhalavi | 9425804704 | ok for 132/33kv x-mers
2 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
3 | 2025-07-25 14:12 | MR2507/0407 |  | 220KV_220KV CHHATARPUR - AJAYGARH(TBCB)CKT IIND LINE | 220KV_CHATARPUR | NON-OCCM-MP | SLIP/MISSING VD ATTENDING&OTHER MAIN. | 26-07-2025 10:00:00 | 26-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 7389495001 | ok
4 | 2025-07-25 12:02 | MR2507/0402 |  | 220KV_220KV Main Bus No.-1 | 220KV_ITARSI | NON-OCCM-MP | Main Bus No.1 connection the 7th section | 26-07-2025 10:00:00 | 26-07-2025 15:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld, 220kv Itasri-Sarni -3 ckt will also be under outage
5 | 2025-07-25 15:39 | MR2507/0410 |  | 132KV_132KV Incoming- I of 160MVA X-mer | 220KV_JAORA | NON-OCCM-MP | 132 KV Main bus section-II shutdown | 26-07-2025 10:00:00 | 26-07-2025 13:00:00 | Er. Rakesh Kumar Badgotiya | 8305447051 | ok, if load is manageble by sub ld Indore, o&m consent required
6 | 2025-07-25 15:41 | MR2507/0411 |  | 132KV_132KV Incoming-II of 160MVA-II X-mer | 220KV_JAORA | NON-OCCM-MP | 132 KV Main bus section-II shutdown | 26-07-2025 10:00:00 | 26-07-2025 13:00:00 | Er. Rakesh Kumar Badgotiya | 8305447051 | ok, if load is manageble by sub ld Indore, o&m consent required
7 | 2025-07-25 13:47 | MR2507/0406 |  | 132KV_132 KV KATNI IC LINE CKT 1 ST | 132KV_KATNI | NON-OCCM-MP | LINE MAINTENANCE WORK | 26-07-2025 10:00:00 | 26-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
8 | 2025-06-30 14:52 | MR2506/0617 | Continuous | 400KV_400KV KATNI-DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-06-30 15:42 | MR2506/0629 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
10 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
11 | 2025-07-24 12:06 | MR2507/0378 |  | 132KV_132KV Main Bus at 132KV Mandla | 132KV_MANDLA | NON-OCCM-MP | for Overhead stringing & Main Bus Isolator Jumper | 26-07-2025 06:00:00 | 26-07-2025 10:00:00 | Vijay Kumar Tandekar | 9425805095 | Deffered by site
12 | 2025-07-24 14:21 | MR2507/0386 | Daily | 220KV_220KV Neemuch Mandsaur Circuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | only hotline permit | 25-07-2025 08:00:00 | 27-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
13 | 2025-07-24 14:16 | MR2507/0385 | Continuous | 220KV_220KV Neemuch-Mandsaur Circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | OPGW Work | 25-07-2025 09:00:00 | 27-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | ok, through sub ld, telemetry to be manual marked by sub ld Indore
14 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
15 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
16 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
17 | 2025-07-11 16:53 | MR2507/0159 | Daily | 220KV_Main BUSâ¿¿B and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 23-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered
18 | 2025-07-17 15:15 | MR2507/0245 | Continuous | 400KV_400 KV MAIN BUS-2 | 400KV_SAGAR | OCCM-MP | FOR EXTENSION OF MAIN BUS -2 | 25-07-2025 08:00:00 | 26-07-2025 17:00:00 | ANIL MAHOR | 9425805149 | Deffered
19 | 2025-07-25 15:35 | MR2507/0408 |  | 132KV_63 MVA X-MAR ABB -1 | 132KV_SAGAR1 | NON-OCCM-MP | STRINGGING OF EARTH WIRE OVER 33KV MAIN BUS | 26-07-2025 07:00:00 | 26-07-2025 10:00:00 | S.K.HAJARI | 9425620010 | o&m consent required
20 | 2025-07-25 12:22 | MR2507/0403 |  | 132KV_132 KV Satna - Rampur baghelan line | 132KV_SATNA1 | NON-OCCM-MP | Line maintenance work | 26-07-2025 10:00:00 | 26-07-2025 17:00:00 | Mr. M.M. Baig | 9425805067 | ok
21 | 2025-07-25 10:36 | MR2507/0400 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 163-165 | 26-07-2025 10:00:00 | 27-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
22 | 2025-07-25 10:16 | MR2507/0399 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 163-164 | 26-07-2025 10:00:00 | 27-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
23 | 2025-07-19 17:13 | MR2507/0270 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
24 | 2025-07-19 17:15 | MR2507/0271 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
25 | 2025-07-01 17:04 | MR2507/0021 |  | 220KV_220KV Singaji Chhegaon feeder - 2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay Testing work of 220KV Chhegaon-2 during AOH | 26-07-2025 10:00:00 | 26-07-2025 19:00:00 | Deepak Sharma | 8005696855 | ok, through sub ld
|  |  |  | 220KV-SATNA-KOTAR-1 | MADHYA PRADESH |  | AMP Work & Line Terminal Equipment Tightness; | 26-Jul-2025 | 09:00 | 26-Jul-2025 | 18:00 | ok
|  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 26-Jul-2025 | 08:00 | 26-Jul-2025 | 17:59 | ok
S/I SLDC JABALPUR