## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-14 |  |  | 2025-10-14
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 12:03 | MR2510/0056 | Daily | 220KV_220 kV Adampur-Hoshangabad line | 220KV_ADAMPUR | NON-OCCM-MP | Defective Disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
2 | 2025-10-13 14:30 | MR2510/0376 |  | 132KV_132 kV Anuppur-Kotma Circuit I | 220KV_ANUPPUR | NON-OCCM-MP | F/o disc stringing replacement & other line mainta | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok
3 | 2025-10-13 15:16 | MR2510/0389 |  | 400KV_400 KV ASHTA-UJJAIN CKT.NO.1 | 400KV_ASHTA4 | NON-OCCM-MP | POST MONSOON BAY MAINTENANCE WORK | 14-10-2025 09:00:00 | 14-10-2025 15:00:00 | JITENDRA LOHANA | 9425804978 | ok, through sub ld
4 | 2025-10-13 11:41 | MR2510/0354 |  | 132KV_40 MVA X-mer (BHEL) | 132KV_BAIHAR | NON-OCCM-MP | post monsoon maint. work | 14-10-2025 09:00:00 | 14-10-2025 17:00:00 | Swati Bisen | 9425801737 | ok
5 | 2025-10-13 15:18 | MR2510/0390 |  | 220KV_220KV Main Bus Section -II | 220KV_BARWAHA | NON-OCCM-WR | 220KV Main Bus Maintenance work | 14-10-2025 09:00:00 | 14-10-2025 15:00:00 | Er.Imran Beg | 9425805200 | ok, through sub ld after load management, upto 4 machines (max) of OSP allowed during s/d period
6 | 2025-10-13 16:18 | MR2510/0395 |  | 132KV_63MVA Transformer Make BBL | 132KV_BETUL1 | NON-OCCM-MP | PMM Work | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | Er. Vishal kumar Malviya | 9425804955 | sub ld
7 | 2025-10-13 12:51 | MR2510/0363 |  | 220KV_220 KV160MVA Transformer No. 1, CGL | 220KV_BHOPAL | NON-OCCM-WR | for Post Monsoon maintenance | 14-10-2025 09:00:00 | 14-10-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
8 | 2025-10-13 12:13 | MR2510/0356 |  | 220KV_220 KV Bina Shivpuri MPPTCL line | 400KV_BINA4 | NON-OCCM-MP | Flash over disc replacement work and other line ma | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 | Satish Kumar Bhagat | 9425806916 | ok, through sub ld
9 | 2025-10-13 13:45 | MR2510/0374 |  | 400KV_50MVAR_BHOPAL-II_LINE REACTOR | 400KV_BINA4 | NON-OCCM-MP | POST MONSOON MAINTENANCE | 14-10-2025 09:00:00 | 14-10-2025 14:00:00 | PERMANAND NAMDEO | 9039472058 | ok, through sub ld
10 | 2025-10-13 13:27 | MR2510/0372 |  | 132KV_132/33 KV 63 MVA BHEL XMER-1 | 132KV_CHAMBAL | NON-OCCM-MP | POST MOONSOON MAINTANANCE | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | ASHISH JAIN | 9425806899 | sub ld
11 | 2025-10-13 15:03 | MR2510/0384 |  | 220KV_220 KV Main Bus | 220KV_CHATARPUR | NON-OCCM-MP | For Conductor dismentle | 14-10-2025 08:00:00 | 14-10-2025 12:00:00 | Sameer Parte | 9575673359 | comments of T&C awaited
12 | 2025-09-18 17:20 | MR2509/0454 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deferred
13 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
14 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
15 | 2025-10-13 13:00 | MR2510/0369 |  | 220KV_160 MVA XMER NO II BBL | 220KV_GANJBASODA | NON-OCCM-MP | POST MANSOON | 14-10-2025 08:30:00 | 14-10-2025 17:30:00 | M.R. SAHU | 9425804982 | ok, through sub ld
16 | 2025-10-13 15:22 | MR2510/0391 |  | 132KV_132/33 40MVA XMER BBL | 132KV_GOURJHAMAR | NON-OCCM-MP | Postmonsoon maintenance and testing work. | 14-10-2025 11:00:00 | 14-10-2025 18:00:00 | P D GOUTAM | 9425808329 | o&m consent required
17 | 2025-10-13 14:31 | MR2510/0378 |  | 220KV_220KV SARNI-HANDIA LINE | 220KV_HANDIYA | NON-OCCM-MP | F/O DISC REPLACEMENT WORK. | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | R.N. PARTE | 9425804701 | Deffered due to s/d on Barwaha bus section
18 | 2025-10-10 11:49 | MR2510/0277 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 78-94 | 11-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | as opportunity s/d
19 | 2025-10-13 12:19 | MR2510/0359 | Continuous | 132KV_NORTHZONE - CHAMBLE CKT-1 LINE | 220KV_INDORE-NZ | NON-OCCM-MP | DAMAGE CONDUCTOR REPLACEMENT WORK. | 13-10-2025 22:00:00 | 14-10-2025 08:00:00 | A.R. KANEL | 9425805217 | sub ld
20 | 2025-10-10 14:45 | MR2510/0293 |  | 220KV_220KV INDORE-SOUTH ZONE-2 LINE | 400KV_INDORE4 | NON-OCCM-MP | POST MONSOON MAINTANANCE WORK | 14-10-2025 09:00:00 | 14-10-2025 17:00:00 | ATUL PARADKAR | 9425804929 | Deffered due to s/d on Barwaha bus section
21 | 2025-10-13 11:03 | MR2510/0351 | Daily | 220KV_220 KV Itarsi-Handia Ckt-II | 220KV_ITARSI | NON-OCCM-MP | Replacement of Single to Double Insulator work | 14-10-2025 09:00:00 | 15-10-2025 18:00:00 | Ashutosh Rai | 9425806902 | Deffered due to s/d on Barwaha bus section
22 | 2025-10-13 11:32 | MR2510/0353 |  | 220KV_220 kV Jabalpur- Amarkantak | 220KV_JABALPUR | NON-OCCM-MP | Flash over disc change at loc no 321 T Ph | 14-10-2025 11:00:00 | 14-10-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
23 | 2025-10-12 11:51 | MR2510/0329 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 400KV_JULWANIYA4 | NON-OCCM-MP | Post monsoon maintenance & testing work | 14-10-2025 09:30:00 | 14-10-2025 17:30:00 | ER. Mannalal Badole | 9131865464 | ok, through sub ld
24 | 2025-10-13 14:51 | MR2510/0379 |  | 132KV_132 KV KATNI KAYMORE CKT 1 | 400KV_KATNI4 | NON-OCCM-MP | LINE MAINTINANCE | 14-10-2025 10:00:00 | 14-10-2025 13:00:00 | PANKAJ YADAV | 9406713326 | ok
25 | 2025-10-13 14:55 | MR2510/0380 |  | 132KV_132 KV KATNI KAYMORE CKT 2 | 400KV_KATNI4 | NON-OCCM-MP | MAINTINACE WORK | 14-10-2025 13:00:00 | 14-10-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
26 | 2025-10-13 15:09 | MR2510/0386 |  | 132KV_40 MVA BBL X-MER | 400KV_KATNI4 | NON-OCCM-MP | 33KV HALF MAIN BUS MAINTENANCE WORK | 14-10-2025 10:00:00 | 14-10-2025 14:00:00 | SK chaturvedi | 9425806938 | o&m consent required
27 | 2025-09-18 13:00 | MR2509/0411 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deferred
28 | 2025-10-13 16:20 | MR2510/0399 |  | 132KV_132KV Kolaras - Mada line | 132KV_KOLARAS | NON-OCCM-MP | For DF/O replacement & other line maint. work | 14-10-2025 10:00:00 | 14-10-2025 15:00:00 | Akhilesh Singh | 8586865656 | sub ld
29 | 2025-10-13 15:40 | MR2510/0392 |  | 220KV_160 MVA X-MER IMP | 220KV_KOTAR | OCCM-MP | Hot point attending 132kv CB TO CT Side Clamp | 14-10-2025 14:00:00 | 14-10-2025 15:30:00 | Arun Kumar kol | 8319677721 | ok
30 | 2025-10-13 13:53 | MR2510/0375 |  | 220KV_160MVA TRANSFORMER | 220KV_MANGLIA2 | NON-OCCM-MP | Post mansoon maintanance | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 | Er.Siddharth Joshi | 9425804936 | ok, through sub ld, o&m shall be informed
31 | 2025-10-13 13:44 | MR2510/0373 |  | 132KV_40MVA BBL X-mer | 132KV_MAUGANJ | OCCM-MP | Post monsoon maintenance | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | IJ Singh | 9424734033 | ok
32 | 2025-10-13 15:01 | MR2510/0383 |  | 160MVA_220/132KV_BBL_X'mer | 220KV_MORENA | NON-OCCM-MP | Post monsoon maintenance work. | 14-10-2025 10:00:00 | 14-10-2025 18:00:00 | AMIT KUMAR DHANELIYA | 9425802242 | ok, through sub ld
33 | 2025-10-13 12:28 | MR2510/0360 |  | 132KV_132/33 KV 40 MVA TELK Xmer | 132KV_NARSINGHPUR1 | NON-OCCM-MP | Post monsoon maintenance work | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | Er. R.K. Chaturvedi | 9425805203 | o&m consent required
34 | 2025-10-13 12:49 | MR2510/0362 |  | 220KV_220 kV Khandwa (PGCIL)- Omakareshwar Ckt 1st | 220KV_OMKARESHWAR | OCCM-WR | For Line Maintenance Work & Cleaning of Disc Insul | 14-10-2025 08:00:00 | 14-10-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
35 | 2025-10-13 13:25 | MR2510/0371 |  | 132KV_132 kv panagar - katangi feeder | 220KV_PANAGAR | NON-OCCM-MP | hot point attend R phase wavetrep | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | H.L.KOSHTA | 7587951105 | ok, o&m shall be informed
36 | 2025-10-13 11:27 | MR2510/0352 |  | 132KV_40 MVA X-MER MAKE IMP | 132KV_PRATAPPURA | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 14-10-2025 11:00:00 | 14-10-2025 17:00:00 | VIKRAM AHIRWAR | 9425805415 | sub ld
37 | 2025-10-13 15:00 | MR2510/0381 |  | 132KV_132kV Janakpur - Rajmilan Ckt | 132KV_RAJMILAN | NON-OCCM-MP | Disc String Replacement work | 14-10-2025 08:00:00 | 14-10-2025 17:00:00 | G.L Sahu | 9425805102 | ok
38 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
39 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
40 | 2025-10-13 14:31 | MR2510/0377 |  | 132KV_132KV 50 MVA BHEL X-MER | 132KV_REWA-II (SAGRA) | NON-OCCM-MP | PENTING WORK | 14-10-2025 10:00:00 | 14-10-2025 18:00:00 | AE. KANISHK SINGH | 9425804656 | ok
41 | 2025-10-13 12:52 | MR2510/0365 |  | 220KV_220kv Damoh-Sagar 1st ckt. Line (PGCIL) | 400KV_SAGAR | OCCM-MP | Line Maintenance work | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 | J.P. Asati | 9424445533 | ok
42 | 2025-10-13 12:58 | MR2510/0368 |  | 132KV_50MVA X-Mer BBL | 132KV_SAORI | NON-OCCM-MP | Post Mansoon Maintenance Work | 14-10-2025 09:00:00 | 14-10-2025 16:00:00 | Er. Anju Dhurve | 9425804752 | ok
43 | 2025-10-13 15:15 | MR2510/0388 |  | 220KV_160 MVA X-MER 3rd | 220KV_SHIVPURI | NON-OCCM-MP | Shutdown Proposed on 160 MVA transformer no 3rd BB | 14-10-2025 09:00:00 | 14-10-2025 15:00:00 | Rohit kumar yadav | 9425804921 | ok, through sub ld
44 | 2025-10-13 16:19 | MR2510/0398 |  | 132KV_132KV Shivpuri RTS Line | 220KV_SHIVPURI | NON-OCCM-MP | Line Maintenance work | 14-10-2025 10:00:00 | 14-10-2025 13:00:00 | Suraj Pawar | 9425814079 | sub ld
45 | 2025-10-13 15:57 | MR2510/0393 |  | 132KV_50 MVA Transformer-II Make -BBL | 132KV_SINGHANA | NON-OCCM-MP | for Post Monsoon Maintenance work | 14-10-2025 10:00:00 | 14-10-2025 18:00:00 | Er. Jagdish Mujalde | 9893790114 | sub ld
46 | 2025-10-13 15:07 | MR2510/0385 |  | 220KV_220 KV Tikamgarh-Chhatarpur & 132 KV Tkamgarh jatara line | 220KV_TIKAMGARH | NON-OCCM-MP | stringing work | 14-10-2025 08:00:00 | 14-10-2025 17:00:00 | Sameer Parte | 9575673359 | ok
47 | 2025-10-13 12:53 | MR2510/0367 |  | 220KV_220 KV UJJAIN 765KV PGCIL HATHUNIYA CKT 2 | 220KV_UJJAIN | OCCM-WR | LINE MAINTENANCE WORK | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 | KUMAR SACHINDRA SHARMA | 7415651054 | ok, through sub ld
48 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
49 | 2025-10-13 12:18 | MR2510/0358 |  | 220KV_220KV INTERCONNECTOR -IV | 400KV_UJJAIN4 | NON-OCCM-MP | POST MONSOON BAY MAINT.WORK | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | Mr.Santosh chavrasia | 9425804677 | Deferred, due to multiple outages in Ujjain
50 | 2025-10-13 15:11 | MR2510/0387 |  | 132KV_40MVA BBL NO.-1 | 132KV_VFJ | NON-OCCM-MP | POST MONSOON MAINTENENCE | 14-10-2025 10:00:00 | 14-10-2025 17:00:00 | AMIT KUMAR DAHIYA | 9425806926 | ok
51 |  | 265217 |  | 400KV-ITARSI-INDORE-MP-2 |  | WR-OCCM | Retrofitting of Old Electromechanical Differential Relay with New ABB make Relay of Line Reactor & CT Oil Sampling works.Dia to be kept open at both ends. | 14-10-2025 09:00:00 | 14-10-2025 20:00:00 |  |  | OK THROUGH SUB LD (Sensitivity on ckt-2 is 15%) Ckt-1 o be in service with AR enabled. SLDC MP to be informed.
52 |  | 265318 |  | 400KV-BINA-MP-GUNA-MP-1 |  | WR-OCCM | AMP work. | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 |  |  | OK THROUGH SUB LD Ok. Ckt-2 to be in service. Load to be managed by SLDC MP in case of contingency.
53 |  | 265932 |  | 400KV-INDORE-PITHAMPUR-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 14-10-2025 08:00:00 | 14-10-2025 18:00:00 |  |  | REAL TIME 400kV INDORE-PG -PITHAMPUR -T2 (sensitivity of 36%) and All other lines &ICTs at Pithampur/singhaji to be in service with AR enabled. No other element shall be effected. care to be taken.
54 |  | 265957 |  | 220KV-GWALIOR-GWALIOR-II-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 14-10-2025 09:00:00 | 14-10-2025 17:00:00 |  |  | REAL TIME All other lines at Gwalior-II to be in service with AR enabled. WR2 to be informed. Load to be managed by SLDC MP
55 |  | 265958 |  | 220KV-INDORE-UJJAIN-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT UJJAIN SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 |  |  | OK THROUGH SUB LD Ckt-1 and all other lines at Ujjain to be in service with AR enabled. No other element shall be effected. Load to be managed by SLDC MP. WR-2 to be informed.
56 |  | 265959 |  | 220KV-DAMOH-SAGAR-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 14-10-2025 09:00:00 | 14-10-2025 18:00:00 |  |  | OK All other lines at Sagar to be in service with AR enabled. Wr2 to be informed. Load to be managed by SLDC MP in case of contingency.
57 |  | 265960 |  | 220KV-BETUL-PANDURNA-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 14-10-2025 09:00:00 | 14-10-2025 17:00:00 |  |  | REAL TIME All other lines at Pandurna to be in service with AR enabled. Wr2 to be informed. Load to be managed by SLDC MP in case of contingency.
58 |  | 265961 |  | 220KV-KHANDWA-OMKARESHWAR-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 14-10-2025 08:00:00 | 14-10-2025 18:00:00 |  |  | OK THROUGH SUB LD All other lines at Omkareshkar to be in service with AR enabled. No other element shall be effected. Load will be managed by SLDC MP. WR2 to be informed.
59 |  | 265931 |  | 400KV/220KV JABALPUR-ICT-2 |  | WR-OCCM | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 13-10-2025 09:00:00 | 14-10-2025 17:00:00 |  |  | REAL TIME SLDC MP consent is required. ICT-1 to be in service with complete did. Load to be managed by SLDC MP