## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-02 | APPROVED OUTAGE LIST FOR DATED 02.09.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | LINE END (IN CASE OF LINE) | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
39 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma |  | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK
12 | 2025-08-31 15:36 | MR2508/0439 | Continuous | 220KV_220kv Badnawar-Barnagar ckt-1 | 400KV_BADNAWAR | NON-OCCM-MP | For installation of double DPR |  | 01-09-2025 10:00:00 | 02-09-2025 18:00:00 | Waiting | Er. ABHISHEK VERMA | 9340855901 | CONTINUE
32 | 2025-09-01 15:48 | MR2509/0020 |  | 132KV_50MVA BHEL TRANSFORMER | 132KV_BANDA | NON-OCCM-MP | POSTMANSOON MAINTINANCE |  | 02-09-2025 10:00:00 | 02-09-2025 18:00:00 | Waiting | PD GAUTAM | 9425808329 | OK O&M TO BE INTIMATED
9 | 2025-09-01 15:20 | MR2509/0016 |  | 132KV_50MVA X-mer No.II | 132KV_BOREGAON | NON-OCCM-MP | Tandelta & Capacitance Measurment work |  | 02-09-2025 11:00:00 | 02-09-2025 17:00:00 | Waiting | Sanjay Shende | 9425811447 | OK O&M TO BE INTIMATED
7 | 2025-09-01 13:05 | MR2509/0009 |  | 220KV_220 KV Chhatarpur-Tikamgarh Bay | 220KV_CHATARPUR | NON-OCCM-MP | For Y &B Phase CT replacement work |  | 02-09-2025 09:00:00 | 02-09-2025 17:00:00 | Waiting | Brajendra Soni | 9131327770 | OK
6 | 2025-09-01 12:24 | MR2509/0006 |  | 132KV_40 MVA-I (ECE) X-mer | 400KV_CHHEGAON4 | NON-OCCM-MP | Post monsoon maintenance |  | 02-09-2025 10:00:00 | 02-09-2025 18:00:00 | Waiting | Shri Ganesh Mansare | 9425802441 | SUB LD
13 | 2025-09-01 15:58 | MR2509/0022 |  | 220KV_220 KV HOSHANGABAD- MANDIDEEP FEEDER | 220KV_HOSHANGABAD | NON-OCCM-MP | LBB TESTING WORK |  | 02-09-2025 15:00:00 | 02-09-2025 18:00:00 | Waiting | V.P.DWIVEDI | 9425804799 | OK THROUGH SUB LD, AFTER REVIVAL OF 220 KV ADAMPUR-HOSHANGABAD CKT
33 | 2025-09-01 15:54 | MR2509/0021 |  | 220KV_220 KV HOSHANGABAD- ADAMPUR FEEDER | 220KV_HOSHANGABAD | NON-OCCM-MP | LBB TESTING WORK |  | 02-09-2025 11:00:00 | 02-09-2025 14:00:00 | Waiting | V.P.DWIVEDI | 9425804799 | OK THROUGH SUB LD
4 | 2025-08-29 11:42 | MR2508/0399 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre |  | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED, COMMUNICATION CONFIRMATION REQUIRED
5 | 2025-08-30 10:24 | MR2508/0413 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 30-08-2025 07:00:00 | 03-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED, COMMUNICATION CONFIRMATION REQUIRED
3 | 2025-08-26 18:22 | MR2508/0354 | Continuous | 132KV_132 KV JBP-SAHPURA DP LINE | 220KV_JABALPUR | OCCM-MP | REPLACEMENT OF TOWER LOC NO 5 |  | 28-08-2025 10:00:00 | 02-09-2025 19:00:00 | Waiting | RAJESH TIWARI | 7898239595 | CONTINUE, EI APPROVAL REQUIRED PRIOR TO CHARGING
29 | 2025-09-01 15:59 | MR2509/0023 |  | 132KV_132 KV JBP-VFJ CKT2 | 220KV_JABALPUR | NON-OCCM-MP | REMOVAL OF JUMPER AT LOC NO18 TAP132KV VINOBA LINE | Both End | 02-09-2025 08:00:00 | 02-09-2025 12:00:00 | Waiting | RAJESH TIWARI | 7898239595 | OK, PRIOR TO CHARGING OF CKT-2 AFTER OPENING TAP ARRANGEMENT PROTECTION COORDINATION TO BE CONFIRMED BY T&C.
30 | 2025-09-01 16:00 | MR2509/0025 |  | 33KV_33KV Main Bus | 132KV_KATANGI | NON-OCCM-MP | to attend hot point and new bay connect to main bu |  | 02-09-2025 10:00:00 | 02-09-2025 12:00:00 | Waiting | Seema Dongre | 9425807247 | OK IF O&M CONSENTED
40 | 2025-09-01 15:59 | MR2509/0024 |  | 33KV_33KV Main Bus | 132KV_KATANGI | NON-OCCM-MP | to attend hot point and new bay connect to main bu |  | 02-09-2025 10:00:00 | 02-09-2025 12:00:00 | Waiting | Seema Dongre | 9425807247 | OK IF O&M CONSENTED
1 | 2025-06-30 16:15 | MR2506/0636 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK |  | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
2 | 2025-06-30 15:33 | MR2506/0626 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK |  | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
19 | 2025-09-01 13:22 | MR2509/0010 |  | 132KV_132KV Nagda-Unhel Line | 400KV_NAGDA4 | NON-OCCM-MP | Line Maintenance work. |  | 02-09-2025 10:00:00 | 02-09-2025 18:00:00 | Waiting | Kamal Solanki | 9425805262 | SUB LD
24 | 2025-09-01 15:46 | MR2509/0019 |  | 132KV_132/33 kv 63 MVA BBL X-MER no.I | 220KV_NARSINGHPUR | NON-OCCM-MP | post monsoon maintenance & relay replacement work |  | 02-09-2025 09:00:00 | 02-09-2025 18:00:00 | Waiting | Dinesh Kumar kushwaha | 9425801319 | OK, O&M TO BE INTIMATED
11 | 2025-09-01 11:41 | MR2509/0004 |  | 220KV_MANDSOUR4-NEEMUCH_Ckt_1 | 220KV_NEEMUCH | NON-OCCM-MP | DTPC carrier protection (FOTE) cable connecting | Both End | 02-09-2025 10:00:00 | 02-09-2025 14:00:00 | Waiting | Vivek Mojasia | 9425806921 | OK THROUGH SUB LD
22 | 2025-09-01 11:58 | MR2509/0005 |  | 220KV_220KV Neemuch - Mandsaur-II | 220KV_NEEMUCH | NON-OCCM-MP | DTPC carrier protection (FOTE) cable connecting |  | 02-09-2025 14:00:00 | 02-09-2025 17:00:00 | Waiting | Vivek Mojasia | 9425806921 | OK THROUGH SUB LD
36 | 2025-08-30 18:01 | MR2508/0423 |  | 220KV_220 Kv Nimrani Julwaniya Line | 220KV_NIMRANI | NON-OCCM-MP | DTPC Wiring work |  | 02-09-2025 11:00:00 | 02-09-2025 18:00:00 | Waiting | Pradip Patidar | 9425801217 | OK THROUGH SUB LD
37 | 2025-09-01 13:01 | MR2509/0007 |  | 132KV_132 KV BHEL X-MER | 132KV_PANNA | NON-OCCM-MP |  |  | 02-09-2025 11:00:00 | 02-09-2025 14:00:00 | Waiting | RN UPADHYAY | 9425802349 | OK, O&M TO BE INTIMATED, X'MER MVA TO BE MENTIONED
38 | 2025-09-01 14:18 | MR2509/0012 |  | 132KV_132KV PATERA AMANGANJ (JK CEMENT)LINE | 132KV_PATERA | NON-OCCM-MP | ERS TOWER INSTALLATION WORK |  | 02-09-2025 11:00:00 | 02-09-2025 14:00:00 | Waiting | PANKAJ YADAV | 9406713326 | OK, TIME LINE SHALL STRICTLY BE ADHERED
31 | 2025-09-01 15:28 | MR2509/0017 |  | 132KV_132 KV 50 MVA (TAL ) | 132KV_PHOOLBAGH GIS | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK |  | 02-09-2025 10:00:00 | 02-09-2025 17:00:00 | Waiting | RAKSHA CHAPARIYA | 6265080313 | SUB LD
8 | 2025-09-01 14:21 | MR2509/0013 |  | 220KV_160MVA Xmer-II BBL | 220KV_SABALGARH | NON-OCCM-MP | Post monsoon Maintenance |  | 02-09-2025 10:00:00 | 02-09-2025 18:00:00 | Waiting | D D Mahour | 9425805742 | OK THROUGH SUB LD
25 | 2025-08-30 17:14 | MR2508/0421 |  | 132KV_SARNI UMRETH | 220KV_SARNI | NON-OCCM-MP | Flash over disc replacement & other line maint. wo |  | 02-09-2025 09:00:00 | 02-09-2025 17:00:00 | Waiting | SHIV KUMAR | 9425806917 | SUB LD
20 | 2025-09-01 15:12 | MR2509/0015 |  | 220KV_220 kv Satna (PGCIL) -Satna ckt -Ist | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | Both End | 02-09-2025 10:00:00 | 02-09-2025 13:00:00 | Waiting | Mr. RK.Prajapati | 9407070182 | OK
23 | 2025-09-01 15:07 | MR2509/0014 |  | 220KV_220 kV Birsingpur TPS-Shahdol Circuit | 220KV_SHAHDOL | NON-OCCM-MP | A planned essential shutdown on following line is |  | 02-09-2025 10:00:00 | 02-09-2025 17:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK
26 | 2025-08-31 18:00 | MR2508/0442 |  | 220KV_160 MVA X-MER-I | 400KV_UJJAIN4 | NON-OCCM-MP | Transformer testing & bay maint.work |  | 02-09-2025 10:00:00 | 02-09-2025 17:00:00 | Waiting | Mr.Santosh Chavrasia | 9425804677 | OK THROUGH SUB LD
28 | 2025-09-01 13:05 | MR2509/0008 |  | 220KV_220KV BHOPAL GCB | 220KV_VIDISHA | OCCM-MP | FOR DPR MAIN-2 RELAY TESTING WORK |  | 02-09-2025 10:00:00 | 02-09-2025 17:00:00 | Waiting | K.C. GOSWAMI | 9425804976 | OK THROUGH SUB LD. LINE TO BE IN SERVICE THROUGH TBC,
35 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE |  | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | Waiting | RAJESH TIWARI | 7898239595 | OK, AFTER LOAD MANAGEMENT AT 33KV. PRIOR TO CHARGING OF 132KV JBP-VFJ CKT-2 AFTER OPENING TAP ARRANGEMENT PROTECTION COORDINATION TO BE CONFIRMED BY T&C.
|  |  |  | 220KV-ANNUPUR-KOTMIKALA-2 |  |  | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 |  | 02-Sep-2025 | 08:00 | 02-Sep-2025 | 17:59 |  | OK
|  |  |  | 400KV-SATPURA-ITARSI-1 |  |  | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) AND CT Oil sampling at Itarsi And CVT Replacement of 400KV-SATPURA-ITARSI-1 under ADD CAP at MPGENCO |  | 02-Sep-2025 | 09:00 | 05-Sep-2025 | 20:00 |  | OK THROUGH SUB LD
|  |  |  | SATPURA - 400KV - BUS 1 |  |  | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-ITARSI-1 is required) |  | 02-Sep-2025 | 09:00 | 05-Sep-2025 | 20:00 |  | OK THROUGH SUB LD
S/I SLDC JABALPUR