## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-07
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-05 15:27 | MR2508/0067 |  | 400KV_315 MVA X-MER-3 | 400KV_BHOPAL4 | NON-OCCM-MP | To attend DC Leakage | 07-08-2025 10:00:00 | 07-08-2025 18:00:00 | AKRAM KHAN | 9425804695 | ok, through sub ld
2 | 2025-08-01 17:06 | MR2508/0013 | Continuous | 400KV_400 kV TIE CB of 315 MVA X-mer-II (BHEL) | 400KV_BINA4 | NON-OCCM-MP | Replacement of C&R panel of 400 kV TIE CB | 04-08-2025 09:00:00 | 08-08-2025 17:00:00 | Parmanand namdeo | 7587951092 | Continuous
3 | 2025-08-04 15:44 | MR2508/0045 |  | 220KV_220 kV Khandwa (PGCIL)-Chhanera Ckt 2nd | 220KV_CHANERA | OCCM-MP | For Line Maintenance work | 07-08-2025 08:00:00 | 07-08-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, through sub ld
4 | 2025-08-06 14:22 | MR2508/0084 |  | 40MVA_132/33KV_BBL_X'mer_1 | 220KV_CHHINDWARA | NON-OCCM-MP | 33KV Incomer CB to Isolator Jumper replacement . | 07-08-2025 10:00:00 | 07-08-2025 12:00:00 | A A Qureshi | 9425804318 | ok
5 | 2025-08-06 12:51 | MR2508/0080 |  | 132KV_132KV Chourai-Chhindwara feeder. | 132KV_CHOURAI | NON-OCCM-MP | CT Tan delta & capacitance measurement work. | 07-08-2025 10:00:00 | 07-08-2025 13:00:00 | S.K.Okte | 7587951132 | ok
6 | 2025-08-06 13:17 | MR2508/0082 |  | 132KV_132KV Chourai- Seoni feeder | 132KV_CHOURAI | NON-OCCM-MP | CT tan delta & capacitance measurement work. | 07-08-2025 14:00:00 | 07-08-2025 17:00:00 | S.K.Okte | 7587951132 | ok
7 | 2025-08-06 14:55 | MR2508/0086 |  | 132KV_132KV DAMOH-HATTA LINE | 132KV_DAMOH1 | NON-OCCM-MP | Line maintenance work | 07-08-2025 11:00:00 | 07-08-2025 17:00:00 | J.P. Asati | 9424445533 | as opportunity s/d
8 | 2025-08-06 13:04 | MR2508/0081 |  | 132KV_132KV Damoh-Hatta Line | 132KV_DAMOH1 | NON-OCCM-MP | 132KV RYB phase LA replacement work both end | 07-08-2025 11:00:00 | 07-08-2025 17:00:00 | Sh. B.K. Sahu | 9425801433 | ok
9 | 2025-08-06 12:12 | MR2508/0079 |  | 220KV_160 MVAX-MER -II MAKE BBL | 220KV_GANJBASODA | NON-OCCM-MP | LBB RELAY TESTING WORK | 07-08-2025 11:00:00 | 07-08-2025 15:00:00 | P K VERMA | 8253003873 | ok, through sub ld
10 | 2025-07-29 10:54 | MR2507/0453 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service, no data interruption shall occur
11 | 2025-08-06 13:52 | MR2508/0083 |  | 132KV_JULWANIYA4-ANJAD_Ckt | 400KV_JULWANIYA4 | NON-OCCM-MP | R ph CT secondary terminal box oil leakage attend | 07-08-2025 11:00:00 | 07-08-2025 15:00:00 | Er. Mannalal Badole | 9131865464 | sub ld
12 | 2025-06-30 16:04 | MR2506/0631 | Continuous | 220KV_220KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 04-08-2025 09:00:00 | 09-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
13 | 2025-06-30 15:11 | MR2506/0622 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 04-08-2025 09:00:00 | 09-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
14 | 2025-08-06 15:10 | MR2508/0088 |  | 132KV_132kv IC Katni -1 feeder | 400KV_KATNI4 | NON-OCCM-MP | For replacement of old duplex C&R panel | 07-08-2025 10:00:00 | 07-08-2025 18:00:00 | SK Chaturvedi | 9425806938 | ok
15 | 2025-08-06 16:41 | MR2508/0095 |  | 132KV_63 MVA BBL XMER | 132KV_KHAJURAHO | NON-OCCM-MP | HOT POINT ATTENDING WORK | 07-08-2025 10:00:00 | 07-08-2025 13:00:00 | BRIJENDRA SONI | 9131327770 | ok
16 | 2025-08-06 16:02 | MR2508/0094 |  | 132KV_50MVA BBL MAKE Transformer | 132KV_KHIMLASA | NON-OCCM-MP | for Oil leakage Attending | 07-08-2025 10:00:00 | 07-08-2025 17:00:00 | P N NAMDEO | 7587951092 | ok
17 | 2025-08-06 15:43 | MR2508/0092 |  | 220KV_160 MVA X-MER AREVA | 220KV_KOTAR | OCCM-MP | OLTC OPERATING ROD GEAR MAINTENANCE WORK | 07-08-2025 10:00:00 | 07-08-2025 13:00:00 | ER. ARUN KUMAR KOL | 8319677721 | ok
18 | 2025-08-04 15:34 | MR2508/0043 | Continuous | 400KV_125MVAR BUS REACTOR | 400KV_MANDSOUR4 | OCCM-MP | 400KV MAIN BUS-1&2 BUS CVT KEPT OFF | 05-08-2025 09:00:00 | 08-08-2025 18:00:00 | RAJESH BHURIA | 9425806920 | as per the voltage profile
19 | 2025-07-29 10:59 | MR2507/0454 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | for replacement existing of 24 Fibre OPGW by 48 Fi | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service, no data interruption shall occur
20 | 2025-08-06 15:46 | MR2508/0093 |  | 220KV_220KV MORENA- MALANPUR Ist | 220KV_MORENA | NON-OCCM-MP | Post Monsoon And Relay Testing Work | 07-08-2025 12:00:00 | 07-08-2025 16:00:00 | AMIT KUMAR DHANELIYA | 9425802242 | ok, through sub ld
21 | 2025-08-06 15:10 | MR2508/0089 |  | 132KV_132/33KV 40MVA X-mer-2 Make-BBL | 132KV_NAINPUR | NON-OCCM-MP | HV Side R&Y CT Replacement work | 07-08-2025 10:00:00 | 07-08-2025 18:00:00 | shri Mitthanlal kulesh | 9424316542 | ok
22 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
23 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
24 | 2025-08-05 17:01 | MR2508/0071 |  | 400KV_Rajgarh (PGCIL) to SSP CKT-1 | 400KV_RAJGARH-PG | OCCM-MP | For line maintenance work | 07-08-2025 10:00:00 | 07-08-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
25 | 2025-08-06 15:19 | MR2508/0091 |  | 220KV_220 kv Ratlam -Nagra Ckt-II both end | 220KV_RATLAM | NON-OCCM-MP | For testing Of Carrier Protection throue opgw (DTP | 07-08-2025 10:00:00 | 07-08-2025 13:00:00 | NIKHIL DUNGE | 9425801487 | ok, through sub ld
26 | 2025-08-06 16:43 | MR2508/0096 |  | 132KV_132KV MAIN BUS | 132KV_SATNA1 | NON-OCCM-MP | For opening of main bus isolator jumper for its re | 07-08-2025 13:00:00 | 07-08-2025 15:00:00 | Vishal baladhare | 9425804690 | o&m consent required
27 | 2025-07-23 17:35 | MR2507/0376 | Continuous | 400KV_Interconnecting Transformer-II 400KV/220KV | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of ICT-II | 04-08-2025 09:30:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | Continuous
28 | 2025-08-01 18:48 | MR2508/0015 | Continuous | 400KV_90 MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of Station Transformer-2 | 04-08-2025 09:00:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | Continuous
29 | 2025-07-26 15:04 | MR2507/0424 |  | 220KV_220KV Bus-coupler | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay testing,CT testing,CVT testing | 07-08-2025 10:00:00 | 07-08-2025 19:00:00 | Deepak Sharma | 8005696855 | Deffered, shall be availed after normalisation of ICT-II
30 | 2025-08-06 11:00 | MR2508/0078 |  | 400KV_400kV Ujjain -Nagda ckt.Ist | 400KV_UJJAIN4 | NON-OCCM-MP | Fote panel wrining and commissioning work | 07-08-2025 11:00:00 | 07-08-2025 14:00:00 | Shri Santosh chavrasia | 9425804677 | ok, through sub ld
31 |  |  |  | 132 KV NARSINGHPUR SHRINAGAR DP LINE |  |  | MODIFICATION / SHIFTING AT LOC 447 & 448 | 07.08.2025 08:00 | 09.08.2025 18:00 |  |  | OK CHARGING AT ELECTRICAL INSPECTOR PERMISION DURING CHARGING
32 |  |  |  | 400 KV BIRSINGHPUR KATNI - II ( BAY 406 ) | SGTPS |  | MAINTEN. WORK | 07.08.2025 09:00 | 07.08.2025 18:00 |  |  | OK
33 |  | 256947 | Daily | 400KV-SSP-RAJGARH-1 | 400 | MP_SLDC | FOR LINE MAINTENANCE WORK | 07-Aug-2025 | 08:00 | 07-Aug-2025 | 18:00 | ok, through sub ld
34 |  | 256965 | Daily | 220KV-KHANDWA-CHHANERA-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 07-Aug-2025 | 08:00 | 07-Aug-2025 | 18:00 | ok, through sub ld
35 |  | 256966 | Daily | 220KV-MORENA-SABALGARH-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 07-Aug-2025 | 09:00 | 07-Aug-2025 | 17:00 | real time
36 |  | 259141 | Daily | MANDSAUR-MP - 400KV - BUS 2 | 400 | MP_SLDC | for isolator alignment work, bus extension and high bus overhead stringing work for installation of new 500MVA ICT | 07-Aug-2025 | 08:00 | 07-Aug-2025 | 17:59 | ok, through sub ld
37 |  | 259201 | Daily | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 07-Aug-2025 | 07:00 | 07-Aug-2025 | 18:59 | ok