## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-10 |  |  | APPROVED OUTAGE LIST FOR DATED 10.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-29 10:54 | MR2507/0453 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
2 | 2025-08-09 15:15 | MR2508/0125 | Continuous | 400KV_400 KV auxiliary BUS | 400KV_MANDSOUR4 | NON-OCCM-MP | New Bus section stringing | 09-08-2025 16:00:00 | 11-08-2025 18:00:00 | jay prakash parmar | 9425806919 | ok, through sub ld
3 | 2025-07-29 10:59 | MR2507/0454 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | for replacement existing of 24 Fibre OPGW by 48 Fi | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
4 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
5 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
6 | 2025-08-09 14:30 | MR2508/0124 |  | 132KV_132KV Rajmilan-Waidhan ckt | 132KV_RAJMILAN | NON-OCCM-MP | Flash over disc replacemaent | 10-08-2025 11:00:00 | 10-08-2025 16:00:00 | G.L SAHU | 9425805102 | ok
7 | 2025-08-07 13:20 | MR2508/0107 | Continuous | 400KV_500 MVA, 400/220 kV ICT | 400KV_SGTPS | NON-OCCM-MP | Testing of NR, DCRM of Bkr, CT testing, aircell re | 08-08-2025 08:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | continuous
8 | 2025-08-08 16:06 | MR2508/0121 | Continuous | 400KV_63MVA, 400/11&6.6 kV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM of Bkr, CT testing, Aircell rep | 09-08-2025 09:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | continuous
9 | 2025-07-23 17:35 | MR2507/0376 | Continuous | 400KV_Interconnecting Transformer-II 400KV/220KV | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of ICT-II | 04-08-2025 09:30:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | continuous
10 | 2025-08-01 18:48 | MR2508/0015 | Continuous | 400KV_90 MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of Station Transformer-2 | 04-08-2025 09:00:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | continuous
S/I SLDC JABALPUR