## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-27 |  |  | APPROVED OUTAGE LIST FOR DATED 27.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-26 12:57 | MR2508/0342 |  | 220KV_220 kV Anuppur-Kotmikala Circuit II | 220KV_ANUPPUR | OCCM-MP | For line maintanance work | 27-08-2025 09:00:00 | 27-08-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-08-26 15:43 | MR2508/0347 |  | 220KV_220kV Ashta Mungliyachhap | 400KV_ASHTA4 | NON-OCCM-MP | measurement of tan delta & capacitance of 220kV Ct | 27-08-2025 09:00:00 | 27-08-2025 12:00:00 | Jitendra Lohana | 9425804978 | ok, through sub ld
3 | 2025-08-26 15:44 | MR2508/0348 |  | 220KV_220KV Ashta Bairagarh | 400KV_ASHTA4 | NON-OCCM-MP | measurement of tan delta & capacitance of 220kV Ct | 27-08-2025 13:00:00 | 27-08-2025 16:00:00 | Jitendra Lohana | 9425804978 | ok, through sub ld
4 | 2025-08-26 15:03 | MR2508/0346 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt. IInd Line | 220KV_CHATARPUR | NON-OCCM-MP | Slip VD Removal, AH tightening | 27-08-2025 10:00:00 | 27-08-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
5 | 2025-08-26 14:47 | MR2508/0345 |  | 220KV_220KV ITARSI-HANDIA CKT-II | 220KV_HANDIYA | NON-OCCM-MP | F/O DISC REPLACEMENT WORK | 27-08-2025 10:00:00 | 27-08-2025 17:00:00 | R.N PARTE | 9425804701 | ok, through sub ld
6 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
7 | 2025-08-26 13:04 | MR2508/0343 |  | 132KV_132 KV katni sleemnabad ckt 2 | 132KV_KATNI | NON-OCCM-MP | For modification shifting & maintenance work . | 27-08-2025 08:00:00 | 27-08-2025 12:00:00 | pankaj yadav | 9406713326 | ok
8 | 2025-08-26 13:09 | MR2508/0344 |  | 132KV_132 kv katni panagar line | 132KV_KATNI | NON-OCCM-MP | For modification shifting & maintenance work . | 27-08-2025 12:00:00 | 27-08-2025 18:00:00 | pankaj yadav | 9406713326 | ok
9 | 2025-06-30 15:28 | MR2506/0625 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENTHENING WORK | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
10 | 2025-06-30 16:11 | MR2506/0634 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
11 | 2025-08-26 17:02 | MR2508/0351 |  | 220KV_220kv 160MVA Xmer-ll CGL | 220KV_MALANPUR | NON-OCCM-MP | HV Side R Phase Bushing Jumper Replacement work | 27-08-2025 10:00:00 | 27-08-2025 17:00:00 | Vikram Ahirwar | 9425805415 | ok, through sub ld
12 | 2025-08-25 16:01 | MR2508/0337 |  | 400KV_400 KV Main Bus-1st at 400 Mandsaur | 400KV_MANDSOUR4 | NON-OCCM-MP | Jampar work | 27-08-2025 10:00:00 | 27-08-2025 18:00:00 | J.P. Parmar | 9425806919 | not approved in WRPC
13 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
14 | 2025-08-26 16:52 | MR2508/0350 |  | 400KV_400kV Bus tie | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tan delta testing | 27-08-2025 14:00:00 | 27-08-2025 16:00:00 | Sh. Rajudash bairagi | 9425801532 | separate bus operation not permitted, all elements to be on same bus
15 | 2025-08-26 10:40 | MR2508/0340 |  | 220KV_220 KV Bus Bar Panel | 400KV_SGTPS | NON-OCCM-MP | 220 KV Bus Bar Panel for Checking, Servicing and T | 27-08-2025 09:00:00 | 27-08-2025 18:00:00 | KIRAN SINGH | 9425826084 | ok, both the buses to be in service
16 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-2 | MADHYA PRADESH,CHATTISGARH |  | FOR LINE MAINTENANCE WORK | 27-Aug-2025 | 09:00 | 27-Aug-2025 | 18:00 | ok
17 |  |  |  | 220KV-REWA-SINDHI-MP-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK ( REWA RUMS) | 27-Aug-2025 | 10:00 | 27-Aug-2025 | 17:00 | real time
18 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 27-Aug-2025 | 07:00 | 27-Aug-2025 | 18:59 | ok
S/I SLDC JABALPUR