## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-12 | APPROVED OUTAGE LIST FOR DATED 12.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | LINE END (IN CASE OF LINE) | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 11:54 | MR2510/0055 | Daily | 220KV_220 kV Adampur-Hoshangabd line | 220KV_ADAMPUR | NON-OCCM-MP | Defective disc replacement work |  | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Waiting | Ankit Mehroliya | 9425804506 | OK THROUGH SUB LD
2 | 2025-10-11 15:32 | MR2510/0319 |  | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | Safety purpose for 63MVA TAL X-mer erection work |  | 12-10-2025 10:00:00 | 12-10-2025 17:00:00 | Waiting | Vishal Kumar Malviya | 9425804955 | SUB LD
3 | 2025-10-11 14:58 | MR2510/0316 |  | 132KV_132 KV Bina-Ashoknagar Ckt | 220KV_BINA | NON-OCCM-MP | Shutdown for line maintenance work |  | 12-10-2025 10:00:00 | 12-10-2025 18:00:00 | Waiting | Sanjay Singh Thakur | 9425806936 | SUB LS
4 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work |  | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
5 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work |  | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
6 | 2025-10-11 14:33 | MR2510/0315 |  | 132KV_132KV ANUPPUR-DONGRITAL CKT | 132KV_DONGRITAL | NON-OCCM-MP | DISC REPLACEMENT WORK |  | 12-10-2025 08:30:00 | 12-10-2025 17:00:00 | Waiting | G.L SAHU | 9425805102 | OK
7 | 2025-10-10 15:37 | MR2510/0299 |  | 132KV_132 KV MAIN BUS | 220KV_GWALIOR-II | NON-OCCM-MP | TO ATTEND HOT POINT |  | 12-10-2025 10:00:00 | 12-10-2025 14:00:00 | Waiting | R.C. ARORA | 9425805108 | OK, THROUGH SUB LD
8 | 2025-10-10 11:49 | MR2510/0277 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 78-94 |  | 11-10-2025 09:00:00 | 14-10-2025 17:00:00 | Waiting | Ashutosh Rai | 9425806902 | OK AS AN OPPURTUNITY SD
9 | 2025-10-11 14:24 | MR2510/0313 |  | 132KV_40MVA Transformer BBL | 132KV_JOBAT | NON-OCCM-MP | Post monsoon maintenance work |  | 12-10-2025 11:00:00 | 12-10-2025 16:00:00 | Waiting | Manoj Randha | 9425820034 | SUB LD
10 | 2025-10-11 14:26 | MR2510/0314 |  | 132KV_132kV Kukshi-Jobat line | 132KV_JOBAT | NON-OCCM-MP | Post monsoon maintenance work |  | 12-10-2025 11:00:00 | 12-10-2025 16:00:00 | Waiting | Manoj Randha | 9425820034 | SUB LD
11 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work |  | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Waiting | Gaurav goyal | 9425805120 | SUB LD
12 | 2025-10-11 16:36 | MR2510/0321 |  | 132KV_AMLA MULTAI | 132KV_MULTAI | NON-OCCM-MP | BIRD GUARD INSTALLATION WORK |  | 12-10-2025 11:00:00 | 12-10-2025 14:00:00 | Waiting | SHIV KUMAR | 9425806917 | SUB LD
13 | 2025-10-11 16:39 | MR2510/0322 |  | 132KV_BETUL MULTAI | 132KV_MULTAI | NON-OCCM-MP | BIRD GUARD INSTALLATION WORK |  | 12-10-2025 11:00:00 | 12-10-2025 14:00:00 | Waiting | SHIV KUMAR | 9425806917 | SUB LD
14 | 2025-10-11 10:25 | MR2510/0305 |  | 132KV_50 mva x-mer | 132KV_MYANA | NON-OCCM-MP | post mansoon |  | 12-10-2025 10:00:00 | 12-10-2025 17:00:00 | Waiting | rakesh suman | 7587951093 | SUB LD
15 | 2025-10-11 12:37 | MR2510/0308 |  | 132KV_132KV Guna Myana Line | 132KV_MYANA | NON-OCCM-MP | Line maint.work |  | 12-10-2025 10:00:00 | 12-10-2025 17:00:00 | Waiting | Akhilesh Singh | 8586865656 | SUB LD
16 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. |  | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
17 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. |  | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | Waiting | G.L Sahu | 9425805102 | DATA CONFIRMATION REQUIRED FROM COMMUNICATION
18 | 2025-10-11 10:48 | MR2510/0307 |  | 132KV_40 MVA X-MER IMP MAKE | 132KV_SALAMATPUR | OCCM-MP | POST MONSOON MAINTENANCE |  | 12-10-2025 09:00:00 | 12-10-2025 16:00:00 | Waiting | R.K. SARATHE | 9340166077 | SUB LD
19 | 2025-10-11 13:21 | MR2510/0311 |  | 132KV_132kv Sheopur Beerpur TBCB Ckt | 132KV_SHEOPUR KALAN | NON-OCCM-MP | Line Mainenance work |  | 12-10-2025 09:31:00 | 12-10-2025 18:30:00 | Waiting | SURAJ PAWAR | 9425814079 | SUB LD
20 | 2025-10-11 15:48 | MR2510/0320 |  | 132KV_132 KV Main Bus | 220KV_SIDHI | NON-OCCM-MP | Main bus to Isolator Jumpering work |  | 12-10-2025 11:00:00 | 12-10-2025 16:00:00 | Waiting | JAGAT NARAYAN SINGH | 9425802388 | OK , TIMING SHOULD BE FOLLOW FROM 11:00 HRS TO 15:00 HRS
21 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER |  | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Accepted | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
22 |  |  |  | 132KV-PENCH-MP-KANHAN-1 | WR |  | s/s required for faulty CVT replacement and overhauling of Ckt breaker |  | 11-Oct-2025 | 09:00 | 12-Oct-2025 | 17:59 |  | ok
S/I SLDC JABALPUR