## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-22 | APPROVED OUTAGE LIST FOR DATED 22.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-21 11:52 | MR2510/0496 |  | 132KV_40MVA BBL X-mer | 132KV_AMARPATAN | NON-OCCM-MP | Differential relay replacement work | 22-10-2025 10:00:00 | 22-10-2025 20:00:00 | ARUN KUMAR KOL | 9425802368 | o&m consent required
2 | 2025-10-21 12:46 | MR2510/0499 |  | 220KV_220 kV Interconnector 2 from Bus Transfer bay to main CB | 220KV_BHOPAL | NON-OCCM-WR | replacement of damaged overhead Conductor | 22-10-2025 08:00:00 | 22-10-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
3 | 2025-10-21 12:54 | MR2510/0500 | Continuous | 220KV_Transfer the Load of 220 kV Interconnector 2 line on Bus Transfer | 220KV_BHOPAL | NON-OCCM-WR | main CB of 220 kV Interconnector 2 line is not rel | 22-10-2025 17:00:00 | 24-10-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
4 | 2025-10-21 12:25 | MR2510/0497 |  | 220KV_200 MVA Transformer | 220KV_BHOPAL | NON-OCCM-WR | replacement damaged overhead Conductor | 22-10-2025 08:00:00 | 22-10-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
5 | 2025-10-21 12:44 | MR2510/0498 |  | 220KV_220 KV Aux. bus | 220KV_BHOPAL | NON-OCCM-WR | replacement of damaged overhead Conductor | 22-10-2025 08:00:00 | 22-10-2025 17:00:00 | A. K. Jain | 9425806899 | ok, through sub ld
6 | 2025-10-21 14:14 | MR2510/0503 |  | 220KV_220 KV Bina-Sagar Ckt-2 | 400KV_BINA4 | NON-OCCM-MP | For f/o disc replacement & other line maint. | 22-10-2025 10:00:00 | 22-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
7 | 2025-10-21 13:04 | MR2510/0501 |  | 400KV_80MVAR Guna-2 Line Reactor | 400KV_BINA4 | NON-OCCM-MP | Post Monsoon Maintenance wprk. | 22-10-2025 09:00:00 | 22-10-2025 14:00:00 | Mr.P.N. Namdeo | 7587951092 | ok
8 | 2025-09-18 17:24 | MR2509/0455 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
9 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
11 | 2025-09-18 13:08 | MR2509/0413 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 22-10-2025 09:00:00 | 25-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
12 | 2025-10-21 14:00 | MR2510/0502 |  | 220KV_160 mva x-mer make BHEL-02 | 220KV_NALKHEDA | NON-OCCM-WR | HV SIDE BREAKER B-PHASE POLE MECHANISM PRO. RECTIF | 22-10-2025 11:00:00 | 22-10-2025 17:00:00 | VK Gupta | 9425801214 | ok, through sub ld
13 | 2025-10-21 11:19 | MR2510/0493 |  | 132KV_132 kv Panagar Katangi | 220KV_PANAGAR | NON-OCCM-MP | For installation of ERS in modification work | 22-10-2025 10:00:00 | 22-10-2025 18:00:00 | pankaj Yadav | 9406713326 | provide the details of work to be done
14 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
15 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
16 | 2025-10-21 11:35 | MR2510/0495 |  | 160MVA_220/132KV_IMP_X'mer | 220KV_SIRMOUR | NON-OCCM-MP | Post Monsoon & Testing Work | 22-10-2025 10:00:00 | 22-10-2025 17:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
17 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
18 |  |  |  | 400KV/132KV VINDHYACHAL-ICT-3 | NTPC |  | Annual Bay Maintenance and Testing/ Relay testing | 22-Oct-2025 | 08:00 | 25-Oct-2025 | 18:00 | ok
19 |  |  |  | INDORE - 400KV - BUS 3 | POWERGRID-WR2 (PGCIL) |  | ICT 3 Erection & Commissioning work | 22-Oct-2025 | 09:00 | 30-Oct-2025 | 18:00 | ok
20 |  |  |  | 220KV-SEONI-PG-CHINDWARA-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 22-Oct-2025 | 09:00 | 22-Oct-2025 | 18:00 | real time
21 |  |  |  | 400KV/220KV SEONI-PG-ICT-2 | POWERGRID-WR1 (PGCIL) |  | AMP of ICT at Seoni S/s. | 22-Oct-2025 | 07:00 | 22-Oct-2025 | 18:00 | ok
S/I SLDC JABALPUR