## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-12
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-11 14:28 | MR2508/0144 |  | 132KV_132 kV Anuppur-Kotma Circuit I | 220KV_ANUPPUR | NON-OCCM-MP | For Broken disc replacement & other line maintanan | 12-08-2025 10:00:00 | 12-08-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
2 | 2025-08-07 11:22 | MR2508/0103 |  | 400KV_315 mva x-mer-3 | 400KV_BHOPAL4 | NON-OCCM-MP | To attend DC leakage | 12-08-2025 10:00:00 | 12-08-2025 18:00:00 | AKRAM KHAN | 9425804695 | ok, through sub ld
3 | 2025-08-11 14:22 | MR2508/0141 |  | 400KV_400KV Auxilary bus & 400KV bus transfer | 400KV_CHHEGAON4 | NON-OCCM-MP | 400KV Bus Transfer isolator spider replacement | 12-08-2025 10:30:00 | 12-08-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | ok, through sub ld
4 | 2025-08-11 14:24 | MR2508/0143 | Continuous | 132KV_132kv 50mva bbl-make transformer | 132KV_DIGODA | NON-OCCM-MP | Air, cell of main-conservator tank charged by bbl | 12-08-2025 10:00:00 | 13-08-2025 07:00:00 | Pushpendra kumar soni | 9425806398 | ok
5 | 2025-08-10 13:51 | MR2508/0131 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 11-08-2025 07:00:00 | 13-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
6 | 2025-08-11 14:01 | MR2508/0139 |  | 400KV_400 KV TBC Bay | 400KV_JULWANIYA4 | NON-OCCM-MP | for CT Tan delta measurement | 12-08-2025 10:00:00 | 12-08-2025 15:00:00 | ER. Ravindra Patil | 8305612190 | ok, through sub ld
7 | 2025-08-11 16:01 | MR2508/0150 |  | 33KV_33 kv Main bus | 132KV_KATANGI_JBP | NON-OCCM-MP | Hot point attend and maintenance work | 12-08-2025 10:00:00 | 12-08-2025 14:00:00 | A.K. Pandey | 9424645081 | ok, for x-mers
8 | 2025-06-30 15:17 | MR2506/0623 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-06-30 16:06 | MR2506/0632 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
10 | 2025-08-10 13:46 | MR2508/0130 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work | 11-08-2025 07:00:00 | 13-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
11 | 2025-08-11 15:35 | MR2508/0147 |  | 220KV_220 KV NARSINGHPUR-PIPARIYA LINE | 220KV_NARSINGHPUR | NON-OCCM-MP | HOT POINT ATTENDING WORK R PHASE ISOLATOR CLAMP | 12-08-2025 13:00:00 | 12-08-2025 16:00:00 | DINESH KUSHWAHA | 9425182413 | ok
12 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
13 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
14 | 2025-08-11 14:16 | MR2508/0140 |  | 220KV_220 KV INTER CONNECTOR-1 LINE | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | CT TEN DELTA MESSURMENT WORK | 12-08-2025 10:00:00 | 12-08-2025 14:00:00 | R.D.BAIRAGI | 9425801532 | real time
15 | 2025-08-10 17:45 | MR2508/0134 | Continuous | 132KV_132KV RAJMILAN-JANAKPUR (CGPTCL) CKT | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | ok, line will be normalised in the present configuration , SLDC CG to be informed
16 | 2025-08-10 17:51 | MR2508/0135 | Continuous | 132KV_132KV Rajmilan-Dongrital ckt | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | ok, line will be normalised in the present configuration
17 | 2025-08-11 15:54 | MR2508/0148 |  | 220KV_220 KV Rewa-Rewa (RUMS) Ckt-1 line | 220KV_REWA | NON-OCCM-WR | installation of broken OPGW | 12-08-2025 08:00:00 | 12-08-2025 18:00:00 | Mr. Ajay Kumar Chourasia | 9425805081 | send emergency proposal to WRLDC for approval
18 | 2025-08-08 19:36 | MR2508/0122 | Continuous | 400KV_50 MVA Station Transformer #11 | 400KV_SATPURA TPS | NON-OCCM-MP | For testing of transformer, bay equipment & P Rela | 11-08-2025 09:00:00 | 14-08-2025 18:00:00 | YASHWANT WARATHE | 9752778063 | Continuous
19 | 2025-08-07 13:20 | MR2508/0107 | Continuous | 400KV_500 MVA, 400/220 kV ICT | 400KV_SGTPS | NON-OCCM-MP | Testing of NR, DCRM of Bkr, CT testing, aircell re | 08-08-2025 08:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
20 | 2025-08-08 16:06 | MR2508/0121 | Continuous | 400KV_63MVA, 400/11&6.6 kV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM of Bkr, CT testing, Aircell rep | 09-08-2025 09:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
21 | 2025-08-11 15:57 | MR2508/0149 |  | 220KV_220 KV Sidhi-Rewa (RUMS) Ckt-1 | 220KV_SIDHI | NON-OCCM-WR | for installation of broken OPGW | 12-08-2025 08:00:00 | 12-08-2025 18:00:00 | Mr. Ajay Kumar Chourasia | 9425805081 | send emergency proposal to WRLDC for approval
22 | 2025-08-11 16:04 | MR2508/0151 |  | 132KV_132KV SIDHI-MAUGANJ CKT-II | 220KV_SIDHI | NON-OCCM-MP | Disc flash over replacement | 12-08-2025 10:00:00 | 12-08-2025 17:00:00 | G.L SAHU | 9425805102 | ok
23 |  |  |  | 220 KV NARSINGPUR SUKHA CIRCUIT 1 | 220 KV NARSINGPUR |  | LOAD SHIT TO BUS COUPLER FOR MAIN 2 DPR WIRING WORK | 12-08-2025 10:00:00 | 12-08-2025 17:00:00 |  |  | OK LINE TO BE IN SERVICE THROUGH TBC
24 |  | 256973 | Daily | 220KV-BETUL-SARNI-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 12-Aug-2025 | 09:00 | 12-Aug-2025 | 17:00 | ok, through sub ld
25 |  | 256974 | Daily | 220KV-KHANDWA-OMKARESHWAR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 12-Aug-2025 | 08:00 | 12-Aug-2025 | 18:00 | real time
26 |  | 259206 | Daily | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 12-Aug-2025 | 07:00 | 12-Aug-2025 | 18:59 | ok