## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-17 |  | APPROVED OUTAGE LIST FOR DATED 17.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-16 15:25 | MR2510/0472 |  | 132KV_132 kV Anuppur-Shahdol line | 220KV_ANUPPUR | NON-OCCM-MP | F/o disc replacement & other line maintenance | 17-10-2025 10:00:00 | 17-10-2025 17:00:00 | Jitendra Tiwari | 9425805298 | Deferred due to s/d on 160MVA at Anuppur
2 | 2025-10-16 12:27 | MR2510/0468 |  | 220KV_160MVA 220/132 BHEL X-MER | 220KV_ANUPPUR | NON-OCCM-MP | Hot Point (132KV sideY-Ph CT clamp Dropper Jumper) | 17-10-2025 09:00:00 | 17-10-2025 17:00:00 | Sunil Kumar Bhalavi | 9425804704 | ok
3 | 2025-10-16 13:38 | MR2510/0470 |  | 132KV_132KV Bhonra Raghogarh Line | 132KV_BHONRA | NON-OCCM-MP | For DF/O & line Maint. work | 17-10-2025 10:00:00 | 17-10-2025 17:00:00 | Akhilesh Singh | 8586865656 | sub ld
4 | 2025-10-16 15:47 | MR2510/0474 |  | 132KV_132 kv bijawar-Badamalehra ckt | 132KV_BIJAWAR | NON-OCCM-MP | for damaged conductor replacement work | 17-10-2025 11:00:00 | 17-10-2025 13:00:00 | Brajendra soni | 9131327770 | ok
5 | 2025-10-08 16:50 | MR2510/0241 |  | 400KV_400 kv main bus-2 | 400KV_BINA4 | NON-OCCM-MP | for stringing and extension of main bus-2 | 17-10-2025 09:00:00 | 17-10-2025 17:00:00 | Anil mahor | 9425805149 | Deferred, not approved in WRPC
6 | 2025-10-16 12:16 | MR2510/0467 |  | 132KV_132 kV Chhindwara Saori Ckt-II | 220KV_CHHINDWARA | NON-OCCM-MP | J/c,V/d,A/h tightening and F/o disc replacement wo | 17-10-2025 09:00:00 | 17-10-2025 13:00:00 | A.M.Shende | 7587951136 | ok, o&m shall be informed
7 | 2025-10-16 12:45 | MR2510/0469 |  | 132KV_132 kV Chhindwara Saori Ckt-I | 220KV_CHHINDWARA | NON-OCCM-MP | J/c,A/h,V/d tightening and F/o disc replace | 17-10-2025 14:00:00 | 17-10-2025 18:00:00 | A.M.Shende | 7587951136 | ok, o&m shall be informed
8 | 2025-09-18 17:20 | MR2509/0454 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
9 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
11 | 2025-10-14 12:30 | MR2510/0410 |  | 220KV_160 MVA BHEL XMER 220/132 KV | 220KV_HOSHANGABAD | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 17-10-2025 09:00:00 | 17-10-2025 17:00:00 | V.P.DWIVEDI | 9425804799 | ok, through sub ld
12 | 2025-10-15 11:40 | MR2510/0451 | Daily | 220KV_220 KV Itarsi-Handia II | 220KV_ITARSI | NON-OCCM-MP | Replacement of Single to Double dis insul.string | 16-10-2025 09:00:00 | 17-10-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
13 | 2025-09-18 13:00 | MR2509/0411 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
14 | 2025-10-15 16:45 | MR2510/0464 |  | 400KV_400KV Pithampur- Badnawar Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | for pad clamp replace on R- Phase Line side isolat | 17-10-2025 11:00:00 | 17-10-2025 16:00:00 | Shri Rajudas bairagi | 9425801532 | ok, through sub ld
15 | 2025-10-16 16:04 | MR2510/0477 | Daily | 220KV_160 MVA X MER 2ND BHEL | 220KV_RAJGARH (BIAORA) | NON-OCCM-MP | POST MANSOON MAITENANCE | 16-10-2025 00:00:00 | 17-10-2025 00:00:00 | NEELESH BASTRI | 9425305055 | ok, through sub ld
16 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
17 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
18 | 2025-10-16 15:35 | MR2510/0473 |  | 132KV_132/33 KV 40 MVA TELK X-MER 02 | 132KV_SIDHI1 | NON-OCCM-MP | FOR OIL TOPPING WORK | 17-10-2025 13:00:00 | 17-10-2025 15:00:00 | SHRI R B SINGH | 9907230394 | ok
19 | 2025-10-16 11:25 | MR2510/0465 |  | 220KV_220kV Tikamgarh â¿¿ Chhatarpur Line | 220KV_TIKAMGARH | NON-OCCM-MP | Slip AH/VD Removal & other Line maintenance work | 17-10-2025 10:00:00 | 17-10-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
20 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
21 |  |  |  | NHPTL-TESTING-of 100 MVA, 220 kV 3 ph Transformer | NHPTL |  | Expected short circuit current: 1.5 kA +/- 10% Expected fault current: 2.5 kA Time duration: 250 ms +/- 10% No. of shots to be taken: | 17-Oct-2025 | 0:00 | 17-Oct-2025 | 23:59 | ok, every instructions of WRLDC to be forwarded to JP BINA and MP BINA
22 |  |  |  | 220KV-MEHGAON-AURIYA-1 | NLDC,MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 17-Oct-2025 | 09:00 | 17-Oct-2025 | 17:00 | real time
23 |  |  |  | 220KV-KHANDWA-CHHEGAON-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 17-Oct-2025 | 08:00 | 17-Oct-2025 | 18:00 | real time
24 |  |  |  | 400KV/220KV SHUJALPUR-ICT-1 | POWERGRID-WR2 (PGCIL) |  | 315MVA,400/220kV ICT-I AT SHUJALPUR, Dia to be kept open at both sides | 17-Oct-2025 | 08:00 | 17-Oct-2025 | 17:30 | ok
S/I SLDC JABALPUR