## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-18 |  | APPROVED OUTAGE LIST FOR DATED 18.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-18 17:20 | MR2509/0454 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
2 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | Deffered
3 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | Deffered
4 | 2025-09-18 13:00 | MR2509/0411 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 13-10-2025 09:00:00 | 18-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
5 | 2025-10-17 15:52 | MR2510/0490 |  | 220KV_22O KV Nalkheda-2, Load on Bus coupler | 220KV_RAJGARH (BIAORA) | NON-OCCM-MP | Nalkheda damage CVT Replacement | 18-10-2025 10:00:00 | 18-10-2025 17:00:00 | Neelesh Bastri | 9425804342 | ok, line to be in service through TBC, through sub ld, shall be completed timely
6 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | Deffered
7 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | Deffered
8 | 2025-10-17 15:02 | MR2510/0489 |  | 220KV_Shutdown (H/T) of 220 kv Rewa-Tons line | 220KV_REWA | NON-OCCM-MP | Jumper cone tightening & other maintenance work | 18-10-2025 11:00:00 | 18-10-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok, shall be completed timely
9 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
10 |  |  |  | 220KV-SEONI-PG-CHINDWARA-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09:00 | 18-Oct-2025 | 18:00 | Daily | Deferred
S/I SLDC JABALPUR