## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-15
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-14 11:04 | MR2509/0305 |  | 220KV_220kV Ashta-Shajapur Ckt No-1 | 400KV_ASHTA4 | NON-OCCM-MP | measurement of tan delta & capacitance of 220kV Ct | 15-09-2025 09:00:00 | 15-09-2025 12:00:00 | Jitendra Lohana | 9425804978 | OK THROUGH SUB LD, 220kV Ashta-Shajapur Ckt No-2 TO BE IN SERVICE
3 | 2025-09-14 11:05 | MR2509/0306 |  | 220KV_220kV Ashta-Shajapur Ckt No-2 | 400KV_ASHTA4 | NON-OCCM-MP | measurement of tan delta & capacitance of 220kV Ct | 15-09-2025 13:00:00 | 15-09-2025 16:00:00 | Jitendra Lohana | 9425804978 | OK THROUGH SUB LD, 220kV Ashta-Shajapur Ckt No-1 TO BE IN SERVICE
4 | 2025-09-14 15:48 | MR2509/0324 |  | 220KV_220kV BADNAWAR-BARNAGAR CKT-1 | 400KV_BADNAWAR | NON-OCCM-MP | For installation OF double DPR | 15-09-2025 11:00:00 | 15-09-2025 17:00:00 | Er. ABHISHEK VERMA | 9340855901 | OK THROUGH SUB LD
5 | 2025-09-12 18:47 | MR2509/0294 | Continuous | 400KV_500 MVA X-MER NO.1(T&R) | 400KV_BHOPAL4 | NON-OCCM-MP | Post mansoon Maintence work | 15-09-2025 09:00:00 | 16-09-2025 18:00:00 | AKRAM KHAN | 9425804695 | OK THROUGH SUB LD
6 | 2025-09-14 11:41 | MR2509/0308 |  | 315MVA_400/220KV_CGL_X'mer_3 | 400KV_BINA4 | NON-OCCM-MP | post monsoon maintenance | 15-09-2025 09:00:00 | 15-09-2025 18:00:00 | P.N. NAMDEO | 9039472058 | DEFERRED DUE TO SD ON 500MVA ICT AT BHOPAL, SHALL BE RESCHEDULED FOR 17.09.2025
7 | 2025-09-14 13:00 | MR2509/0312 | Daily | 132KV_132 kV Shahdol-Birsinghpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For replacement of damaged OPGW | 15-09-2025 08:00:00 | 20-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK FOR 15.09.2025 DAILY BASIS SD
8 | 2025-09-14 12:41 | MR2509/0310 |  | 220KV_160 MVA IMP | 220KV_CHATARPUR | NON-OCCM-MP | Post monsoon maintenance | 15-09-2025 10:00:00 | 15-09-2025 18:00:00 | Brajendra Soni | 9131327770 | OK
9 | 2025-09-13 12:44 | MR2509/0297 |  | 220KV_220 kV Chhegaon - Nimrani Ckt 1st | 400KV_CHHEGAON4 | NON-OCCM-WR | For Jumper Tightening & Other Line Maintenance wor | 15-09-2025 09:00:00 | 15-09-2025 17:00:00 | C.H.Namdev | 9425802377 | OK THROUGH SUB LD
10 | 2025-09-13 16:33 | MR2509/0302 |  | 132KV_132 kV Chhindwara-Chourai | 220KV_CHHINDWARA | NON-OCCM-MP | Flash over disc replace and Bird guard provide | 15-09-2025 09:00:00 | 15-09-2025 17:00:00 | A.M.Shende | 7587951136 | OK O&M TO BE INTIMATED
11 | 2025-09-14 13:01 | MR2509/0313 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | For replacement of damaged OPGW | 15-09-2025 08:00:00 | 20-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK FOR 15.09.2025 DAILY BASIS SD
12 | 2025-09-07 13:02 | MR2509/0161 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-2 | 220KV_INDORE NORTH | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
13 | 2025-09-07 12:51 | MR2509/0159 | Daily | 132KV_132KV North Zone- Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
14 | 2025-09-07 12:45 | MR2509/0158 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
15 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | RESCHEDULED FRO 11.09.2025 TO 30.09.2025
16 | 2025-09-14 13:23 | MR2509/0314 |  | 132KV_132 kv katni panagar line | 132KV_KATNI | NON-OCCM-MP | For Modification shifting work . | 15-09-2025 09:00:00 | 15-09-2025 18:00:00 | pankaj yadav | 9406713326 | OK
17 | 2025-09-14 12:19 | MR2509/0309 |  | 132KV_40 MVA BBL X-mer | 220KV_MAIHAR | NON-OCCM-MP | For post monsoon maint.& testing work. | 15-09-2025 10:00:00 | 15-09-2025 17:00:00 | ARUN KUMAR KOL | 9425802368 | OK
18 | 2025-09-14 15:11 | MR2509/0321 |  | 132KV_50MVA TRANSFORMER BBL | 132KV_MEGHNAGAR | NON-OCCM-MP | For post monsoon maintenance work | 15-09-2025 10:00:00 | 15-09-2025 18:00:00 | Er Kamesh ninama | 9713485920 | SUB LD
19 | 2025-09-14 15:11 | MR2509/0322 |  | 132KV_50MVA TRANSFORMER BBL | 132KV_MEGHNAGAR | NON-OCCM-MP | For post monsoon maintenance work | 15-09-2025 10:00:00 | 15-09-2025 18:00:00 | Er Kamesh ninama | 9713485920 | SUB LD
20 | 2025-09-14 15:16 | MR2509/0323 |  | 160MVA_220/132KV_BBL_X'mer_2 | 220KV_MEHGAON | NON-OCCM-MP | post monsoon maintenance | 15-09-2025 10:30:00 | 15-09-2025 17:00:00 | ASHEESH KUMAR | 8319926224 | OK THROUGH SUB LD
21 | 2025-09-14 11:40 | MR2509/0307 |  | 220KV_200 MVA CGPISL TRANSFORMER | 220KV_NAGDA | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK | 15-09-2025 09:30:00 | 15-09-2025 17:00:00 | VIKRAM DEHARIYA | 7000276050 | OK THROUGH SUB LD
22 | 2025-09-14 15:06 | MR2509/0320 |  | 132KV_50 MVA 132/33KV BHEL X-MER | 132KV_NARSINGHPUR1 | NON-OCCM-MP | Post Monsoon Maintenance work | 15-09-2025 10:00:00 | 15-09-2025 17:00:00 | Rajesh Kumar Chaturvedi | 9425805203 | OK
23 | 2025-09-07 12:39 | MR2509/0157 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line. | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
24 | 2025-09-07 12:57 | MR2509/0160 | Daily | 132KV_132KV Niranjanpur - Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 11-09-2025 07:00:00 | 30-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
25 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
26 | 2025-09-14 13:30 | MR2509/0315 |  | 132KV_132/33KV 40MVA X-MER BBL | 132KV_PATAN | NON-OCCM-MP | POST MONSOON MAINTENANCE, LV SIDE CT REPLACEMENT | 15-09-2025 09:00:00 | 15-09-2025 18:00:00 | RAHUL GAJBHIYE | 9425801304 | REPETED ENTRY
27 | 2025-09-14 13:30 | MR2509/0316 |  | 132KV_132/33KV 40MVA X-MER BBL | 132KV_PATAN | NON-OCCM-MP | POST MONSOON MAINTENANCE, LV SIDE CT REPLACEMENT | 15-09-2025 09:00:00 | 15-09-2025 18:00:00 | RAHUL GAJBHIYE | 9425801304 | OK
28 | 2025-09-14 14:10 | MR2509/0317 |  | 220KV_200MVA X-MER NO.I (CG POWER) | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-WR | POST MONSOON MAINT WORK | 15-09-2025 10:00:00 | 15-09-2025 17:00:00 | RAJU DAS BAIRAGI | 9425801532 | OK THROUGH SUB LD
29 | 2025-08-20 17:33 | MR2508/0262 |  | 400KV_400kV Pithampur-PGCIL Indore ckt-I | 400KV_PITHAMPUR4 | OCCM-MP | Tan delta testing & bay maintenance work | 15-09-2025 10:00:00 | 15-09-2025 17:00:00 | Sh. Rajudash bairagi | 9425801532 | RESCHEDULED FOR 23.09.2025
30 | 2025-09-14 09:00 | MR2509/0303 |  | 132KV_132KV Rajgarh - Raghogarh Line | 132KV_RAGHOGARH | NON-OCCM-MP | For DF/O replacement & other line maint. work | 15-09-2025 09:00:00 | 15-09-2025 18:00:00 | Akhilesh Singh | 8986865656 | SUB LD
31 | 2025-09-11 12:24 | MR2509/0255 |  | 400KV_Rajgarh (PGCIL)-SSP CKT-2 | 400KV_RAJGARH-PG | OCCM-MP | for line maintenance work | 15-09-2025 08:00:00 | 15-09-2025 18:00:00 | V.R. Panadia | 9425802330 | OK THROUGH SUB LD
32 | 2025-09-14 14:44 | MR2509/0318 |  | 132KV_132kv rajmilan - janakpur ckt | 132KV_RAJMILAN | NON-OCCM-MP | Disc replacement | 15-09-2025 08:00:00 | 15-09-2025 17:00:00 | G.L Sahu | 9425805102 | OK, JANAKPUR TO BE INFORMED, LOAD OF JANAKPUR TO BE MANAGED THROUGH ANUPPUR
33 | 2025-09-14 12:50 | MR2509/0311 |  | 132KV_132/33kv, 63 MVA X-MER-III (BBL) | 220KV_RATLAM | NON-OCCM-MP | LV side CT replacement work | 15-09-2025 09:00:00 | 15-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | SUB LD
34 | 2025-09-13 14:48 | MR2509/0299 |  | 132KV_132kv Sabalgarh Vijaypur ckt Ist | 220KV_SABALGARH | NON-OCCM-MP | Line Maintenance work | 15-09-2025 09:00:00 | 15-09-2025 17:00:00 | Suraj Pawar | 9425814079 | SUB LD
35 | 2025-09-13 12:28 | MR2509/0296 |  | 132KV_132kv Sagar-Garhakota line | 400KV_SAGAR | NON-OCCM-MP | Line maintenance work | 15-09-2025 10:00:00 | 15-09-2025 18:00:00 | J.P. Asati | 9424445533 | OK
36 | 2025-09-14 15:05 | MR2509/0319 |  | 132KV_63 MVA ABB Xmer | 132KV_SAGAR1 | NON-OCCM-MP | Postmansoon maintenance work | 15-09-2025 09:00:00 | 15-09-2025 17:00:00 | SK HAZARI | 9425801421 | OK
37 | 2025-09-09 15:38 | MR2509/0204 |  | 220KV_220 kv Satna (PGCIL) â¿¿ Kotar line | 220KV_SATNA | NON-OCCM-MP | line maintenance work | 15-09-2025 10:00:00 | 15-09-2025 17:00:00 | Mr R.K.Prajapati | 9407070182 | DEFERRED WRPC /WRLDC APPROVAL REQUIRED
38 | 2025-09-09 17:25 | MR2509/0221 |  | 220KV_220kv Tikamgarh - Damoh (PGCIL) line | 220KV_TIKAMGARH | NON-OCCM-MP | Bay maintenance | 15-09-2025 10:00:00 | 15-09-2025 15:00:00 | Pushpendra Kumar soni | 9425806398 | OK
39 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | OK, FTC TO BE SUBMITTED
40 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
41 |  | 266006 | Daily | 220KV-DAMOH-TIKAMGAD-1 | 220 | MADHYA PRADESH | CT TAN DELTA WORK | 15-Sep-2025 | 07:00 | 15-Sep-2025 | 19:59
42 |  | 260554 | Daily | 400KV-BHOPAL-MP-BINA-MP-1 | 400 | MADHYA PRADESH | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 15-Sep-2025 | 09:00 | 15-Sep-2025 | 18:00
43 |  | 260555 | Daily | 400KV-SSP-RAJGARH-2 | 400 | NCA,POWERGRID-WR2 (PGCIL),SSP (SSNL),MADHYA PRADESH,GUJARAT | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 15-Sep-2025 | 08:00 | 15-Sep-2025 | 18:00 | OK THROUGH SUB LD
44 |  | 260590 | Daily | 220KV-ITARSI-MP-ITARSI-2 | 220 | MADHYA PRADESH | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 15-Sep-2025 | 07:00 | 15-Sep-2025 | 17:00 | OK THROUGH SUB LD
45 |  | 260591 | Daily | 220KV-GWALIOR-MAHALGAON-1 | 220 | MADHYA PRADESH | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 15-Sep-2025 | 09:00 | 15-Sep-2025 | 17:00 | OK THROUGH SUB LD
46 |  | 260592 | Daily | 220KV-BETUL-PANDURNA-1 | 220 | MADHYA PRADESH | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 15-Sep-2025 | 09:00 | 15-Sep-2025 | 17:00 | OK THROUGH SUB LD
47 |  | 262508 | Daily | 220KV-ANNUPUR-KOTMIKALA-1 | 220 | MADHYA PRADESH,CHATTISGARH | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 15-Sep-2025 | 08:00 | 15-Sep-2025 | 17:59 | OK
48 |  | 265825 | Daily | 220KV-INDORE-INDORE NORTH ZONE-1 | 220 | MADHYA PRADESH | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 15-Sep-2025 | 07:00 | 15-Sep-2025 | 23:59 | OK LINE TO BE IN SERVICE
49 |  | 265845 | Daily | 220KV-INDORE-INDORE NORTH ZONE-2 | 220 | MADHYA PRADESH | PEPLACEMENT OF EXISTING 24FIBRE OPGW WITH48 FIBRE OPGW. DATA IS DIVERTED, ONLINE WORK PERMIT, AUTO TO NON AUTO | 15-Sep-2025 | 07:00 | 15-Sep-2025 | 19:59 | OK LINE TO BE IN SERVICE