## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-11 |  |  | APPROVED OUTAGE LIST FOR DATED 11.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-08 15:51 | MR2508/0120 |  | 400KV_Badnawar-Rajgarh (PGCIL) CKT-2 | 400KV_BADNAWAR | OCCM-MP | for line maintenance work | 11-08-2025 10:00:00 | 11-08-2025 18:00:00 | V.R. Panadia | 9425802330 | ok, through sub ld
2 | 2025-08-10 10:06 | MR2508/0126 |  | 400KV_315 MVA Transformer MAKE BHEL | 400KV_BINA4 | NON-OCCM-MP | Testing for new tie C&R panel | 11-08-2025 00:00:00 | 11-08-2025 14:00:00 | P.N. Namdeo | 9039472058 | ok, through sub ld
3 | 2025-08-10 13:51 | MR2508/0131 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 11-08-2025 07:00:00 | 13-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
4 | 2025-08-09 11:49 | MR2508/0123 |  | 220KV_220KV Itarsi-PGCIL No.1 Load Transfer Main CB to 220KV TBC | 220KV_ITARSI | NON-OCCM-MP | 220KV PGCIL No.1 for DPR Relya Testing work | 11-08-2025 10:00:00 | 11-08-2025 17:00:00 | J.K.Khoriya | 9425804975 | ok, line to be in service through TBC
5 | 2025-08-10 15:20 | MR2508/0132 |  | 220KV_220kV Transfer Bus Coupler | 400KV_JULWANIYA4 | NON-OCCM-MP | CTs tan delta measurement & bay main.work | 11-08-2025 10:00:00 | 11-08-2025 15:00:00 | Er. Mannalal Badole | 9131865464 | ok, through sub ld
6 | 2025-06-30 15:17 | MR2506/0623 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
7 | 2025-06-30 16:06 | MR2506/0632 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
8 | 2025-08-09 15:15 | MR2508/0125 | Continuous | 400KV_400 KV auxiliary BUS | 400KV_MANDSOUR4 | NON-OCCM-MP | New Bus section stringing | 09-08-2025 16:00:00 | 11-08-2025 18:00:00 | jay prakash parmar | 9425806919 | ok, through sub ld
9 | 2025-08-10 13:46 | MR2508/0130 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work | 11-08-2025 07:00:00 | 13-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
10 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
11 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
12 | 2025-08-10 17:45 | MR2508/0134 | Continuous | 132KV_132KV RAJMILAN-JANAKPUR (CGPTCL) CKT | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | comments of T&C required
13 | 2025-08-10 17:51 | MR2508/0135 | Continuous | 132KV_132KV Rajmilan-Dongrital ckt | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | comments of T&C required
14 | 2025-08-10 13:19 | MR2508/0128 |  | 132KV_132KV Main Bus | 132KV_SATNA1 | NON-OCCM-MP | Connecting the main bus isolator jumper | 11-08-2025 09:00:00 | 11-08-2025 11:00:00 | Er. Vishal baladhare | 9425804690 | ok
15 | 2025-08-08 19:36 | MR2508/0122 | Continuous | 400KV_50 MVA Station Transformer #11 | 400KV_SATPURA TPS | NON-OCCM-MP | For testing of transformer, bay equipment & P Rela | 11-08-2025 09:00:00 | 14-08-2025 18:00:00 | YASHWANT WARATHE | 9752778063 | other supply shall be available
16 | 2025-08-10 13:43 | MR2508/0129 |  | 220KV_220KV PGCILCKT-1 | 220KV_SEONI | OCCM-MP | 22okv Aux.bus isolator alignment | 11-08-2025 10:00:00 | 11-08-2025 17:00:00 | Shri C.S.Sanodiya | 9009798506 | ok
17 | 2025-08-07 13:20 | MR2508/0107 | Continuous | 400KV_500 MVA, 400/220 kV ICT | 400KV_SGTPS | NON-OCCM-MP | Testing of NR, DCRM of Bkr, CT testing, aircell re | 08-08-2025 08:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
18 | 2025-08-08 16:06 | MR2508/0121 | Continuous | 400KV_63MVA, 400/11&6.6 kV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM of Bkr, CT testing, Aircell rep | 09-08-2025 09:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
19 | 2025-08-10 16:17 | MR2508/0133 |  | 132KV_132KV SIDHI-MAUGANJ CKT-I | 220KV_SIDHI | NON-OCCM-MP | line maintenance work. | 11-08-2025 10:00:00 | 11-08-2025 17:00:00 | G.L SAHU | 9425805102 | ok
20 | 2025-07-23 17:35 | MR2507/0376 | Continuous | 400KV_Interconnecting Transformer-II 400KV/220KV | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of ICT-II | 04-08-2025 09:30:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | Continuous
21 | 2025-08-01 18:48 | MR2508/0015 | Continuous | 400KV_90 MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Overhauling work of Station Transformer-2 | 04-08-2025 09:00:00 | 11-08-2025 18:00:00 | Yogesh Chouhan | 7999328631 | Continuous
22 | 2025-08-08 14:54 | MR2508/0118 |  | 400KV_400 KV UJJAIN-INDORE PGCIL CKT IST | 400KV_UJJAIN4 | OCCM-WR | Bay maintenance and testing work | 11-08-2025 09:00:00 | 11-08-2025 18:00:00 | Santosh Chavrasiya | 9425804677 | ok, through sub ld
23 | 2025-08-10 12:20 | MR2508/0127 |  | 400KV_400kV Ujjain Hathuniya PGCIL ckt 1 | 400KV_UJJAIN4 | OCCM-WR | K Sachindra | 11-08-2025 10:00:00 | 11-08-2025 17:00:00 | K Sachindra | 7415651054 | as opportunity s/d
24 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 11-Aug-2025 | 07:00 | 11-Aug-2025 | 18:59 | ok
25 |  |  |  | DAMOH - 400KV - BUS 1 | POWERGRID-WR2 (PGCIL) |  | AMP of Bus-I | 11-Aug-2025 | 09:00 | 11-Aug-2025 | 18:00 | ok
26 |  |  |  | 400KV-INDORE-UJJAIN-1 | MADHYA PRADESH |  | FOR BAY MAINTENANCE & TESTING WORK AT 400KV S/S UJJAIN | 11-Aug-2025 | 09:00 | 11-Aug-2025 | 18:00 | ok, through sub ld
27 |  |  |  | 400KV-BADNAWAR-RAJGARH-2 | POWERGRID-WR2 (PGCIL),MADHYA PRADESH,GUJARAT |  | FOR LINE MAINTENANCE WORK | 11-Aug-2025 | 08:00 | 11-Aug-2025 | 18:00 | ok, through sub ld
28 |  |  |  | 220KV-SEONI-MP-SEONI-PG-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 11-Aug-2025 | 09:00 | 11-Aug-2025 | 18:00 | ok
S/I SLDC JABALPUR