## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-06 |  | APPROVED OUTAGE LIST FOR DATED 06.10.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-03 12:03 | MR2510/0056 | Daily | 220KV_220 kV Adampur-Hoshangabad line | 220KV_ADAMPUR | NON-OCCM-MP | Defective Disc replacement work | 04-10-2025 09:00:00 | 14-10-2025 17:00:00 | Ankit Mehroliya | 9425804506 | ok, through sub ld
2 | 2025-10-05 13:57 | MR2510/0114 |  | 132KV_63MVA TRANSFORMER-II | 132KV_ALIRAJPUR | NON-OCCM-MP | POST MONSOON MAINTENANCE | 06-10-2025 10:00:00 | 06-10-2025 18:00:00 | PERAM KIRAD | 7691908749 | sub ld
3 | 2025-10-05 15:33 | MR2510/0117 |  | 132KV_132 KV ASHTA-ICHHAWAR CKT.NO.1ST | 400KV_ASHTA4 | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 06-10-2025 13:00:00 | 06-10-2025 16:00:00 | JITENDRA LOHANA | 9425804978 | sub ld
4 | 2025-10-05 13:42 | MR2510/0110 |  | 220KV_220/33kv 50mva xmer -1st make bbl | 220KV_BADNAGAR | OCCM-MP | Postmansoon maitenance and testing work | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | Poshkar kushwaha | 9425813990 | ok, through sub ld, o&m shall be informed
5 | 2025-10-02 14:05 | MR2510/0040 |  | 315MVA_400/220KV_BHEL_Xmer_1 | 400KV_BADNAWAR | NON-OCCM-MP | Post mansoon Maintenance & testing work | 06-10-2025 08:00:00 | 06-10-2025 18:00:00 | Er Abhishek Verma | 9340855901 | ok, through sub ld
6 | 2025-10-01 17:24 | MR2510/0013 |  | 220KV_160MVA Xmer -I Make-AREVA | 220KV_BADOD | NON-OCCM-WR | Post Monsoon & Transformer Testing work | 06-10-2025 09:00:00 | 06-10-2025 17:30:00 | ER Y.K Rathore | 9425804968
7 | 2025-10-01 17:26 | MR2510/0014 |  | 220KV_220KV BAROD-UJJAIN CKT-I | 220KV_BADOD | NON-OCCM-WR | DPR RELAY SETTING WORK & HAND PRIP ONLY BAROD END | 06-10-2025 12:31:00 | 06-10-2025 14:30:00 | ER Y K RATHORE | 9425804968 | ok, through sub ld
8 | 2025-10-05 13:55 | MR2510/0113 |  | 132KV_40 MVA BHEL_X-mer | 220KV_BETUL | NON-OCCM-MP | Post monsoon maintenance & testing work. | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
9 | 2025-10-05 13:53 | MR2510/0112 |  | 220KV_160 MVA TELK TRANSFORMER | 220KV_BINA | NON-OCCM-MP | POST MONSOON MAINTENANCE WORK | 06-10-2025 09:30:00 | 06-10-2025 18:00:00 | ER LALIT SINGH | 9425806845 | ok, through sub ld
10 | 2025-10-05 11:11 | MR2510/0104 |  | 40MVA_132/33KV_BBL_X'mer_2 | 132KV_CHHINDWARA1 | NON-OCCM-MP | Post Mansoon Maintenance Work | 06-10-2025 14:00:00 | 06-10-2025 18:00:00 | Er. Anju Dhurve | 9425804752 | ok
11 | 2025-10-05 11:08 | MR2510/0102 |  | 63MVA_132/33KV_BBL_Xmer_1 | 132KV_CHHINDWARA1 | NON-OCCM-MP | Post Mansoon Maintenance Work | 06-10-2025 09:00:00 | 06-10-2025 13:00:00 | Er.Anju Dhurve | 9425804752 | ok
12 | 2025-10-04 15:57 | MR2510/0095 |  | 220KV_160 MVA 220/132KV AREVA X-MER-2 | 220KV_DAMOH | NON-OCCM-MP | Post Monsoon Maintenance & Testing work | 06-10-2025 09:00:00 | 06-10-2025 18:00:00 | M.K.Choubey | 9425801424 | ok
13 | 2025-09-18 17:16 | MR2509/0453 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M. M. BAIG | 9425805067 | real time
14 | 2025-10-05 11:10 | MR2510/0103 |  | 132KV_132 KV 40 MVAX-MER-2,Telk | 220KV_DATIA | NON-OCCM-WR | Post monsoon maintenance & testing work | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | Raksha Chhapariya | 6265080313 | sub ld
15 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
16 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
17 | 2025-10-05 15:51 | MR2510/0119 |  | 220KV_220/132KV 160MVA EMCO | 220KV_DEWAS | NON-OCCM-MP | FOR POST MONSOOM MAINT. | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | ARVIND KUMAR JOSHI | 9425801305 | ok, through sub ld
18 | 2025-10-05 13:32 | MR2510/0109 |  | 132KV_132KV Anuppur-Dongrital ckt. | 132KV_DONGRITAL | NON-OCCM-MP | disc replacement | 06-10-2025 08:33:00 | 06-10-2025 17:00:00 | G.L SAHU | 9425805102 | ok, if 132kv VSTPS-Waidhan ckt s/d not availed by NTPC
19 | 2025-10-04 15:35 | MR2510/0094 |  | 220KV_160 MVA X-MER BHEL | 220KV_GORABAZAR | NON-OCCM-MP | POST MANSOON WORK | 06-10-2025 08:00:00 | 06-10-2025 16:00:00 | R,S BAIS | 9425804887 | ok
20 | 2025-10-05 11:58 | MR2510/0105 |  | 220KV_160 MVA X-MER 220KV/132KV Ist (BHEL) | 220KV_GUNA | NON-OCCM-MP | POST MANSOON MAINTENANCE & RELAY TESTING WORK | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | SH. SAGAR SINGH DHAKAD | 9589205697 | ok, through sub ld
21 | 2025-10-05 12:15 | MR2510/0106 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 220KV_HANDIYA | NON-OCCM-MP | Post monsoon Maint. & Testing Work | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | K.R. Dongre | 9424430754 | real time
22 | 2025-10-04 12:27 | MR2510/0086 | Daily | 220KV_220 KV Hoshangabad-Adampur | 220KV_HOSHANGABAD | NON-OCCM-MP | Resagging work b/w loc.no. 20 of lilo to 71 | 05-10-2025 09:00:00 | 10-10-2025 17:00:00 | Ashutosh Rai | 9425806902 | as opportunity s/d
23 | 2025-10-01 11:00 | MR2510/0003 |  | 220KV_220KV Indore-Badnagar line | 400KV_INDORE4 | NON-OCCM-MP | For post monsoon maintenance work. | 06-10-2025 09:00:00 | 06-10-2025 17:00:00 | Er.Atul Paradkar | 9425804929 | Deffered due to s/d on Badnawar ICT
24 | 2025-10-04 12:05 | MR2510/0085 |  | 132KV_63 MVA ABB TRANSFORMER | 220KV_JABALPUR | NON-OCCM-MP | POST MANSOON & 33 KV CT REPLECMENT | 06-10-2025 08:00:00 | 06-10-2025 18:00:00 | D.N PODDAR | 9425805034 | ok, o&m shall be informed
25 | 2025-09-18 12:55 | MR2509/0410 | Continuous | 400KV_400KV DAMOH - KATNI LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 06-10-2025 09:00:00 | 11-10-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered, not in WR list
26 | 2025-10-05 09:09 | MR2510/0098 |  | 132KV_132kv 50MVA Xmer BBL | 220KV_MALANPUR | NON-OCCM-MP | Post Monsoon Maint. work | 06-10-2025 10:30:00 | 06-10-2025 17:30:00 | Vikram Ahirwar | 9425805415 | sub ld
27 | 2025-10-05 10:37 | MR2510/0101 | Daily | 132KV_132KV Neemuch Manasa Line | 132KV_MANASA | NON-OCCM-MP | Re sagging and line maintanence work | 06-10-2025 08:00:00 | 12-10-2025 18:00:00 | Gaurav goyal | 9425805120 | sub ld
28 | 2025-10-04 14:18 | MR2510/0089 |  | 220KV_160MVA XMER-2 IMP MAKE | 220KV_MANDIDEEP | NON-OCCM-MP | POST- MONSOON MAINT. & TESTING WORK | 06-10-2025 09:00:00 | 06-10-2025 18:00:00 | A.K. VERMA | 9425801324 | ok, through sub ld
29 | 2025-10-05 15:42 | MR2510/0118 | Continuous | 400KV_400kv bus bar protection | 400KV_MANDSOUR4 | NON-OCCM-MP | 400 à¤¿à¥¿à¤µà¥¿ à¤¿à¤ªà¤¿à¥¿à¤¿à¤¦à¥à¤° à¤®à¤¿à¤¦à¤¸à¥¿à¤° à¤ªà¤° à¤µà¤°à¥à¤¤à¤®à¤¾à¤¨ à¤®à¥¿à¤¿ à¤¨à¤µà¥¿à¤¨ 500 M | 05-10-2025 10:00:00 | 06-10-2025 18:00:00 | rajesh bhuriya | 9425806920 | Deffered, not in WR list
30 | 2025-10-05 10:08 | MR2510/0100 |  | 132KV_132 KV 40 MVA BBL X- MER II | 132KV_MANGAWAN | NON-OCCM-MP | Post monsoon maintenance and testing | 06-10-2025 11:00:00 | 06-10-2025 18:00:00 | Kanishka singh | 9425804656 | ok
31 | 2025-10-05 12:15 | MR2510/0107 |  | 20MVA_132/33KV_VOLTAMP_X'mer_2 | 132KV_MORWA | NON-OCCM-MP | Y Phase C.T replacement work due to high tan delta | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | S.B.Singh | 9039635859 | ok
32 | 2025-10-05 09:11 | MR2510/0099 |  | 400KV_315MVA ICT-1 transformer make-BHEL | 400KV_NAGDA4 | NON-OCCM-MP | Post monsoon maintenance and testing work | 06-10-2025 09:00:00 | 06-10-2025 18:00:00 | Sunil Bamniya | 9425820045 | ok, through sub ld, ICT 2 shall be in service
33 | 2025-10-02 15:27 | MR2510/0050 | Continuous | 220KV_220/132 Kv 160MVA BHEL 3 X-mer | 220KV_NARSINGHPUR | NON-OCCM-MP | Replacement of CB,PI&Mainbus isolator erection | 03-10-2025 09:00:00 | 08-10-2025 17:00:00 | Dinesh Kumar Kushwaha | 9425182413 | Continuous
34 | 2025-10-05 13:45 | MR2510/0111 |  | 220KV_220 KV Narsinghpur-Pipariya Ckt | 220KV_NARSINGHPUR | NON-OCCM-MP | Flashover disc replacement work at loc.No.281/R-Ph | 06-10-2025 10:00:00 | 06-10-2025 18:00:00 | Ashish Kumar | 9425805935 | Deffered due to s/d on 160MVA x-mers at Narsinghpur and Pipariya
35 | 2025-10-05 12:16 | MR2510/0108 |  | 220KV_160 MVA Xmer-2 | 220KV_PIPARIYA | NON-OCCM-WR | For post moonson maintenance work | 06-10-2025 10:00:00 | 06-10-2025 17:00:00 | B K Jhariya | 9425806831 | ok, through sub ld
36 | 2025-10-02 10:44 | MR2510/0018 | Daily | 400KV_315 MVA ICT-II make-CGL | 400KV_PITHAMPUR4 | NON-OCCM-MP | Post monsoon maintenance & testing work. | 06-10-2025 10:00:00 | 07-10-2025 18:00:00 | Rajudas bairagi | 9425801532 | ok, through sub ld
37 | 2025-10-05 15:22 | MR2510/0115 |  | 132KV_63 MVA bbl-make transformer | 132KV_PRITHVIPUR | NON-OCCM-MP | Post mnsoon | 06-10-2025 09:00:00 | 06-10-2025 13:00:00 | Pushpendra kumar soni | 9425806398 | ok
38 | 2025-10-05 15:25 | MR2510/0116 |  | 132KV_40 MVA bbl-make transformer | 132KV_PRITHVIPUR | NON-OCCM-MP | Post maansoon | 06-10-2025 14:00:00 | 06-10-2025 18:00:00 | Pushpendra Kumar soni | 9425806398 | ok
39 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
40 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data availability confirmation required from communication
41 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
42 |  |  |  | 220KV-SATNA-KOTAR-1 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 06-Oct-2025 | 10:00 | 06-Oct-2025 | 17:00 | real time
43 |  |  |  | 220KV-RAJGARH-RAJGARH-MP-2 |  |  | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 06-Oct-2025 | 08:00 | 06-Oct-2025 | 18:00 | real time
44 |  |  |  | 132KV-VSTPS-WAIDHAN-1 |  |  | Annual Bay Maitenanace & Testing/ CRP replacement | 04-Oct-2025 | 08:08 | 11-Oct-2025 | 18:00 | real time
S/I SLDC JABALPUR