## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-14 |  |  | 2025-08-14
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-13 13:00 | MR2508/0179 |  | 132KV_132KV Alot-Jharla Ckt-II Line | 132KV_ALOT | NON-OCCM-MP | Jumper cone tighting work. | 14-08-2025 10:00:00 | 14-08-2025 18:00:00 | Kamal Solanki | 9425805262 | sub ld
2 | 2025-08-13 13:17 | MR2508/0181 |  | 132KV_132kv main bus | 220KV_BADNAGAR | OCCM-MP | For attending Red Hot point Yph section isolater c | 14-08-2025 10:00:00 | 14-08-2025 14:00:00 | Poshkar kushwaha | 9425813990 | o&m consent required, sub ld to manage the loading
3 | 2025-08-13 11:47 | MR2508/0178 |  | 132KV_132 KV Bina-Borl Ckt-1 | 220KV_BINA | NON-OCCM-MP | for conductor jumpering & modification related wor | 14-08-2025 10:00:00 | 14-08-2025 17:00:00 | Sanjay Singh Thakur | 9425806936 | ok
4 | 2025-08-12 15:27 | MR2508/0167 | Continuous | 132KV_132kv 50 mva bbl-make transformer | 132KV_DIGODA | NON-OCCM-MP | Air cell of main-conservator tank charged by bbl r | 13-08-2025 10:00:00 | 14-08-2025 16:00:00 | Pushpendra Kumar soni | 9425806398 | Continuous
5 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
6 | 2025-06-30 15:17 | MR2506/0623 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
7 | 2025-06-30 16:06 | MR2506/0632 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
8 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
9 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
10 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
11 | 2025-08-10 17:45 | MR2508/0134 | Continuous | 132KV_132KV RAJMILAN-JANAKPUR (CGPTCL) CKT | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
12 | 2025-08-10 17:51 | MR2508/0135 | Continuous | 132KV_132KV Rajmilan-Dongrital ckt | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
13 | 2025-08-05 12:05 | MR2508/0051 | Continuous | 400KV_400 kv MAIN BUS-2 | 400KV_SAGAR | OCCM-MP | FOR EXT OF MAIN BUS-2 AND PANTO ISO ERECTIONIO | 13-08-2025 09:00:00 | 14-08-2025 17:00:00 | ANIL MAHOR | 9425805149 | Continuous
14 | 2025-08-08 19:36 | MR2508/0122 | Continuous | 400KV_50 MVA Station Transformer #11 | 400KV_SATPURA TPS | NON-OCCM-MP | For testing of transformer, bay equipment & P Rela | 11-08-2025 09:00:00 | 14-08-2025 18:00:00 | YASHWANT WARATHE | 9752778063 | Continuous
15 | 2025-08-07 13:20 | MR2508/0107 | Continuous | 400KV_500 MVA, 400/220 kV ICT | 400KV_SGTPS | NON-OCCM-MP | Testing of NR, DCRM of Bkr, CT testing, aircell re | 08-08-2025 08:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
16 | 2025-08-08 16:06 | MR2508/0121 | Continuous | 400KV_63MVA, 400/11&6.6 kV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM of Bkr, CT testing, Aircell rep | 09-08-2025 09:00:00 | 14-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
17 | 2025-08-13 13:11 | MR2508/0180 |  | 220KV_220/132 KV 160 MVA IMP X-mer | 220KV_SIRMOUR | NON-OCCM-MP | For NIFPS installation work | 14-08-2025 11:00:00 | 14-08-2025 16:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
18 |  | 261932 |  | SAGAR - 400KV - BUS 2 |  | WR-OCCM | for bus extension work and erection of pantograph isolator for installation of new 125 MVAR bus reactor | 13-08-2025 08:00:00 | 14-08-2025 16:59:00 |  |  | CONTINUOUS All Elements to be in service with Bus-1. In case of N-1 all elements will be out. Load to be managed by SLDC MP
19 |  | 259208 |  | 132KV-DHARNI-NEPANAGAR-1 |  | WR-OCCM | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 14-08-2025 07:00:00 | 14-08-2025 18:59:00 |  |  | OK A/R in NA, line to be in service