## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-01
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-26 10:45 | MR2509/0704 | Daily | 132KV_132kV Balaghat Baihar Line | 132KV_BALAGHAT | OCCM-MP | Hand Trip Due to load Manage | 28-09-2025 08:00:00 | 02-10-2025 17:00:00 | S.K. BHALADHARE | 9425807264 | ok
2 | 2025-09-30 14:44 | MR2509/0791 |  | 220KV_220KV Barwaha-Handia Feeder | 220KV_BARWAHA | NON-OCCM-MP | S/d for Main-2 DPR Relay Testing & Commissioning W | 01-10-2025 10:00:00 | 01-10-2025 17:00:00 | Er.Imran Beg | 9425805200 | ok, through sub ld
3 | 2025-09-30 14:36 | MR2509/0788 |  | 132KV_132 KV Bina-Khurai Ckt-1 | 220KV_BINA | NON-OCCM-MP | For line maintenance work. | 01-10-2025 10:00:00 | 01-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | ok
4 | 2025-09-30 13:03 | MR2509/0787 |  | 220KV_220 KV Jabalpur Ckt-2 | 220KV_BIRSINGHPUR | NON-OCCM-MP | Line Iso Jha Repairing & Alignment work | 01-10-2025 10:00:00 | 01-10-2025 16:00:00 | Toshan Singh | 9425809482 | ok
5 | 2025-09-30 15:49 | MR2509/0799 |  | 132KV_50 MVA BBL-make-Make Transformer | 132KV_BUDHERA | NON-OCCM-MP | Post mansoon maintenance | 01-10-2025 14:00:00 | 01-10-2025 18:00:00 | Pushpendra Kumar soni | 9425906398 | o&m consent required
6 | 2025-09-30 15:47 | MR2509/0798 |  | 132KV_40 MVA bhel -make transformer | 132KV_BUDHERA | NON-OCCM-MP | Post mansoon maintenance | 01-10-2025 09:00:00 | 01-10-2025 13:00:00 | Pushpendra Kumar soni | 9425806398 | o&m consent required
7 | 2025-09-30 14:43 | MR2509/0790 |  | 220KV_220 KV PGCIL CKT. II | 220KV_GUNA | NON-OCCM-MP | AMP of Transmission line and associated line bay | 01-10-2025 09:00:00 | 01-10-2025 18:00:00 | Vivek Kumar | 8058823505 | ok, through sub ld
8 | 2025-09-29 18:00 | MR2509/0783 | Continuous | 132KV_132KV bus coupler | 220KV_HANDIYA | NON-OCCM-MP | Safety Purpose | 30-09-2025 10:00:00 | 02-10-2025 17:00:00 | K R Dongre | 9424430754 | sub ld
9 | 2025-09-29 17:48 | MR2509/0782 | Continuous | 220KV_220KV Bus Coupler | 220KV_HANDIYA | NON-OCCM-MP | Safety Purpose | 30-09-2025 10:00:00 | 02-10-2025 17:00:00 | K.R. Dongre | 9424430754 | ok, through sub ld
10 | 2025-09-30 14:41 | MR2509/0789 |  | 220KV_220 Bus Coupler (TBC) | 220KV_HANDIYA | NON-OCCM-MP | H/T For safety & Clearance Purpose | 01-10-2025 09:00:00 | 01-10-2025 18:00:00 | K.R. Dongre | 9424430754 | ok, through sub ld
11 | 2025-09-30 15:44 | MR2509/0796 |  | 220KV_220 KV NORTH ZONE(INDORE)-PGCIL 1 | 220KV_INDORE NORTH | NON-OCCM-MP | FIRE WEGDE CONNECTOR INSTALLATION WORK | 01-10-2025 09:00:00 | 01-10-2025 17:00:00 | CHANDRAKANT KAUSHAL | 9425801530 | Deffered, not in WR list
12 | 2025-09-30 15:47 | MR2509/0797 |  | 220KV_220 KV NORTH ZONE -PGCIL CKT 1 | 220KV_INDORE-NZ | NON-OCCM-MP | FIRE WEDGE CONNECTOR INSTALLATION WORK | 01-10-2025 09:00:00 | 01-10-2025 17:00:00 | CHANDRAKANT KAUSHAL | 9425801530 | Deffered, not in WR list
13 | 2025-09-30 15:16 | MR2509/0794 |  | 220KV_220KV Kanwan-Dhar ckt -2nd | 220KV_KANWAN2 | NON-OCCM-MP | attend hot point of Y-Phase line Isolator clamp | 01-10-2025 11:00:00 | 01-10-2025 14:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
14 | 2025-09-26 11:48 | MR2509/0709 | Daily | 132KV_132kV Balaghat Kirnapur Ckt-IInd | 400KV_KIRNAPUR | NON-OCCM-MP | Re-sagging of section Loc 465 to 478 & 529 to 547 | 28-09-2025 08:00:00 | 02-10-2025 17:00:00 | Shridhar Kumar Bhaladhare | 9425448642 | ok, after load management
15 | 2025-09-30 16:45 | MR2509/0800 |  | 220KV_160MVA X-MER IMP | 220KV_KOTAR | OCCM-MP | OIL TOPPING WORK IN CONSERVATOR TANK | 01-10-2025 14:00:00 | 01-10-2025 15:30:00 | ARUN KUMAR KOL | 8319677721 | ok
16 | 2025-09-30 16:46 | MR2509/0801 | Continuous | 220KV_220 /132 kv 160 Bhel X-mer3 | 220KV_NARSINGHPUR | NON-OCCM-MP | Sd for replacement Cb ,pi erection isolator | 01-10-2025 09:00:00 | 06-10-2025 17:00:00 | Dinesh kushwaha | 9425182413 | please plan after 2nd October (dusshera)
17 | 2025-09-30 15:06 | MR2509/0793 |  | 132KV_40 MVA IMP XMER | 132KV_REWA-II (SAGRA) | NON-OCCM-MP | POST MANSOON MAINTENACE AND TESTINGI WORK | 01-10-2025 11:00:00 | 01-10-2025 18:00:00 | ER KANISHKA SINGH | 9425804656 | ok
18 | 2025-09-29 16:45 | MR2509/0779 | Daily | 132KV_132kV Seoni Nainpur Line | 132KV_SEONI1 | NON-OCCM-MP | Hand Trip Due to Load Manage | 30-09-2025 08:00:00 | 01-10-2025 07:00:00 | S.K. BHALADHARE | 9425807264 | shall be done only if required
19 | 2025-09-30 12:20 | MR2509/0786 |  | 132KV_132KV Ashta â¿¿ Sonkatchh Line | 132KV_SONKATCH | NON-OCCM-MP | . For overhead crossing between location no.- 322R | 01-10-2025 09:00:00 | 01-10-2025 17:00:00 | A.R.KANEL | 9425805217 | sub ld
20 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
21 |  | 261137 |  | 400KV-INDORE-MP-ASOJ-1 | 400 | POWERGRID_WR2 | Simultaneous outage of ASOJ - 400KV - BUS 2 is required Bus-2 Pento Isolator replacement work under add cap, Dia to be kept open at both ends. | 01-Oct-2025 | 07:00 | 01-Oct-2025 | 15:00 | ok
22 |  | 261137 |  | 400KV-INDORE-MP-ASOJ-2 | 400 | POWERGRID_WR2 | Simultaneous outage of ASOJ - 400KV - BUS 2 is required Bus-2 Pento Isolator replacement work under add cap, Dia to be kept open at both ends. | 01-Oct-2025 | 16:00 | 01-Oct-2025 | 23:00 | ok
23
24
25