## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-30 |  |  | APPROVED OUTAGE LIST FOR DATED 30.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-29 15:36 | MR2507/0464 |  | 220KV_220/132KV 160MVA BBL X-mer | 220KV_ANUPPUR | NON-OCCM-MP | Neutal copper strips replacement & 132kv side LBB | 30-07-2025 11:00:00 | 30-07-2025 17:00:00 | sunil kumar bhalavi | 9425804704 | ok
2 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
3 | 2025-07-29 16:15 | MR2507/0465 |  | 220KV_220Kv Chhegaon-Khandwa(CTU) CKT-II | 400KV_CHHEGAON4 | NON-OCCM-MP | For CVT Wiring Work | 30-07-2025 10:30:00 | 30-07-2025 16:30:00 | Shri Ganesh Mansare | 9425802441 | Deffered, not in WR list
4 | 2025-07-29 11:51 | MR2507/0456 |  | 132KV_132 KV Damoh -Hatta line | 132KV_DAMOH1 | NON-OCCM-MP | Replacement of LA RYB phase | 30-07-2025 10:00:00 | 30-07-2025 17:00:00 | B K Sahu | 9425801433 | ok
5 | 2025-07-25 16:41 | MR2507/0414 | Daily | 400KV_125 MVAr SHUNT REACTOR | 400KV_INDIRASAGAR | NON-OCCM-WR | MAINTENANCE WORK OF SAID ITEM | 29-07-2025 10:00:00 | 31-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | as per the voltage profile
6 | 2025-07-29 11:34 | MR2507/0455 |  | 220KV_220KV Main Bus No.-2 | 220KV_ITARSI | NON-OCCM-MP | Main Bus 2 Fly over Jumper connecting | 30-07-2025 10:00:00 | 30-07-2025 16:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld, 220kv Itarsi-Sarni 3 will also be out
7 | 2025-07-29 14:50 | MR2507/0460 |  | 220KV_220KV Kanwan-Badnawar 1st | 220KV_KANWAN2 | NON-OCCM-MP | To repaired the droper jumpher wire | 30-07-2025 11:30:00 | 30-07-2025 14:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
8 | 2025-06-30 15:05 | MR2506/0621 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered, not in WR list
9 | 2025-06-30 15:54 | MR2506/0630 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
10 | 2025-07-27 14:12 | MR2507/0430 | Continuous | 132KV_132 KV Khurai- Sagar ckt | 132KV_KHURAI | NON-OCCM-MP | For modification work of above line | 27-07-2025 07:00:00 | 03-08-2025 18:00:00 | Sanjay singh thakur | 9425806936 | Continuous
11 | 2025-07-28 19:22 | MR2507/0451 |  | 132KV_132KV Kirnapur-Moil line | 400KV_KIRNAPUR | NON-OCCM-MP | For 132kV CC & Wave Trap erect work at 400KV K"pur | 30-07-2025 10:00:00 | 30-07-2025 18:00:00 | Vijay Kumar Tandekar | 9425805095 | ok, line shall be restored in its present configuration
12 | 2025-07-29 12:58 | MR2507/0459 |  | 132KV_132kV KIRNAPUR-BHARVELI LINE | 400KV_KIRNAPUR | NON-OCCM-MP | J/C CONE TIGHTENING WORK & OTHER LINE MAINTENANCE | 30-07-2025 10:00:00 | 30-07-2025 18:00:00 | S.K. BHALADHARE | 9425807264 | what is bharveli?
13 | 2025-07-24 12:24 | MR2507/0380 | Continuous | 400KV_400 KV Main Bus-2nd | 400KV_MANDSOUR4 | NON-OCCM-MP | Overhead stringing work | 29-07-2025 09:00:00 | 05-08-2025 18:00:00 | J.P. Parmar | 9425806919 | Deffered, not in WR list
14 | 2025-07-28 18:36 | MR2507/0449 | Daily | 220KV_220 KV Narsinghpur-Chichli-Pipariya Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Rectification/replacement/work between Tower No-33 | 30-07-2025 09:00:00 | 05-08-2025 18:00:00 | Ashish Kumar | 9425805935 | Deffered due to s/d on 220kv Bus at Itarsi ss
15 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
16 | 2025-07-27 16:04 | MR2507/0434 | Continuous | 220KV_220KV Neemuch Mandsaur circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | OPGW work | 27-07-2025 18:00:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | Continuous
17 | 2025-07-27 16:08 | MR2507/0435 | Daily | 220KV_220KV Neemuch-Mandsaur ciucuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | Only hot line permit | 28-07-2025 08:00:00 | 30-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
18 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
19 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
20 | 2025-07-25 11:39 | MR2507/0401 |  | 220KV_220KV Main Bus | 220KV_PANDHURNA | NON-OCCM-MP | Replacement of old Defective /Cracked 220KV Solid | 30-07-2025 08:00:00 | 30-07-2025 15:00:00 | MR sahu | 9425804982 | ok, through sub ld
21 | 2025-07-28 14:18 | MR2507/0443 |  | 220KV_220KV Pithampur-Depalpur ckt | 400KV_PITHAMPUR4 | NON-OCCM-MP | IInd DPR Relay commissioning and testing work | 30-07-2025 11:00:00 | 30-07-2025 18:00:00 | Rajudas Bairagi | 9425801532 | Deffered by site
22 | 2025-07-28 13:43 | MR2507/0439 |  | 220KV_Rajgarh (PGCIL) to Rajgarh (MPPTCL) CKT-2 | 220KV_RAJGARH DHAR | OCCM-MP | For line maintenance work | 30-07-2025 10:00:00 | 30-07-2025 18:00:00 | V.R.Panadia | 9425802330 | ok, through sub ld
23 | 2025-07-29 15:27 | MR2507/0462 |  | 132KV_132KV Morwa-Bargawan(TBCB) CKT-I | 132KV_RAJMILAN | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 30-07-2025 10:00:00 | 30-07-2025 17:00:00 | G.L SAHU | 9425805102 | ok, adani to be informed
24 | 2025-07-29 12:39 | MR2507/0457 |  | 220KV_220KV DAMOH-SAGAR 2nd Ckt. LINE (PGCIL) | 400KV_SAGAR | OCCM-MP | Line maintenance work | 30-07-2025 09:00:00 | 30-07-2025 18:00:00 | J.P. Asati | 9424445533 | ok
25 | 2025-07-16 11:19 | MR2507/0211 | Continuous | 220KV_63MVA 220KV/11&6.6 kV Station Trf-5A | 400KV_SGTPS | NON-OCCM-MP | Relay testing,DCRM,CT test,Aircell replacemen | 28-07-2025 08:00:00 | 30-07-2025 18:00:00 | Pramod Mishra | 8989973149 | Continuous
26 | 2025-07-23 17:12 | MR2507/0374 | Continuous | 400KV_90MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | OVERHAULLING OF 90MVA STATION TRANSFORMER-2 | 28-07-2025 09:30:00 | 06-08-2025 17:30:00 | Yogesh Chouhan | 7999328631 | Continuous
27 | 2025-07-29 15:35 | MR2507/0463 |  | 220KV_220kV Tikamgarh-Damoh (MPPTCL) Line | 220KV_TIKAMGARH | NON-OCCM-MP | Missing/Slip/Loose, AH/VD Attending | 30-07-2025 10:00:00 | 30-07-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
28 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 30-Jul-2025 | 08:00 | 30-Jul-2025 | 17:59 | ok
29 |  |  |  | 220KV-PANDURNA-KALMESHWAR-1 | MADHYA PRADESH,MAHARASHTRA |  | line outage required for 220kv Bus shutdown for jumper replacement work for upcoming 200MVA x-mer and isolator alignment work | 30-Jul-2025 | 08:00 | 30-Jul-2025 | 14:59 | ok, through sub ld
30 |  |  |  | 220KV-DAMOH-SAGAR-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 30-Jul-2025 | 09:00 | 30-Jul-2025 | 18:00 | ok
31 |  |  |  | 220KV-MORENA-MEHGAON-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 30-Jul-2025 | 09:00 | 30-Jul-2025 | 17:00 | real time
32 |  |  |  | 220KV-RAJGARH-RAJGARH-MP-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 30-Jul-2025 | 08:00 | 30-Jul-2025 | 18:00 | ok, through sub ld
33 |  |  |  | 220KV-REWA-REWA-MP-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK ( REWA RUMS) | 30-Jul-2025 | 10:00 | 30-Jul-2025 | 17:00 | real time
34 |  |  |  | 220KV-BETUL-PANDURNA-1 | MADHYA PRADESH |  | line outage required for 220kv Bus shutdown for jumper replacement work for upcoming 200MVA x-mer and isolator alignment work | 30-Jul-2025 | 08:00 | 30-Jul-2025 | 14:59 | ok, through sub ld
35 |  |  |  | 220KV-SATNA-MP-SATNA-3 | MADHYA PRADESH |  | AMP Work & Line Terminal Equipment Tightness; | 30-Jul-2025 | 09:00 | 30-Jul-2025 | 18:00 | ok
36 |  |  |  | 400KV-INDORE-MP-ASOJ-2 | POWERGRID-WR2 (PGCIL) |  | PLCC digital protection coupler installation work & Line AMP Works, Dia to be kept open at both ends. | 30-Jul-2025 | 09:00 | 30-Jul-2025 | 18:00 | ok
S/I SLDC JABALPUR