## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-11-01 |  |  | APPROVED OUTAGE LIST FOR DTD.01.11.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-31 15:51 | MR2510/0718 |  | 220KV_220KV TBC | 400KV_ASHTA4 | NON-OCCM-MP | Post Monsoon Maintenace work | 01-11-2025 11:00:00 | 01-11-2025 16:00:00 | Jitendra Lohana | 9425804978 | ok, through sub ld, no other element shall be affected
2 | 2025-10-16 17:16 | MR2510/0478 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | M.M. BAIG | 9425805067 | Deffered
3 | 2025-10-31 17:02 | MR2510/0724 |  | 220KV_220 KV HOSHANGABAD- PGCIL NO. 2 FEEDER | 220KV_HOSHANGABAD | NON-OCCM-MP | LOAD FEED TO TBC FOR LBB TESTING WORK | 01-11-2025 14:00:00 | 01-11-2025 18:00:00 | V.P.DWIVEDI | 9425804799 | ok, line to be in service through TBC, through sub ld
4 | 2025-10-31 16:58 | MR2510/0723 |  | 220KV_220 KV HOSHANGABAD- PGCIL NO. 1 FEEDER | 220KV_HOSHANGABAD | NON-OCCM-MP | LOAD SHIFTING TBC FOR LBB TESTING WORK | 01-11-2025 09:00:00 | 01-11-2025 13:00:00 | V.P.DWIVEDI | 9425804799 | ok, line to be in service through TBC, through sub ld
5 | 2025-10-31 11:06 | MR2510/0700 | Daily | 220KV_220 KV Itarsi-Pipariya II | 220KV_ITARSI | NON-OCCM-MP | Replacement of Single to Double Disc insul. string | 01-11-2025 09:00:00 | 05-11-2025 18:00:00 | Ashutosh Rai | 9425806902 | Deffered, due to multiple outages at Itarsi end
6 | 2025-10-31 12:44 | MR2510/0704 |  | 220KV_220KV Julwania - Kukshi DCDS Ckt-2nd line | 400KV_JULWANIYA4 | NON-OCCM-MP | F/o disc insulator rep.& Add. bird excreta prev.in | 01-11-2025 10:00:00 | 01-11-2025 17:00:00 | Dinesh More | 9425806860 | ok, through sub ld
7 | 2025-09-18 13:12 | MR2509/0414 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
8 | 2025-10-31 13:10 | MR2510/0706 |  | 132KV_132 KV 63 MVA X-MER BBL | 220KV_KOTAR | OCCM-MP | FOR DAMAGE CONDUCTOR ATTENDING WORK | 01-11-2025 11:00:00 | 01-11-2025 14:00:00 | ER. ARUN KUMAR KOL | 8319677721 | o&m consent required
9 | 2025-10-31 16:04 | MR2510/0719 |  | 132KV_132 kV Pandhurna Multai | 220KV_PANDHURNA | NON-OCCM-MP | F/o disc replaced and Bird guard provide | 01-11-2025 09:30:00 | 01-11-2025 18:00:00 | A.M.Shende | 7587951136 | ok
10 | 2025-10-08 12:32 | MR2510/0204 | Daily | 400KV_400KV Rajgarh-SSP Ckt-1 | 400KV_RAJGARH-PG | NON-OCCM-WR | old disc insulator replacement work | 01-11-2025 08:00:00 | 15-11-2025 18:00:00 | V.R.panadia | 8120516165 | ok, through sub ld
11 | 2025-10-31 12:38 | MR2510/0703 |  | 132KV_132 kv Rampur-Satna Line | 132KV_RAMPUR BAGHELAN | NON-OCCM-MP | Sf6 Gas leakage & R ph C.T. Red Hot Poin Attending | 01-11-2025 10:00:00 | 01-11-2025 14:00:00 | Kanishk Singh | 9893124647 | ok
12 | 2025-09-05 17:39 | MR2509/0127 | Continuous | 400KV_400KV Sarni-Ashta line-II | 400KV_SATPURA TPS | NON-OCCM-MP | Work of complete overhauling & testing of 400KV br | 30-10-2025 09:00:00 | 01-11-2025 18:00:00 | YASHWANT WARATHE | 9425611046 | Deffered
13 | 2025-10-31 16:05 | MR2510/0720 |  | 132KV_SONKACHH - ASHTA LINE | 132KV_SONKATCH | NON-OCCM-MP | FOR OPGW CONNECTIVITY AT 132 KV S/S JAWARJOD | 01-11-2025 09:00:00 | 01-11-2025 18:00:00 | A.R. KANEL | 9425805217 | sub ld
14 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
15 | 2025-09-02 14:10 |  |  | 400KV-SSP-RAJGARH-1 |  | occm-wr | for old disc replacement Work & other line maintenance work | 01-Nov-2025 | 09:00 | 01-Nov-2025 | 18:00 | ok
16 | 2025-09-02 14:10 |  |  | 220KV-DAMOH-SAGAR-2 |  | occm-wr | AMP of line terminal of Damoh Sagar 2 | 01-Nov-2025 | 09:00 | 01-Nov-2025 | 17:30 | ok
17 | 2025-09-02 14:10 |  |  | 220KV-ITARSI-MP-ITARSI-1 |  | occm-wr | For Repairing/Replacement of Damaged Conductor for Wave Trap of Line | 01-Nov-2025 | 08:00 | 01-Nov-2025 | 17:59 | ok, through sub ld
s/I ,sldc mpptcl jbp