## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-06-25 |  |  | 2025-06-25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-16 18:55 | MR2506/0355 | Daily | 220KV_220 KV BAIRAGARH MUGALIYACHAP LINE | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-16 19:00 | MR2506/0357 | Daily | 220KV_220 KV BHOPAL BAIRAGARH LINE-3 | 220KV_BAIRAGARH | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-23 09:45 | MR2506/0456 | Daily | 220KV_220 kv Bairagarh Ashta | 220KV_BAIRAGARH | NON-OCCM-MP | OPGW MAINTENANCE WORK | 23-06-2025 09:00:00 | 30-06-2025 09:00:00 | Nitin Reshwal | 9425804890 | ok, line to be in service
4 | 2025-05-02 13:52 | MR2505/0038 | Continuous | 132KV_20 MVA Emco-i | 132KV_BARWANI | NON-OCCM-WR | augmentation of new 63 MVA transformer | 03-05-2025 11:00:00 | 30-06-2025 19:00:00 | vijay chand saiyam | 9425820043 | sub ld
5 | 2025-06-22 12:03 | MR2506/0444 | Continuous | 132KV_20 MVA GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | X-mer shifting from existing location to Wooden sl | 23-06-2025 10:00:00 | 27-06-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
6 | 2025-06-24 15:13 | MR2506/0509 |  | 220KV_220 KV Bina-Datia Ckt | 400KV_BINA4 | NON-OCCM-MP | for line maintenance work | 25-06-2025 10:00:00 | 25-06-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | as opportunity s/d
7 | 2025-06-24 13:22 | MR2506/0495 |  | 220KV_220 KV Bina Datia | 400KV_BINA4 | NON-OCCM-MP | Flash over disc replacement work and other line | 25-06-2025 10:00:00 | 25-06-2025 19:00:00 | Satish Kumar Bhagat | 9425806916 | ok, through sub ld
8 | 2025-06-24 15:20 | MR2506/0510 |  | 220KV_220 KV Bina-Guna Ckt | 400KV_BINA4 | NON-OCCM-MP | For F/o disc replacement and other line maintenanc | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 | Sanjay Singh Thakur | 9425806936 | ok, through sub ld
9 | 2025-06-23 09:15 | MR2506/0455 | Continuous | 220KV_220 KV BUSCOUPLER & 220 MAIN BUS -2 | 400KV_BINA4 | NON-OCCM-MP | FOR ERECTION OF STRUCTURE AND STRINGING | 24-06-2025 10:00:00 | 27-06-2025 17:00:00 | ANIL MAHOR | 9425805149 | ok
10 | 2025-06-24 15:00 | MR2506/0507 |  | 132KV_132 kV Birsinghpur-Umaria Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | For Jumper cone tightening & other line maintenanc | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 | Jitendra Tiwari | 9425805298 | ok, o&m to be informed
11 | 2025-06-24 12:49 | MR2506/0493 |  | 400KV_400Kv Main Bus-I | 400KV_CHHEGAON4 | NON-OCCM-MP | 400KV BUS TIE R-Phase damaged dropper jumper repai | 25-06-2025 10:00:00 | 25-06-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | emergency approval required from WRLDC
12 | 2025-06-23 18:10 | MR2506/0484 |  | 132KV_132KV Chhindwara-Saori line | 220KV_CHHINDWARA | NON-OCCM-MP | For Feeder bay shifting work at 220KV Sub Chhindwa | 25-06-2025 08:00:00 | 25-06-2025 15:00:00 | Vijay Kumar Tandekar | 9425805095 | ok, any new charging will require FTC approval
13 | 2025-06-24 14:32 | MR2506/0501 |  | 220KV_160 MVA transformer-I make BBL | 220KV_DALODA | NON-OCCM-MP | Rain shield provided on the Buchholz relay | 25-06-2025 10:00:00 | 25-06-2025 14:00:00 | Er. Shailendra Bourasi | 9907246485 | ok, through sub ld
14 | 2025-04-28 13:05 | MR2504/0766 | Continuous | 20MVA_132/33KV_BHEL_X'mer_4 | 220KV_DAMOH | OCCM-MP | augmantation of 20 MVA transformer by 63 mva trans | 28-04-2025 14:00:00 | 30-06-2025 16:00:00 | MK Choubey | 8959559657 | Continuous
15 | 2025-05-07 15:18 | MR2505/0133 | Continuous | 160MVA_220/132KV_BHEL_X'mer_1 | 220KV_HANDIYA | NON-OCCM-MP | for Replacement of Transformer | 08-05-2025 10:00:00 | 08-07-2025 17:00:00 | J.D.Khoria | 9425804975 | Continuous
16 | 2025-06-17 21:54 | MR2506/0387 | Continuous | 400KV_UNIT - 7 | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-06-2025 06:00:00 | 30-06-2025 18:00:00 | Vinay Mishra | 9575074321 | as per system requirement
17 | 2025-06-20 19:03 | MR2506/0431 | Continuous | 400KV_400 KV BUS 2 | 400KV_INDIRASAGAR | NON-OCCM-MP | SF 6 CB maintenance work | 24-06-2025 10:00:00 | 28-06-2025 17:00:00 | SANJAY PATEL | 9424050443 | Continuous
18 | 2025-06-12 16:27 | MR2506/0283 | Daily | 220KV_NORTH ZONE - HATUNIYA CKT-2 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF EXISTING E/W BY 24F OPGW | 15-06-2025 07:00:00 | 25-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
19 | 2025-06-17 18:15 | MR2506/0379 | Daily | 132KV_NIRANJANPUR - JETPURA LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
20 | 2025-06-17 18:13 | MR2506/0378 | Daily | 132KV_NORTHZONE - NIRANJANPUR LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | Deffered
21 | 2025-06-17 18:00 | MR2506/0375 | Daily | 220KV_NORTHZONE - HATUNIYA (PGCIL) CKT-1 LINE | 220KV_INDORE NORTH | NON-OCCM-MP | REPLACEMENT OF 24F OPGW BY 48F OPGW | 21-06-2025 07:00:00 | 26-06-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
22 | 2025-06-23 17:09 | MR2506/0482 | Daily | 220KV_220 KV South Zone - Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R. KANEL | 9425805217 | ok, line to be in service
23 | 2025-06-23 17:04 | MR2506/0481 | Daily | 220KV_220KV Indore (400KV) - Mangliya line | 400KV_INDORE4 | NON-OCCM-MP | Existing 24 Fibre OPGW Wire by 48 Fibre OPGW work | 24-06-2025 07:00:00 | 15-07-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
24 | 2025-06-24 11:48 | MR2506/0489 | Daily | 220KV_220 KV SARNI-ITARSI III LINE | 220KV_ITARSI | NON-OCCM-MP | Resagging work b/w loc.no. 199-218 | 25-06-2025 09:00:00 | 27-06-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
25 | 2025-06-24 11:47 | MR2506/0488 |  | 132KV_132 kV Jabalpur- VFJ ckt-I | 220KV_JABALPUR | NON-OCCM-MP | Disc F/o change at loc. 40 B Ph | 25-06-2025 10:00:00 | 25-06-2025 13:00:00 | Jitendra Tiwari | 9425805298 | o&m consent required
26 | 2025-06-24 15:48 | MR2506/0514 |  | 220KV_220KV Kanwan-Dhar 1st feeder | 220KV_KANWAN2 | NON-OCCM-MP | DTPC Commissioning work | 25-06-2025 11:00:00 | 25-06-2025 15:00:00 | Er. Abhishek Verma | 9340855901 | ok, through sub ld
27 | 2024-11-20 16:32 | MR2411/0430 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok
28 | 2024-11-20 16:36 | MR2411/0431 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 23-06-2025 09:00:00 | 28-06-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok
29 | 2025-06-23 13:35 | MR2506/0465 |  | 132KV_132kV KIRNAPUR-DONGARGARH LINE | 400KV_KIRNAPUR | OCCM-MP | REPLACEMENT WORK OF PID DEFECTIVE F/O DISC | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 | SHRIDHAR KUMAR BHALADHARE | 9425807264 | ok
30 | 2025-06-24 11:40 | MR2506/0487 |  | 132KV_132kV MANDLA-DINDORI LINE | 132KV_MANDLA | NON-OCCM-MP | Emergency Side Tree Cutting & Other Line Maint. | 25-06-2025 10:00:00 | 25-06-2025 18:00:00 | SHRIDHAR KUMAR BHALADHARE | 9425807264 | ok
31 | 2025-06-24 16:05 | MR2506/0517 |  | 220KV_220kV Mandsaur-Nipaniya-2 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 12:30:00 | 25-06-2025 13:00:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
32 | 2025-06-24 14:54 | MR2506/0505 |  | 220KV_220kV Mandsaur-Gurjarkhedi-1 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 10:30:00 | 25-06-2025 11:00:00 | Rajesh Bhuria | 9425806920 | NTPC consent required
33 | 2025-06-24 15:00 | MR2506/0506 |  | 220KV_220kV Mandsaur-Gujarkhedi-2 feeder | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 11:00:00 | 25-06-2025 11:30:00 | Rajesh Bhuria | 9425806920 | NTPC consent required
34 | 2025-06-24 16:01 | MR2506/0516 |  | 220KV_220kV Mandsaur-Nipaniya-1 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 12:00:00 | 25-06-2025 12:30:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
35 | 2025-06-24 16:19 | MR2506/0520 |  | 220KV_220kv Mandsaur-Daloda-1 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 15:00:00 | 25-06-2025 15:30:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
36 | 2025-06-24 16:10 | MR2506/0518 |  | 220KV_220kV Mandsaur-Neemuch-1 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 14:00:00 | 25-06-2025 14:30:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
37 | 2025-06-24 14:26 | MR2506/0498 |  | 220KV_220kV Main Bus-2 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 Maintenance work | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 | Rajesh Bhuria | 9425806920 | as opportunity s/d
38 | 2025-06-23 12:29 | MR2506/0460 |  | 220KV_220 KV Main Bus-II | 400KV_MANDSOUR4 | NON-OCCM-MP | Stringing work of 220 KV Yard | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 | J.P. Parmar | 9425806919 | ok, through sub ld
39 | 2025-06-24 16:13 | MR2506/0519 |  | 220KV_220kV Mandsaur-Neemuch-2 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 14:30:00 | 25-06-2025 15:00:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
40 | 2025-06-24 16:26 | MR2506/0522 |  | 220KV_220kV Mandsaur-Daloda-2 | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-2 connected isolator maintenance wo | 25-06-2025 15:30:00 | 25-06-2025 16:00:00 | Rajesh Bhuria | 9425806920 | ok, through sub ld
41 | 2025-06-24 14:41 | MR2506/0503 |  | 132KV_132kV Sabalgarh - Motijheel Line | 132KV_MOTIJHEEL | NON-OCCM-MP | Line Maintenance work | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 | Pankaj Kumar | 9425805317 | sub ld
42 | 2025-06-16 18:57 | MR2506/0356 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA LINE | 220KV_MUGALIYACHAAP | NON-OCCM-MP | LIVE LINE PERMIT FOR HOT LINE | 17-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | communication consent required
43 | 2025-06-20 11:59 | MR2506/0420 | Daily | 220KV_220 KV BHOPAL MUGALIYACHAAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | OPGW MAINTENANCE WORK | 21-06-2025 09:00:00 | 30-06-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
44 | 2025-06-24 15:59 | MR2506/0515 |  | 220KV_160 MVA XMER NO -3 MAKE BHEL | 220KV_PIPARIYA | NON-OCCM-MP | DC LEKAGE Testing Work | 25-06-2025 13:00:00 | 25-06-2025 17:00:00 | B.K.Jhariya | 9425806831 | ok, through sub ld
45 | 2025-05-08 17:07 | MR2505/0173 | Continuous | 400KV_400kV SSTPH-Pithampur Line Ckt-2 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
46 | 2025-05-08 16:57 | MR2505/0172 | Continuous | 400KV_400kVSSTPH-Pithampur Ckt-1 | 400KV_PITHAMPUR4 | NON-OCCM-MP | Tower Strengthening work | 01-06-2025 08:00:00 | 30-06-2025 18:00:00 | Naresh Pandre | 9425806905 | Deffered
47 | 2025-06-24 13:34 | MR2506/0497 |  | 220KV_220kv Rajgarh-Nalkheda line ckt-II | 220KV_RAJGARH (BIAORA) | NON-OCCM-MP | For Jumper Cone Tightning Work | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 | P.S .Solanki | 9425820041 | ok, through sub ld
48 | 2025-06-24 15:05 | MR2506/0508 |  | 132KV_132KV RAJMILAN-WAIDHAN CKT | 132KV_RAJMILAN | NON-OCCM-MP | FLASH OVER DISC REPLACEMENT | 25-06-2025 11:00:00 | 25-06-2025 17:00:00 | G.L SAHU | 9425805102 | ok
49 | 2025-06-13 14:42 | MR2506/0295 | Daily | 132KV_132kv SAGAR-SAGAR IC 3 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | Work installation of OPGW | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
50 | 2025-06-13 14:38 | MR2506/0294 | Daily | 132KV_132KV SAGAR-SAGAR IC 1 CKT. LINE | 400KV_SAGAR | NON-OCCM-MP | OPGW Work installation (Hot Line Permit | 14-06-2025 07:00:00 | 30-06-2025 19:00:00 | J.P. Asati | 9424445533 | ok, line to be in service
51 | 2025-05-03 11:32 | MR2505/0054 | Continuous | 220KV_100 MVA X-mer Make CGL | 220KV_SARNI | NON-OCCM-MP | X-mer Augmentation work by 160 MVA X-mer AREVA | 05-05-2025 10:00:00 | 10-07-2025 17:00:00 | Er K.K. Choure | 9425801357 | Continuous
52 | 2025-06-24 15:34 | MR2506/0512 |  | 132KV_132 kv Satna - Devendra nagar line | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 | Mr. M.M. Baig | 9425805067 | ok, adani to be informed
53 | 2025-05-21 18:39 | MR2505/0454 |  | 400KV_400 KV SARNI-ISP | 400KV_SATPURA TPS | NON-OCCM-MP | Work of routine testing general checking & mainten | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 | S.S.THAKUR | 9425611244 | ok
54 | 2025-06-20 12:24 | MR2506/0422 | Continuous | 220KV_Bay no 21 tie cum bus coupler breaker | 400KV_SGTPS | NON-OCCM-MP | For overhauling of 220 kv circuit breaker | 23-06-2025 08:00:00 | 26-06-2025 16:00:00 | S Banerjee | 9424352880 | ok
55 | 2025-06-24 14:39 | MR2506/0502 |  | 132KV_132 KV Narsinghpur-Shrinagar DP Line | 132KV_SHRINAGAR | NON-OCCM-MP | Flashover Disc replacement work at Loc.No.477/R-04 | 25-06-2025 10:00:00 | 25-06-2025 18:00:00 | Ashish Kumar | 9425805935 | ok, discom and T&C to be informed
56 | 2025-06-22 13:36 | MR2506/0448 | Continuous | 132KV_132KV SIDHI-MAUGANJ CKT-1&2 | 220KV_SIDHI | NON-OCCM-MP | TOWER MODIFICATION &SHIFTING WORK | 23-06-2025 08:00:00 | 26-06-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
57 | 2025-06-24 12:22 | MR2506/0490 |  | 220KV_220/132 KV 160MVA XMER 1ST | 220KV_SUWASRA2 | NON-OCCM-MP | REPLACEMENTS OF O/C RELAY | 25-06-2025 10:00:00 | 25-06-2025 14:00:00 | SUNIL PANWAR | 9425804939 | ok, through sub ld
58 | 2025-06-24 12:25 | MR2506/0491 |  | 220KV_220/132 KV 160 MVA X-MER 2ND | 220KV_SUWASRA2 | NON-OCCM-MP | REPLACEMENTS OF O/C RELAY | 25-06-2025 14:00:00 | 25-06-2025 18:00:00 | SUNIL PANWAR | 9425804939 | ok, through sub ld
59 | 2025-06-17 17:47 | MR2506/0373 | Daily | 132KV_132 kV Tikamgarh-Badamalhera line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
60 | 2025-06-17 17:49 | MR2506/0374 | Daily | 132KV_132 kV Tikamgarh IC 1st line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW installation work | 20-06-2025 07:00:00 | 30-06-2025 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
61 | 2025-06-24 15:42 | MR2506/0513 |  | 220KV_220kV Tikamgarh-Damoh (PGCIL) Line | 220KV_TIKAMGARH | OCCM-MP | DFO replacement, JCT & other line maintenance work | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
62 | 2025-06-24 13:06 | MR2506/0494 |  | 220KV_220kv Ujjain- Barod ckt.-IInd | 400KV_UJJAIN4 | NON-OCCM-MP | DPR relay installation and pre monsoon bay maint.w | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 | santosh chavraisa | 9425804677 | Deffered due to
62 | 2025-06-21 09:53 | MR2506/0433 | Daily | 400KV_400 KV ASHTA-UJJAIN LINE DCDS(CKT 1&2) | 400KV_UJJAIN4 | OCCM-WR | ONLINE PERMIT WORK | 21-06-2025 10:00:00 | 25-06-2025 19:00:00 | KUMAR SACHINDRA SHARMA | 7415651054 | ok, line to be in service
63 |  | 248347 |  | 220KV-PANDURNA-KALMESHWAR-1 |  | WR-OCCM | E/W Replacement & Routine Maint. Work | 25-06-2025 07:00:00 | 25-06-2025 18:00:00 |  |  | OK All other lines at Pandurna/Kalmeshwar to be in service with AR enabled. SLDC MH to be informed, Load to be managed by SLDC MP/MH
63 |  | 248348 |  | 132KV-MANSAR-MS-PENCH-1 |  | WR-OCCM | For routine maintenance work | 25-06-2025 07:00:00 | 25-06-2025 18:00:00 |  |  | OK Ok, Load to be managed by SLDC MP/MH.
64 |  | 250016 |  | 220KV-INDORE-UJJAIN-2 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 25-06-2025 08:00:00 | 25-06-2025 18:00:00 |  |  | REAL TIME All other lines & ICTs at Indore/Ujjain to be in service with AR enabled. No other element shall be effected. care to be taken.
64 |  | 250021 |  | 220KV-DAMOH-TIKAMGAD-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 |  |  | OK All other lines at Tikamgad to be in service with AR enabled. WR2 to be informed. Load to be managed by SLDC MP
65 |  | 250022 |  | 220KV-RAJGARH-RAJGARH-MP-1 |  | WR-OCCM | FOR LINE MAINTENANCE WORK | 25-06-2025 08:00:00 | 25-06-2025 18:00:00 |  |  | RAL TIME Ckt 2 to be in service. Load to be managed by MPSLD. WR2 to be informed.
65 |  | 250023 |  | 220KV-REWA-SINDHI-MP-2 |  | WR-OCCM | For Line maintenance work | 25-06-2025 10:00:00 | 25-06-2025 17:00:00 |  |  | REAL TIME All other 220 kV lines from Rewa to be in service. Load to be managed by SLDC MP.
66 |  | 250034 |  | 132KV-KIRNAPUR-DONGARGARH-1 |  | WR-OCCM | LINE MAINTENANCE WORK | 25-06-2025 09:00:00 | 25-06-2025 18:00:00 |  |  | OK Ok, Load to be managed by SLDC MP/CG. SLDC CG to be informed.
67 |  | 253389 |  | 220KV-INDORE-INDORE NORTH ZONE-1 |  | WR-OCCM | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 25-06-2025 07:00:00 | 25-06-2025 18:59:00 |  |  | OK A/R in N/A, Line will be in service.
68 |  | 253401 |  | 220KV-INDORE-INDORE NORTH ZONE-2 |  | WR-OCCM | AR from auto to non auto mode for replacement of existing earth wire by 24 Fibre OPGW work | 25-06-2025 07:00:00 | 25-06-2025 18:59:00 |  |  | OK A/R in N/A, Line will be in service.
69 |  |  |  | 500 MVA Xmer--III(T&R) AT 400 KV JULWANIA |  |  | CSD RELAY COMMISSIONING WORK | 25-06-2025 09:00:00 | 26-06-2025 17:00:00 |  |  | OK THROUGH SUB LD