## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-10 | APPROVED OUTAGE LIST FOR DTD. 10.09.25
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-09-09 15:47 | MR2509/0209 |  | 132KV_Shutdown (H/T) of 132 KV Amarpatan-Jhinna DCSS line | 132KV_AMARPATAN | NON-OCCM-WR | charging of 132kv Amarpatan â¿¿Chavar line | 10-09-2025 08:00:00 | 10-09-2025 17:00:00 | Mr. Ramkirti Prajapati | 9407070182 | REALTIME, FTC OF CHAVAR CKT TO BE SUBMITTED
2 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
3 | 2025-09-09 07:57 | MR2509/0197 |  | 220KV_160 MVA X-MER NO. 1 MAKE - CGL | 220KV_BAIRAGARH | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 10-09-2025 09:00:00 | 10-09-2025 18:00:00 | SH. AMBARISH SHRIPAD JOSHI | 7587951085 | OK THROUGH SUB LD
4 | 2025-09-09 15:22 | MR2509/0200 |  | 132KV_50 MVA X-mer | 132KV_BATIYAGARH | NON-OCCM-MP | Post monsoon maintenance | 10-09-2025 11:00:00 | 10-09-2025 17:00:00 | B K Sahu | 9425801433 | OK THROUGH SUB LD
5 | 2025-09-06 15:08 | MR2509/0153 | Daily | 132KV_132 kV Shahdol-Birsingpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
6 | 2025-09-09 09:50 | MR2509/0198 |  | 132KV_63 MVA Transformer | 220KV_CHATARPUR | NON-OCCM-MP | For incoming side damaged jumper replacement work | 10-09-2025 10:00:00 | 10-09-2025 12:00:00 | Brajendra Soni | 9131327770 | OK O&M TO BE INTIMATED
7 | 2025-09-09 16:15 | MR2509/0213 |  | 200MVA_400/220KV_TNR_Xmer_4 | 400KV_CHHEGAON4 | NON-OCCM-MP | post monsoon maintenance work | 10-09-2025 10:00:00 | 10-09-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | OK THROUGH SUB LD
8 | 2025-09-09 15:22 | MR2509/0199 |  | 220KV_220 kV Chhindwara-Pandhurna | 220KV_CHHINDWARA | NON-OCCM-MP | F/o disc replace and Bird guard provide | 10-09-2025 09:00:00 | 10-09-2025 17:00:00 | A.M.shende | 7587951136 | OK, OTHER ELEMENTS TO BE IN SERVICE AT PANDHURNA
9 | 2025-09-06 15:08 | MR2509/0154 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
10 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | RESCHEDULED
11 | 2025-09-09 15:27 | MR2509/0201 |  | 220KV_220 kV Jabalpur- Birsinghpur ckt-II | 220KV_JABALPUR | NON-OCCM-MP | Disc F/o change at loc. C51 Top Phase | 10-09-2025 10:00:00 | 10-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
12 | 2025-09-09 15:41 | MR2509/0207 |  | 220KV_160 MVA transformer -I make BHEL | 220KV_JAORA | NON-OCCM-MP | Post monsoon maintenance work. | 10-09-2025 09:00:00 | 10-09-2025 18:00:00 | Er. Rakesh Kumar Badgotiya | 8305447051 | OK THROUGH SUB LD
13 | 2025-06-30 16:18 | MR2506/0637 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED WRPC CONSENT REQUIRED
14 | 2025-06-30 15:35 | MR2506/0627 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 08:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED WRPC CONSENT REQUIRED
15 | 2025-09-04 16:12 | MR2509/0103 | Daily | 132KV_132 KV Nimarani-II | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 09-09-2025 11:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
16 | 2025-09-04 16:18 | MR2509/0105 |  | 132KV_63 MVA X-mer-II make BBL | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 10-09-2025 10:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
17 | 2025-09-04 16:07 | MR2509/0102 | Daily | 132KV_132 KV Singhana Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
18 | 2025-09-04 16:27 | MR2509/0107 |  | 132KV_132 KV Nimarani-III feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 10-09-2025 10:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
19 | 2025-09-04 16:32 | MR2509/0109 |  | 132KV_63 MVA X-mer-I make BBL | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 10-09-2025 17:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
20 | 2025-09-04 16:14 | MR2509/0104 | Daily | 132KV_132 KV Ultratech-I Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 09-09-2025 11:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
21 | 2025-09-04 16:22 | MR2509/0106 |  | 132KV_132 KV Dhamnod Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 10-09-2025 10:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
22 | 2025-09-04 16:29 | MR2509/0108 |  | 132KV_132 KV Ultratech-II Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 10-09-2025 10:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
23 | 2025-09-04 16:38 | MR2509/0110 |  | 132KV_132 KV Kukshi Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 10-09-2025 17:00:00 | 10-09-2025 18:00:00 | Er. Manoj Randha | 9425820034 | SUB LD
24 | 2025-09-09 16:37 | MR2509/0218 |  | 132KV_40 MVA X-mer BBL | 132KV_MANDLA | NON-OCCM-MP | Oil leakage attending work | 10-09-2025 08:00:00 | 10-09-2025 18:00:00 | R S Bais | 9425163265 | OK
25 | 2025-09-09 15:52 | MR2509/0212 |  | 220KV_50 MVA BBL 220/33 KV | 220KV_NAGDA | NON-OCCM-WR | POST MANSOON MAINTENANCE | 10-09-2025 10:00:00 | 10-09-2025 17:00:00 | VIKRAM DEHARIYA | 7587951150 | SUB LD
26 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | A.R.KANEL | 9425805217 | SUB LD
27 | 2025-09-09 16:26 | MR2509/0217 |  | 220KV_160 MVA-II (CGL) | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | POST MONSOON MAINT WORK | 10-09-2025 10:00:00 | 10-09-2025 17:00:00 | RAJU DAS BAIRAGI | 9425801532 | OK THROUGH SUB LD
28 | 2025-09-09 15:40 | MR2509/0206 |  | 220KV_220 KV Bus-Coupler | 220KV_RATLAM | NON-OCCM-MP | for Safety purpose for maintanance of Auxillary | 10-09-2025 09:00:00 | 10-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | OK THROUGH SUB LD
29 | 2025-09-09 15:36 | MR2509/0203 |  | 220KV_160 MVA X-MER (BHEL)-I st | 220KV_RATLAM | NON-OCCM-MP | for Post mansoon Maintenance & testing work. | 10-09-2025 09:00:00 | 10-09-2025 18:00:00 | NIKHIL DUNGE | 9425801487 | OK THROUGH SUB LD
30 | 2025-09-09 15:31 | MR2509/0202 |  | 132KV_Sarni Betul line | 220KV_SARNI | NON-OCCM-MP | Broken disc replacement & Bird guard installation | 10-09-2025 09:00:00 | 10-09-2025 17:00:00 | SHIV KUMAR | 9425806917 | SUB LD
31 | 2025-09-09 15:50 | MR2509/0211 |  | 220KV_Shutdown (H/T) of 220 kv Satna-Manpur DCDS line | 220KV_SATNA | NON-OCCM-WR | replacement of flash over disc insulator string & | 10-09-2025 09:00:00 | 10-09-2025 17:00:00 | Mr. Ramkirti Prajapati | 9407070182 | OK, Manpur to be intimated
32 | 2025-09-06 11:42 | MR2509/0147 |  | 220KV_220kv ICT NO.1(400/220KV,315 MVA XMER-1) | 220KV_SUKHA | OCCM-WR | R AND Y PHASE CT REPLACEMENT WORK | 10-09-2025 09:00:00 | 10-09-2025 18:00:00 | ashish sonkeshariya | 7587951153 | OK
33 | 2025-09-09 15:48 | MR2509/0210 |  | 220KV_220KV Suwasra- Nipaniya ckt | 220KV_SUWASRA2 | NON-OCCM-MP | Providing M2 DPR Relay work | 10-09-2025 09:00:00 | 10-09-2025 18:00:00 | SUNIL PAWAR | 9425804939 | OK THROUGH SUB LD
34 | 2025-09-09 16:16 | MR2509/0214 |  | 220KV_Opportunity S/D of 220 KV Suwasara- Nipaniya Line | 220KV_SUWASRA2 | NON-OCCM-MP | For Line Maintenance work | 10-09-2025 09:30:00 | 10-09-2025 17:30:00 | Ravindra Kumar Marskole | 9425814080 | OK THROUGH SUB LD
35 | 2025-09-08 16:35 | MR2509/0195 |  | 220KV_220kv Tikamgarh -Damoh (PGCIL) | 220KV_TIKAMGARH | NON-OCCM-MP | Bay maintenance | 10-09-2025 10:00:00 | 10-09-2025 15:00:00 | Pushpendra Kumar soni | 9425806398 | RESCHEDULED FOR 15.09.2025
36 | 2025-09-04 17:19 | MR2509/0111 |  | 220KV_220 KV MAIN BUS | 220KV_UJJAIN | OCCM-WR | HOT POINT ON PGCIL-II MAIN BUS SIDE ISOLATOR JAW | 10-09-2025 09:00:00 | 10-09-2025 17:00:00 | B.C JOSHI | 7587951137 | DEFERRED BY WRLDC DUE TO MULTIPLE OUTAGES
37 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | continue
38 | 2025-09-09 15:39 | MR2509/0205 |  | 132KV_50MVA X-mer TAL | 132KV_UNCHEHRA | NON-OCCM-MP | For attending hot point on 50MVA X-mer CB LV side | 10-09-2025 10:00:00 | 10-09-2025 13:00:00 | Arun kumar kol | 9425802368 | OK ONLY IF O&M CONSENTED
39 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
40 |  |  |  | SHUTDOWN ON 132KV 63 MVA X-MER BBL/ 50 MVA X-MER BHEL | 220 KV KOTAR |  | FOR 33KV MAIN BUS MAINT. WORK | 10-09-2025 11:00:00 | 10-09-2025 13:00:00 |  |  | OK
41 | 2025-09-09 15:39 |  |  | 132KV-PENCH-KANHAN-1 |  | OCCM-WR | MAINTENANCE WORK | 10-Sep-2025 | 09:00 | 10-Sep-2025 | 16:00 | OK
42 | 2025-09-09 15:39 |  |  | 400KV-BINA-MP-BINA-3 |  | OCCM-WR | Simultaneous ouatge of765KV/400KV BINA-ICT-2 &400KV-BINA-MP-BINA-3 required for Bay-420 LBB Testing.Dia to be kept open.Dia to be kept open. | 10-Sep-2025 | 09:00 | 11-Sep-2025 | 17:00 | OK THROUGH SUB LD
43 | 2025-09-09 15:39 |  |  | 400KV/220KV JABALPUR-ICT-1 |  | OCCM-WR | FOR REPLACEMENT OF CTS | 10-Sep-2025 | 08:00 | 10-Sep-2025 | 18:00 | OK,
44 | 2025-09-09 15:39 |  |  | 220KV-KHANDWA-CHHANERA-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 10-Sep-2025 | 09:00 | 10-Sep-2025 | 17:00 | OK THROUGH SUB LD
45 | 2025-09-09 15:39 |  |  | 220KV-BINA-SHIVPURI-1 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 10-Sep-2025 | 10:00 | 10-Sep-2025 | 17:00 | OK THROUGH SUB LD
46 | 2025-09-09 15:39 |  |  | 220KV-SATNA-MP-SATNA-2 |  | OCCM-WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 10-Sep-2025 | 08:00 | 10-Sep-2025 | 17:59 | OK
47 | 2025-09-09 15:39 |  |  | 220KV-ANNUPUR-KOTMIKALA-1 |  | OCCM-WR | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 10-Sep-2025 | 08:00 | 10-Sep-2025 | 17:59 | OK
48 | 2025-09-09 15:39 |  |  | SATPURA - 400KV - BUS 1 |  | OCCM-WR | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400KV-SATPURA-KORADI-1 is required) | 10-Sep-2025 | 08:00 | 10-Sep-2025 | 17:59 | OK
49 | 2025-09-09 15:39 |  |  | 400KV-KORADI-SATPURA-1 |  | OCCM-WR | For replacemnet of Bus-1 PG isolator under ADD CAP at MPGENCO (Simultaneous outage of 400kV Bus-1 is required at Sarni S/S of MPGENCO) And CVT Replacement of 400KV-SATPURA-KORADI-1 under ADD CAP at MPGENCO | 10-Sep-2025 | 08:00 | 10-Sep-2025 | 17:59 | OK
S/I, SLDC MPPTCL JABALPUR