## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-01
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:08 | MR2508/0326 | Daily | 220KV_220KV Anuppur Kotmikala ckt-2 | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work due to Low Ground clearance ma | 31-08-2025 08:00:00 | 08-09-2025 18:00:00 | Jitendra Tiwari | 9425805298 | OK
2 | 2025-08-31 15:36 | MR2508/0439 | Continuous | 220KV_220kv Badnawar-Barnagar ckt-1 | 400KV_BADNAWAR | NON-OCCM-MP | For installation of double DPR | 01-09-2025 10:00:00 | 02-09-2025 18:00:00 | Er. ABHISHEK VERMA | 9340855901 | OK THROUGH SUB LD
3 | 2025-08-30 13:55 | MR2508/0415 |  | 132KV_40 MVA T &R transformer | 132KV_BANDA | OCCM-MP | Post mansoon maintenance &oil leakage attend | 01-09-2025 11:00:00 | 01-09-2025 17:00:00 | P D Goutam | 9425808329 | OK
4 | 2025-08-31 14:36 | MR2508/0434 |  | 132KV_132KV BINA MUNGAOLI CKT-2 | 220KV_BINA | NON-OCCM-MP | FOR F/O DISC INSULATOR REPLACEMENT WORK | 01-09-2025 10:00:00 | 01-09-2025 18:00:00 | SANJAY SINGH THAKUR | 9425806936 | OK
5 | 2025-08-31 14:55 | MR2508/0436 |  | 132KV_132 KV Chhatarpur-Bijawer Tap Nowgong Bay | 220KV_CHATARPUR | NON-OCCM-MP | for CT Tan delta measurement work | 01-09-2025 09:30:00 | 01-09-2025 13:30:00 | Brajendra Soni | 9131327770 | OK, 132 KV LAVKUSHNAGR- AJAYGARH CKT TO BE IN SERVICE
6 | 2025-08-31 10:34 | MR2508/0424 |  | 132KV_63 MVA-II (BBL) X-mer | 400KV_CHHEGAON4 | NON-OCCM-MP | Post monsoon maintenance | 01-09-2025 10:00:00 | 01-09-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | SUB LD
7 | 2025-08-31 11:34 | MR2508/0425 |  | 132KV_132/33 KV 40 MVA x-mer -ll(EMCO) | 132KV_DATIA1 | NON-OCCM-MP | Post mansoon maintenance | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | Atul shakya | 9425806928 | SUB LD
8 | 2025-08-29 11:42 | MR2508/0399 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION FROM COMMUNICATION REQUIRED
9 | 2025-08-30 10:24 | MR2508/0413 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 30-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION FROM COMMUNICATION REQUIRED
10 | 2025-08-31 16:31 | MR2508/0440 |  | 220KV_220KV SOUTH ZONE-INDORE-III | 220KV_INDORE-SZ | NON-OCCM-MP | bay maintenance and measurement Tan delta of CT | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | DHARMENDRA KUSHWAHA | 9425802801 | OK THROUGH SUB LD
11 | 2025-08-29 13:01 | MR2508/0403 | Daily | 220KV_220KV Indore (400KV â¿¿ Mangliya Line. | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION FROM COMMUNICATION REQUIRED
12 | 2025-08-31 11:39 | MR2508/0427 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_INDORE-SZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 31-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION FROM COMMUNICATION REQUIRED
13 | 2025-08-26 18:22 | MR2508/0354 | Continuous | 132KV_132 KV JBP-SAHPURA DP LINE | 220KV_JABALPUR | OCCM-MP | REPLACEMENT OF TOWER LOC NO 5 | 28-08-2025 10:00:00 | 02-09-2025 19:00:00 | RAJESH TIWARI | 7898239595 | CONTINUE
14 | 2025-08-29 15:51 | MR2508/0411 |  | 220KV_220kV Julwaniya-Sendhwa-2 ckt. | 400KV_JULWANIYA4 | NON-OCCM-MP | Main DPR-2 relay & DTPC Commissioning work | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | Er. M. L. Badoleji | 9131865464 | OK THROUGH SUB LD
15 | 2025-08-31 16:45 | MR2508/0441 |  | 220KV_220KV Julwania - Sendhwa DCDS Ckt-II line | 400KV_JULWANIYA4 | NON-OCCM-MP | Jumper tightening & Other line maintenance work. | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | Dinesh More | 9425806860 | OK THROUGH SUB LD
16 | 2025-06-30 16:15 | MR2506/0636 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC APPROVAL REQUIRED
17 | 2025-06-30 15:33 | MR2506/0626 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 01-09-2025 09:00:00 | 06-09-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC APPROVAL REQUIRED
18 | 2025-08-31 12:46 | MR2508/0430 |  | 220KV_160MVA CGL Xmer | 400KV_KATNI4 | NON-OCCM-MP | For replacement of 132kv C&R panel | 01-09-2025 10:00:00 | 01-09-2025 18:00:00 | SK chaturvedi | 9425806938 | OK
19 | 2025-08-29 11:47 | MR2508/0400 | Daily | 220KV_220KV Indore (400KV) â¿¿ South Zone (I/C- 3) Line | 220KV_MANGLIA2 | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 29-08-2025 07:00:00 | 03-09-2025 19:00:00 | A.R.KANEL | 9425805217 | DATA REROUTING REQUIRED AND CONFIRMATION FROM COMMUNICATION REQUIRED
20 | 2025-08-31 14:42 | MR2508/0435 |  | 33KV_33kV Main Bus | 132KV_NAINPUR | NON-OCCM-MP | newly constructed 33kv B/Cconnect to 33kv Mainbus | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | Shri Sandeep Damahe | 9425805009 | OK IF O&M CONSENT PROVIDED
21 | 2025-08-29 15:24 | MR2508/0408 |  | 132KV_50MVA X-MER-1 | 132KV_PHOOLBAGH GIS | NON-OCCM-MP | FOR POST MOONSOON MAINTENANCE | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | RAKSHA CHAPPARIYA | 6265080313 | SUB LD
22 | 2025-08-30 17:53 | MR2508/0422 |  | 400KV_400KV MAIN BUS-II | 400KV_PITHAMPUR4 | NON-OCCM-MP | Bus maintenance work | 01-09-2025 11:00:00 | 01-09-2025 18:00:00 | Shri Rajudas Bairagi | 9425801532 | OK THROUGH SUB LD, ALL ELEMENTS TO BE IN SERVICE THROUGH 220KV MAIN BUS -1
23 | 2025-08-31 13:38 | MR2508/0432 |  | 220KV_220kv Ratangarh - Neemuch -II | 220KV_RATANGARH | NON-OCCM-MP | DTPC carrier protection cable connecting work | 01-09-2025 11:00:00 | 01-09-2025 15:00:00 | S.H. Mansuri | 9755872660 | OK THROUGH SUB LD
24 | 2025-08-31 12:56 | MR2508/0431 |  | 220KV_160MVA-I AREVA | 220KV_SABALGARH | NON-OCCM-MP | Post Monsoon Maintenance | 01-09-2025 10:00:00 | 01-09-2025 18:00:00 | Er D D Mahour | 9425805742 | OK THROUGH SUB LD
25 | 2025-08-30 17:11 | MR2508/0419 |  | 132KV_SARNI KHAPASWAMI | 220KV_SARNI | NON-OCCM-MP | Flash over disc replacement & other line maint. wo | 01-09-2025 09:00:00 | 01-09-2025 17:00:00 | SHIV KUMAR | 9425806917 | SUB LD
26 | 2025-08-31 12:31 | MR2508/0429 |  | 132KV_63 MVA Xmer BBL | 220KV_SATNA | NON-OCCM-MP | For attending damaged conductor | 01-09-2025 11:00:00 | 01-09-2025 14:00:00 | Ravi Pandey | 9425805296 | OK, O&M TO BE INTIMATED
27 | 2025-08-31 11:35 | MR2508/0426 |  | 132KV_132kV Seoni Katangi | 132KV_SEONI1 | NON-OCCM-MP | Rectification of Drone Survey Defect | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | S. K. Nadekar | 9415806848 | OK O&M TO BE INTIMATED
28 | 2025-08-31 15:29 | MR2508/0438 |  | 220KV_220 kV Birsinghpur TPH-Shahdol Circuit | 400KV_SGTPS | NON-OCCM-MP | For replace of damaged OPGW | 01-09-2025 10:00:00 | 01-09-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK
29 | 2025-08-31 14:14 | MR2508/0433 |  | 132KV_132 KV Jabalpur - Shahpura line | 132KV_SHAHPURA | NON-OCCM-MP | Flashover Disc replacement work at Tension Loc.No. | 01-09-2025 10:00:00 | 01-09-2025 18:00:00 | Ashish Kumar | 9425805935 | OK, LINE ALREADY UNDER S/D
30 |  |  |  | 220KV-ANNUPUR-KOTMIKALA-2 |  | MP CG | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 2025-09-01 08:00 | 01-09-2025 18:00:00 |  |  | OK
31 |  |  |  | 400KV-BADNAWAR-RAJGARH-1 |  | POWERGRID-WR2 (PGCIL),MP | For Attending Hotspot in Line Isolator of Line Bay, Non auto mode of ckt 2 is required . Dia to be kept open at both ends. | 2025-09-01 10:00 | 2025-09-01 10:00 |  |  | OK THROUGH SUB LD
32 |  |  |  | 220KV-AJAYGARH-SATNA-1 |  | MP | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 2025-09-01 10:00 | 2025-09-01 10:00 |  |  | OK