## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-29
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-28 15:53 | MR2510/0654 |  | 132KV_40 MVA BBL Xmer | 132KV_AMARPATAN | NON-OCCM-MP | Testing work of 40 MVA TELK Xmer | 29-10-2025 10:00:00 | 29-10-2025 17:00:00 | Arun Kumar | 9131207339 | o&m consent required
2 | 2025-10-28 13:39 | MR2510/0638 |  | 50MVA_132/33KV_BHEL_Xmer_1 | 132KV_CHOURAI | NON-OCCM-MP | Post monsoon Maintenance work | 29-10-2025 10:00:00 | 29-10-2025 17:00:00 | S.K.OKTE | 7587951132 | ok
3 | 2025-10-16 17:16 | MR2510/0478 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | M.M. BAIG | 9425805067 | Deffered
4 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
5 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
6 | 2025-10-28 16:04 | MR2510/0656 |  | 220KV_160 MVA X-MER NO. 2ND EMCO | 220KV_DEWAS | NON-OCCM-WR | 132 KV I/C R PHASE C.T. CLAMP HOT POINT ATTANDING | 29-10-2025 10:00:00 | 29-10-2025 16:00:00 | ARVIND KUMAR JOSHI | 9425801305 | ok, through sub ld
7 | 2025-10-28 15:37 | MR2510/0651 |  | 220KV_100MVA X-MER 3 IMP MAKE | 220KV_GUJARKHEDI | NON-OCCM-MP | POST MANSOON MAINTANANCE & TESTING WORK | 29-10-2025 14:00:00 | 29-10-2025 20:00:00 | SUNIL PAWAR | 9425804939 | ok, through sub ld
8 | 2025-10-28 16:01 | MR2510/0655 |  | 220KV_160MVA-I MAKE BHEL | 220KV_INDORE-SZ | NON-OCCM-MP | POST MONSOON MAINTENCE | 29-10-2025 09:00:00 | 29-10-2025 17:00:00 | DHARMENDRA KUSHWAHA | 9425802801 | ok, through sub ld
9 | 2025-10-27 11:50 | MR2510/0608 | Daily | 220KV_220 KV Itarsi-Handia Ckt-II | 220KV_ITARSI | NON-OCCM-MP | Replacement of Single to Double disc insut.string | 28-10-2025 09:00:00 | 30-10-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
10 | 2025-10-28 14:41 | MR2510/0648 |  | 220KV_220KV PGCIL No.-01 | 220KV_ITARSI | OCCM-MP | Bay maintenance work | 29-10-2025 07:00:00 | 29-10-2025 17:00:00 | J.D.Khoria | 9425804975 | ok, through sub ld
11 | 2025-09-18 13:12 | MR2509/0414 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | SHRI M.M. BAIG | 9425805067 | Deffered
12 | 2025-10-28 13:42 | MR2510/0640 |  | 220KV_200 MVA X-MER MAKE CGL | 220KV_MALANPUR | NON-OCCM-MP | POST MONSOON MAINTEMANCE WORK | 29-10-2025 10:00:00 | 29-10-2025 17:00:00 | VIKRAM AHIRWAR | 9425805415 | ok, through sub ld
13 | 2025-10-21 20:41 | MR2510/0507 |  | 220KV_KHANDWA-PG-OMKARESHWAR_Ckt | 220KV_OMKARESHWAR | NON-OCCM-WR | Annual Maintenance | 29-10-2025 09:30:00 | 29-10-2025 18:00:00 | Pankaj Sharma | 7898703187 | ok, through sub ld
14 | 2025-10-21 20:46 | MR2510/0508 |  | 220KV_Main Bus A and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 29-10-2025 09:30:00 | 29-10-2025 18:00:00 | Pankaj Sharma | 7898703187 | ok
15 | 2025-10-28 12:17 | MR2510/0632 |  | 220KV_200MVA X-mer CG Power | 220KV_PANDHURNA | NON-OCCM-MP | Leakage from air leak detector /cops relay | 29-10-2025 12:00:00 | 29-10-2025 15:00:00 | Sanjay Shende | 9425811447 | ok
16 | 2025-10-28 14:39 | MR2510/0647 |  | 132KV_132/33KV 50MVA X-MER BBL | 132KV_PATAN | NON-OCCM-MP | POST MONSOON MAINTENANCE AND TESTING WORK | 29-10-2025 10:00:00 | 29-10-2025 18:00:00 | RAHUL GAJBHIYE | 9425801304 | ok
17 | 2025-10-28 15:49 | MR2510/0653 |  | 132KV_132KV 50MVA X-MER-2 MAKE ATLANTA | 132KV_PONDER | NON-OCCM-MP | Post mansoon bay maintenance and testing work | 29-10-2025 10:00:00 | 29-10-2025 17:00:00 | Rajesh Kumar Chaturvedi | 9425805203 | o&m consent required
18 | 2025-10-28 15:23 | MR2510/0650 |  | 220KV_160 MVA X-mer-II make AREVA | 220KV_RAJGARH DHAR | NON-OCCM-MP | Post monsoon maintenance work. | 29-10-2025 10:00:00 | 29-10-2025 17:00:00 | Er. Manoj Randha | 9425820034 | ok, through sub ld
19 | 2025-10-28 13:52 | MR2510/0641 |  | 132KV_40MVA BBL XMER | 132KV_RAMPUR BAGHELAN | NON-OCCM-MP | POST MONSOON MAINTENANCE | 29-10-2025 10:30:00 | 29-10-2025 18:00:00 | KANISHKA SINGH | 9425804656 | ok
20 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
21 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
22 | 2025-10-28 13:39 | MR2510/0639 |  | 132KV_Sarni Betul | 220KV_SARNI | NON-OCCM-MP | Broken Disc Replacement work and Bird guard insta | 29-10-2025 09:00:00 | 29-10-2025 17:00:00 | SHIV KUMAR | 9425806917 | sub ld
23 | 2025-09-05 17:34 | MR2509/0126 | Continuous | 400KV_SARNI-ASHTA LINE -I | 400KV_SATPURA TPS | NON-OCCM-MP | Work of complete overhauling & testing of 400KV br | 27-10-2025 09:00:00 | 29-10-2025 18:00:00 | YASHWANT WARATHE | 9425611046 | Deffered
24 | 2025-10-28 14:27 | MR2510/0644 |  | 132KV_132KV Seoni-Interconnector ckt-1 | 132KV_SEONI1 | NON-OCCM-MP | RYB ph CT Tan- delta measurement & testing work | 29-10-2025 09:00:00 | 29-10-2025 13:00:00 | Ramkumar Meshram | 7587951054 | ok
25 | 2025-10-28 14:21 | MR2510/0643 |  | 132KV_132KV Seoni -Nainpur Line | 132KV_SEONI1 | NON-OCCM-MP | RYB ph CT Tan -Delta Measurement & testing work | 29-10-2025 14:00:00 | 29-10-2025 18:00:00 | Ramkumar Meshram | 7587951054 | ok
26 | 2025-10-28 12:20 | MR2510/0633 |  | 132KV_40 MVA BBL X MER | 132KV_SHAHPURA | NON-OCCM-MP | POST MONSOON MAINTENANCE | 29-10-2025 10:00:00 | 29-10-2025 18:00:00 | H.L.KOSTHA | 7587951105 | ok
27 | 2025-10-28 14:31 | MR2510/0646 |  | 220KV_160 MVA transformer no 2nd BBL | 220KV_SHEOPUR KALAN2 | NON-OCCM-MP | post monsoon maintenance & RELAY testing work at 2 | 29-10-2025 10:00:00 | 29-10-2025 17:00:00 | I.A KHAN | 6264419968 | ok, through sub ld
28 | 2025-10-28 15:07 | MR2510/0649 |  | 132KV_132 Kv Tikamgarh I/C.-IInd Line | 220KV_TIKAMGARH | NON-OCCM-MP | JCT/AH/VD Tightening, T/C & Other line Maint. | 29-10-2025 10:00:00 | 29-10-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, o&m shall be informed
29 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
30 | 2025-10-28 16:14 | MR2510/0657 |  | 400KV_220 KV UJJAIN ( 400 KV SS UJN) BADOD CKT I ST | 400KV_UJJAIN4 | NON-OCCM-MP | LINE MAINTENANCE WORK | 29-10-2025 09:00:00 | 29-10-2025 17:00:00 | KUMAR SACHINDRA SHARMA | 7415651054 | ok, through sub ld
31 | 2025-10-27 15:02 | MR2510/0621 | Continuous | 132KV_40 MVA XMER | 132KV_UMARIYA | NON-OCCM-MP | OLTC OIL LEAKAGE ATTENDING & 33KV RYB CT REPLACEME | 28-10-2025 09:00:00 | 29-10-2025 18:00:00 | TOSHAN SINGH | 9425809482 | Continuous
32 |  | 264487 | Daily | 400KV-DAMOH-BIRSINGPUR-1 | 400 | POWERGRID_WR2 | ATTENDING S/D NATURE DEFECTS IN LINE,AMP Work of of Line terminal equipment and its BAY, Non auto mode of ckt 2 is required . Dia to be kept open at both ends. | 29-Oct-2025 | 08:00 | 29-Oct-2025 | 18:00 | ok
33 |  | 265241 | Continous | 400KV-KORADI-SATPURA-1 | 400 | POWERGRID_WR2 | For CT Replacement of 400KV-SATPURA-KORADI-1 under ADD CAP at MPGENCO | 29-Oct-2025 | 09:00 | 31-Oct-2025 | 20:00 | deffered by wrldc
34 |  | 264947 | Daily | 400KV-NAGDA-SHUJALPUR-1 | 400 | POWERGRID_WR2 | Insulator replacement and shutdown defect rectification, Non auto of 400KV-NAGDA-SHUJALPUR-2, . Dia to be kept open at both ends. | 29-Oct-2025 | 09:00 | 29-Oct-2025 | 18:00 | ok
35 |  | 265987 | Daily | 220KV-BHANPURA-RANPUR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 29-Oct-2025 | 08:00 | 29-Oct-2025 | 18:00 | real time
36 |  | 265984 | Daily | 220KV-GWALIOR-MAHALGAON-3 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 29-Oct-2025 | 09:00 | 29-Oct-2025 | 17:00 | real time
37 |  | 265985 | Daily | 220KV-ITARSI-MP-ITARSI-1 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT ITARSI MPPTCL SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 29-Oct-2025 | 07:00 | 29-Oct-2025 | 17:00 | ok, through sub ld
38 |  | 265986 | Daily | 220KV-DAMOH-TIKAMGAD-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 29-Oct-2025 | 09:00 | 29-Oct-2025 | 18:00 | real time
39 |  | 265988 | Daily | 220KV-RAJGARH-DHAR-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 29-Oct-2025 | 08:00 | 29-Oct-2025 | 18:00 | real time
40 |  | 265989 | Daily | 220KV-REWA-REWA-MP-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 29-Oct-2025 | 10:00 | 29-Oct-2025 | 17:00 | real time
41 |  | 272668 | Daily | 220KV-KHANDWA-OMKARESHWAR-1 | 220 | MP_SLDC | for annual maintenance of switchyard equipments | 29-Oct-2025 | 09:30 | 29-Oct-2025 | 17:59 | ok, through sub ld