## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-27
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
2 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
3 | 2025-07-25 18:37 | MR2507/0415 |  | 132KV_132KV Main Bus at 132KV sub Mandla | 132KV_MANDLA | NON-OCCM-MP | for Overhead stringing & Main Bus Isolator Jumper | 27-07-2025 06:00:00 | 27-07-2025 10:00:00 | Vijay Kumar Tandekar | 9425805095 | ok, any new charging shall be done only after FTC completion
4 | 2025-07-26 12:03 | MR2507/0417 |  | 132KV_40 mva x-mer bbl | 132KV_MANDLA | NON-OCCM-MP | 33 kv vcb replacement work | 27-07-2025 06:00:00 | 27-07-2025 10:00:00 | R S BAIS | 9425163265 | ok
5 | 2025-07-24 14:21 | MR2507/0386 | Daily | 220KV_220KV Neemuch Mandsaur Circuit Ist | 220KV_NEEMUCH | NON-OCCM-MP | only hotline permit | 25-07-2025 08:00:00 | 27-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | ok, line to be in service
6 | 2025-07-24 14:16 | MR2507/0385 | Continuous | 220KV_220KV Neemuch-Mandsaur Circuit IInd | 220KV_NEEMUCH | NON-OCCM-MP | OPGW Work | 25-07-2025 09:00:00 | 27-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | Continuous
7 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
8 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
9 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
10 | 2025-07-25 10:36 | MR2507/0400 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 163-165 | 26-07-2025 10:00:00 | 27-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
11 | 2025-07-25 10:16 | MR2507/0399 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 163-164 | 26-07-2025 10:00:00 | 27-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
12 | 2025-07-25 10:16 |  |  | 220KV Sagar BEGUMGANJ Line-2 (Bay No-204) | 220/132/33kV Begumganj SS(MPPTP-IIL) | NON-OCCM-MP | for Bay maintenance and testing work. | 2025-07-27 09:30 | 27-07-2025 18:00:00 |  |  | ok
13 |  |  |  | 160MVA ICT-2(Bay No-207 HV SIDE Bay & 107 IV SIDE Bay | 220/132/33kV Begumganj SS(MPPTP-IIL) | NON-OCCM-MP | for Bay maintenance and testing work. | 2025-07-27 09:30 | 27-07-2025 18:00:00 |  |  | OK,THRU SUBLD
13 |  |  |  | 220KV Main Bus-2 | 220/132/33kV Begumganj SS(MPPTP-IIL) | NON-OCCM-MP | Bay maintenance and testing work | 2025-07-27 09:30 | 27-07-2025 18:00:00 |  |  | ok
14 |  |  |  | 220 KV Bus coupler(Bay No-208) Bay maintenance and testing work | 220/132/33kV Begumganj SS(MPPTP-IIL) | NON-OCCM-MP | for Bay maintenance and testing work. | 2025-07-27 09:30 | 27-07-2025 18:00:00 |  |  | ok
15 | 2025-07-25 10:16 | 257843 |  | 132KV-DHARNI-NEPANAGAR-1 |  |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 27-Jul-2025 | 27-Jul-2025 |  |  | ok