## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-16 |  |  | APPROVED OUTAGE LIST FOR DATED 16.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-15 12:58 | MR2508/0194 |  | 220KV_Anuppur No.2 | 220KV_AMARKANTAK | OCCM-WR | 295 ABC trip coil circuit unhealthy | 16-08-2025 09:00:00 | 16-08-2025 14:00:00 | Vijay Kothari | 9425808910 | ok
2 | 2025-08-11 17:24 | MR2508/0154 | Daily | 220KV_220 kV Anuppur- Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | For Re-sagging work at loc. 424-425 | 16-08-2025 08:00:00 | 19-08-2025 18:00:00 | Jitendra Tiwari | 9425805298 | Not approved by WRPC for 16-17
3 | 2025-08-15 12:19 | MR2508/0192 |  | 132KV_132kV Banmore - J.K.Tyre Line | 132KV_BANMORE | NON-OCCM-MP | Line Maintenance work | 16-08-2025 10:00:00 | 16-08-2025 14:00:00 | Pankaj Kumar | 9425805317 | sub ld
4 | 2025-08-15 09:20 | MR2508/0190 |  | 132KV_132 kV Chhatarpur â¿¿ Khajuraho Ckt-II Line | 220KV_CHATARPUR | NON-OCCM-MP | AH/VD Tightening & other line maintenance work | 16-08-2025 10:00:00 | 16-08-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
5 | 2025-08-15 11:20 | MR2508/0191 |  | 132KV_63MVA X-MER No.I Make BBL | 132KV_HARDA | NON-OCCM-MP | 63 MVA Xmer 33 KV Incoming NO.I CB Timing work | 16-08-2025 12:00:00 | 16-08-2025 14:00:00 | Sh.J.D.Khoria | 9425804975 | sub ld
6 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
7 | 2025-06-30 15:17 | MR2506/0623 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
8 | 2025-06-30 16:06 | MR2506/0632 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 11-08-2025 09:00:00 | 16-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
9 | 2025-08-14 22:22 | MR2508/0189 |  | 132KV_Regarding shutdown required on 132KV Kirnapur- Moil Line (ldeally charge up to dead end tower near 132KV Moil S/s) for Flashover polymer Insulator replacement work. | 400KV_KIRNAPUR | NON-OCCM-MP | for Flashover polymer Insulator replacement work | 16-08-2025 09:00:00 | 16-08-2025 18:00:00 | Vijay Kumar Tandekar | 9425805095 | ok, line to be charged as per the present configuration after s/d
10 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | ok, line to be in service
11 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
12 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
13 | 2025-08-14 17:15 | MR2508/0185 |  | 400KV_Rajgarh (PGCIL)-SSP CKT-2 | 400KV_RAJGARH-PG | OCCM-MP | for line maintenance work. | 16-08-2025 10:00:00 | 16-08-2025 18:00:00 | V.R. Panadia | 9425802330 | Deffered by WRLDC due to High Generation at SSP
14 | 2025-08-10 17:45 | MR2508/0134 | Continuous | 132KV_132KV RAJMILAN-JANAKPUR (CGPTCL) CKT | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
15 | 2025-08-10 17:51 | MR2508/0135 | Continuous | 132KV_132KV Rajmilan-Dongrital ckt | 132KV_RAJMILAN | NON-OCCM-MP | Tower Erection work | 11-08-2025 08:00:00 | 16-08-2025 18:00:00 | G.L SAHU | 9425805102 | Continuous
16 | 2025-08-15 14:25 | MR2508/0195 |  | 132KV_132kv Sabalgarh Motijheel Ckt | 220KV_SABALGARH | NON-OCCM-MP | Line Maintenance work | 16-08-2025 09:00:00 | 16-08-2025 17:00:00 | SURAJ PAWAR | 9425814079 | sub ld
17 | 2025-08-14 15:29 | MR2508/0183 |  | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of flashover disc insulator | 16-08-2025 10:00:00 | 16-08-2025 13:00:00 | S.K. Nadekar | 9425806848 | ok
18 | 2025-08-14 15:36 | MR2508/0184 |  | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of flashover disc insulator | 16-08-2025 14:00:00 | 16-08-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
19 | 2025-08-15 14:28 | MR2508/0196 |  | 132KV_40 MVA X-MER BBL NO.-1 | 132KV_VFJ | NON-OCCM-MP | CT TO LINE ISOLATOR R PHASE CLAMP HOT POINT | 16-08-2025 10:00:00 | 16-08-2025 14:00:00 | AMIT KUMAR DAHIYA | 9425806926 | o&m consent required
20 |  |  |  | INDORE - 220KV - BUS 2 | POWERGRID-WR2 (PGCIL) |  | BUS AMP Work | 16-Aug-2025 | 09:00 | 16-Aug-2025 | 18:00 | ok
21 |  |  |  | 400KV-NAGDA-DEHGAM-2 | POWERGRID-WR2 (PGCIL) |  | Diffrential Realy Retrofitting work. Dia to be kept both ends. | 16-Aug-2025 | 09:00 | 16-Aug-2025 | 18:00 | ok
22 |  |  |  | 220KV-MEHGAON-AURIYA-1 | NLDC,MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 16-Aug-2025 | 09:00 | 16-Aug-2025 | 17:00 | real time
23 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 16-Aug-2025 | 07:00 | 16-Aug-2025 | 18:59
S/I SLDC JABALPUR