## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-18 |  |  | APPROVED OUTAGE LIST FOR DATED 18.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-16 14:51 | MR2507/0226 |  | 132KV_Shutdown (H/T) of 132 KV Amarpatan-Jhinna DCSS line | 132KV_AMARPATAN | NON-OCCM-WR | purpose of bay shifting work | 18-07-2025 10:00:00 | 18-07-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | forward through T&C, first confirm the status of FTC of new bay
2 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
5 | 2025-07-17 15:01 | MR2507/0242 |  | 220KV_220KV Barwaha Handiya line | 220KV_BARWAHA | NON-OCCM-MP | Line maintnancework | 18-07-2025 10:00:00 | 18-07-2025 18:00:00 | Naresh Pandre | 9425806905 | ok, through sub ld
6 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
7 | 2025-07-14 18:13 | MR2507/0185 | Continuous | 132KV_20MVA_GEC_X-mer | 220KV_BETUL | NON-OCCM-MP | shifting from existing foundation to wooden sleepe | 15-07-2025 10:00:00 | 18-07-2025 17:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
8 | 2025-07-17 14:51 | MR2507/0240 |  | 220KV_CHHEGAON4-SINGHAJI TPS_Ckt_2 | 400KV_CHHEGAON4 | NON-OCCM-MP | CVT Wiring work | 18-07-2025 10:00:00 | 18-07-2025 18:00:00 | Shri Ganesh Mansare | 9425802441 | ok, through sub ld
9 | 2025-07-17 15:33 | MR2507/0246 |  | 220KV_220 kV Bus tie | 220KV_CHICHLI | NON-OCCM-MP | CT testing Work | 18-07-2025 11:00:00 | 18-07-2025 17:00:00 | Rajesh chaturvedi | 9425805203 | deferred due to bus outage at Itarsi
10 | 2025-07-17 14:41 | MR2507/0239 |  | 220KV_220 KV Nagda â¿¿ Daloda ckt-1st. | 220KV_DALODA | NON-OCCM-MP | for Line maintenance work | 18-07-2025 10:00:00 | 18-07-2025 18:00:00 | Kumar Vishal | 9425805018 | ok, through sub ld
11 | 2025-07-15 17:02 | MR2507/0203 |  | 400KV_400 KV ISP-NAGDA | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 18-07-2025 10:00:00 | 18-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | deferred due to high ISP generation
12 | 2025-07-15 16:01 | MR2507/0200 |  | 220KV_220KV Main Bus No.-2 | 220KV_ITARSI | NON-OCCM-MP | For Aug. Bus Tie single zebra to twin zebra | 18-07-2025 10:00:00 | 18-07-2025 15:00:00 | J.D.Khoriya | 9425804975 | ok, through sub ld
13 | 2025-07-17 14:12 | MR2507/0236 |  | 220KV_220 KV Jabalpur-Narsinghpur line ckt-I | 220KV_JABALPUR | NON-OCCM-MP | Flashover disc replacement Work at Loc.No. 33/R - | 18-07-2025 10:00:00 | 18-07-2025 18:00:00 | Ashish Kumar | 9425805935 | deferred due to bus outage at Itarsi
14 | 2025-07-17 14:57 | MR2507/0241 |  | 220KV_220kV Julwaniya-Kukshi Ckt.-2 | 400KV_JULWANIYA4 | NON-OCCM-MP | R ph CT secondary terminal box oil leakage attend | 18-07-2025 09:30:00 | 18-07-2025 16:00:00 | Er. Mannalal Badole | 9131865464 | as opportunity shutdown
15 | 2025-07-17 14:27 | MR2507/0237 |  | 220KV_220KV Julwania-Kukshi DCDS Ckt-2nd line | 400KV_JULWANIYA4 | NON-OCCM-MP | Jumper tightening & other line maintenance work. | 18-07-2025 09:30:00 | 18-07-2025 16:00:00 | Dinesh More | 9425806860 | ok, through sub ld
16 | 2024-11-20 16:49 | MR2411/0436 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | deffered, not in WR list
17 | 2024-11-20 16:54 | MR2411/0437 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | deferred
18 | 2025-07-12 10:50 | MR2507/0161 | Continuous | 132KV_132 KV Khurai-Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | Extension of continous Sd for Modification work | 12-07-2025 07:00:00 | 18-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | continuous
19 | 2025-07-17 14:35 | MR2507/0238 |  | 220KV_220KV Mandsour-Daloda-2 | 400KV_MANDSOUR4 | OCCM-MP | additional DPR -2 connecting & Bay Maintenance wor | 18-07-2025 12:00:00 | 18-07-2025 18:00:00 | Chandraprakash Dhakad | 7587951067 | ok, through sub ld
20 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
21 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
22 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
23 | 2025-07-17 11:16 | MR2507/0233 |  | 220KV_220 kV Panagar- Amarkantak | 220KV_PANAGAR | NON-OCCM-MP | Disc Change at loc, 286 M Ph | 18-07-2025 10:00:00 | 18-07-2025 18:00:00 | Jitendra Tiwari | 9425805298 | ok
24 | 2025-07-16 14:17 | MR2507/0224 |  | 400KV_400KV PITHAMPUR-BADNAWAR CKT-II | 400KV_PITHAMPUR4 | NON-OCCM-MP | Bay maintenance & Relay testing work | 18-07-2025 11:00:00 | 18-07-2025 18:00:00 | Mr. Ankit Prajapati | 9131296643 | ok, through sub ld
25 | 2025-07-17 13:15 | MR2507/0234 |  | 132KV_132KV Ratlam- RAILWAY TRACTION Ckt-I both end | 220KV_RATLAM | NON-OCCM-MP | Work:- for carrying out pre monsoon maintenance wo | 18-07-2025 09:00:00 | 18-07-2025 12:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
26 | 2025-07-17 13:17 | MR2507/0235 |  | 132KV_132KV Ratlam- RAILWAY TRACTION Ckt-II both end | 220KV_RATLAM | NON-OCCM-MP | Work:- for carrying out pre monsoon maintenance wo | 18-07-2025 13:00:00 | 18-07-2025 17:00:00 | NIKHIL DUNGE | 9425801487 | sub ld
27 | 2025-07-15 11:47 | MR2507/0186 | Continuous | 400KV_400 kv main bus-1 | 400KV_SAGAR | NON-OCCM-MP | for erection of panto iso and string of 400 kv bus | 17-07-2025 08:00:00 | 18-07-2025 17:00:00 | Anil mahor | 9425805149 | deffered, not in WR list
28 | 2025-07-17 16:09 | MR2507/0247 |  | 132KV_160MVA IMP | 220KV_SIRMOUR | NON-OCCM-MP | INFPS installation work | 18-07-2025 10:00:00 | 18-07-2025 18:00:00 | I.J. Singh | 9424734033 | ok
29 | 2025-07-17 15:12 | MR2507/0244 |  | 132KV_132 KV DIGODA 1 LINE & 132 kv DIGODA 2 LINE | 220KV_TIKAMGARH | NON-OCCM-MP | FOR JUMPERING WORK AT 132 DIGODA LINE 2 | 18-07-2025 10:00:00 | 18-07-2025 14:00:00 | SAMEER PARTE | 9575673359 | sub ld
30 | 2025-07-17 11:11 | MR2507/0232 |  | 400KV_400 KV UJJAIN NAGDA CKT-2ND | 400KV_UJJAIN4 | NON-OCCM-MP | Pre monsoon bay maintenance work | 18-07-2025 10:00:00 | 18-07-2025 17:00:00 | Mr. Santosh Chavrasia | 9425804677 | ok, through sub ld
31 |  |  |  | 400KV-DAMOH-BIRSINGPUR-1 | POWERGRID-WR2 (PGCIL) | 400 | AMP Work of of Line terminal equipment and its BAY at birsingpur , Non auto mode of ckt 2 is required for opportunity work in line . Dia to be kept open at both ends. | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 20:00 | ok
32 |  |  |  | 400KV-BHOPAL-MP-BINA-MP-2 | MADHYA PRADESH | 400 | FOR BAY MAINTENANCE & TESTING WORK | 17-Jul-2025 | 09:00 | 17-Jul-2025 | 18:00 | real time
33 |  |  |  | 400KV-INDORE-UJJAIN-2 | MADHYA PRADESH | 400 | FOR BAY MAINTENANCE & TESTING WORK | 17-Jul-2025 | 09:00 | 17-Jul-2025 | 18:00 | real time
34 |  |  |  | 220KV-GWALIOR-MAHALGAON-2 | MADHYA PRADESH | 220 | FOR BAY MAINTENANCE & TESTING WORK | 17-Jul-2025 | 09:00 | 17-Jul-2025 | 17:00 | real time
35 |  |  |  | 220KV-KHANDWA-CHHEGAON-1 | MADHYA PRADESH | 220 | FOR LINE MAINTENANCE WORK | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 18:00 | real time
36 |  |  |  | 220KV-BHANPURA-MODAK-1 | POWERGRID-NR,MADHYA PRADESH | 220 | FOR LINE MAINTENANCE WORK | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 18:00 | real time
37 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 | MAHARASHTRA | 132 | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 17-Jul-2025 | 08:00 | 17-Jul-2025 | 17:59
S/I SLDC JBALPUR