## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-28 |  |  | APPROVED OUTAGE LIST FOR DATED 28.08.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | LINE END (IN CASE OF LINE) | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-27 13:12 | MR2508/0359 |  | 220KV_220kv Main Bus 2 | 220KV_BADNAGAR | OCCM-MP | For attending isolater alliement work Bus ti Pith, |  | 28-08-2025 10:00:00 | 28-08-2025 17:00:00 | Waiting | Poshkar kushwaha | 9425813990 | ok through sub ld
2 | 2025-08-27 13:10 | MR2508/0358 |  | 132KV_Betul Multai | 220KV_BETUL | NON-OCCM-MP | Flash over disc replacement & other line maint. wo |  | 28-08-2025 09:00:00 | 28-08-2025 17:00:00 | Waiting | SHIV KUMAR | 9425806917 | sub ld
3 | 2025-08-27 14:39 | MR2508/0363 |  | 220KV_220KV ITARSI-HANDIA-CKT-I LINE | 220KV_HANDIYA | NON-OCCM-MP | F/O DISC REPLACEMENT WORK |  | 28-08-2025 10:00:00 | 28-08-2025 17:00:00 | Waiting | R.N PARTE | 9425804701 | ok through sub ld
4 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | Accepted | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
5 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr |  | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | -
6 | 2025-08-27 12:34 | MR2508/0357 |  | 220KV_220KV SOUTH ZONE-INDORE-I LINE | 220KV_INDORE-SZ | NON-OCCM-MP | Attend hot Point of B Phase Wave Trap Bottom clamp |  | 28-08-2025 10:00:00 | 28-08-2025 17:00:00 | Waiting | Dharmendra Kushwaha | 9425802801 | ok through sub ld
7 | 2025-08-26 18:22 | MR2508/0354 | Continuous | 132KV_132 KV JBP-SAHPURA DP LINE | 220KV_JABALPUR | OCCM-MP | REPLACEMENT OF TOWER LOC NO 5 |  | 28-08-2025 10:00:00 | 02-09-2025 19:00:00 | Waiting | RAJESH TIWARI | 7898239595 | realtime, will be finalized tomorrow morning after discussion
8 | 2025-06-30 15:28 | MR2506/0625 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENTHENING WORK |  | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | deferred
9 | 2025-06-30 16:11 | MR2506/0634 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK |  | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | deferred
10 | 2025-08-27 11:43 | MR2508/0356 |  | 220KV_220 kv katni satna line | 400KV_KATNI4 | NON-OCCM-MP | line maintenance work |  | 28-08-2025 10:00:00 | 28-08-2025 18:00:00 | Waiting | pankaj yadav | 9406713326 | ok
11 | 2025-08-26 15:59 | MR2508/0349 |  | 132KV_132 KV Main bus | 132KV_KOTHIYA | NON-OCCM-MP | Jumpering work |  | 28-08-2025 11:00:00 | 28-08-2025 16:00:00 | Waiting | Er. Sunny Kumar | 9425806888 | sub ld
12 | 2025-08-12 17:42 | MR2508/0177 | Daily | 220KV_220KV Mangliya -Jaitpura Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work |  | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | Accepted | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
13 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre |  | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
14 | 2025-08-27 14:41 | MR2508/0364 |  | 132KV_132/33 kv 63 MVA BBL X-mer no.01 | 220KV_NARSINGHPUR | NON-OCCM-MP | 33 kv Incomer no.01 breaker & pannel replacement w |  | 28-08-2025 09:00:00 | 28-08-2025 18:00:00 | Waiting | Dinesh Kumar kushwaha | 9425801319 | ok
15 | 2025-08-27 13:17 | MR2508/0360 |  | 132KV_Unit No. 1 | 132KV_PENCH | NON-OCCM-MP | Replacement of accuracy class 1 C.T. with 0.2S CT |  | 28-08-2025 08:00:00 | 28-08-2025 20:00:00 | Waiting | Arun Mungole | 8329756200 | as per system availability, prior to normalization protection format to be submitted & Abt to be informed
16 | 2025-08-27 13:18 | MR2508/0361 |  | 132KV_Unit No. 1 | 132KV_PENCH | NON-OCCM-MP | Replacement of accuracy class 1 C.T. with 0.2S CT |  | 28-08-2025 08:00:00 | 28-08-2025 20:00:00 | Waiting | Arun Mungole | 8329756200
17 | 2025-08-27 13:18 | MR2508/0362 |  | 132KV_Unit No. 1 | 132KV_PENCH | NON-OCCM-MP | Replacement of accuracy class 1 C.T. with 0.2S CT |  | 28-08-2025 08:00:00 | 28-08-2025 20:00:00 | Waiting | Arun Mungole | 8329756200
18 | 2025-08-27 15:35 | MR2508/0367 |  | 220KV_160 MVA-II (CGL) | 220KV_PITHAMPUR (SEC-III) | NON-OCCM-MP | Post monsoon |  | 28-08-2025 10:00:00 | 28-08-2025 17:00:00 | Waiting | sh. Rajudash | 9425801532 | ok through sub ld
19 | 2025-08-26 12:22 | MR2508/0341 |  | 132KV_132kv sabalgarh sheopur ckt-2 Tap To Khandar | 220KV_SABALGARH | OCCM-MP | line maintenance work |  | 28-08-2025 09:00:00 | 28-08-2025 17:00:00 | Waiting | suraj pawar | 9425814079 | ok through sub ld
20 | 2025-08-27 15:22 | MR2508/0366 |  | 220KV_Shutdown (H/T) of 220 kv Satna-Manpur DCDS line | 220KV_SATNA | NON-OCCM-WR | replacement of flash over disc insulator string, |  | 28-08-2025 11:00:00 | 28-08-2025 17:00:00 | Waiting | Mr. Ajay Kumar Chaurasia | 9425805081 | ok
21 | 2025-08-26 18:17 | MR2508/0353 |  | 400KV_SINGHAJI-TPS-II-PITHAMPUR4_Ckt_4 | 400KV_SINGHAJI-TPS-II | NON-OCCM-MP | PMU installation work by MPPTCL | Both End | 28-08-2025 10:00:00 | 28-08-2025 18:00:00 | Waiting | Mr. Sharad Tiwari | 7987469237 | ok through sub ld
22 | 2025-08-27 10:55 | MR2508/0355 |  | 132KV_132kV Tikamgarh - Budhera Ckt.- IInd Line | 220KV_TIKAMGARH | NON-OCCM-MP | Flace over Disc/Polymer repalcement |  | 28-08-2025 10:00:00 | 28-08-2025 18:00:00 | Waiting | Manoj Kumar Tiwari | 9425804993 | ok
23 | 2025-08-27 14:41 | MR2508/0365 |  | 220KV_220KV Vidisha-Bina line | 220KV_VIDISHA | OCCM-MP | MAIN DPR RELAY 2 TESTING WORK |  | 28-08-2025 10:00:00 | 28-08-2025 17:00:00 | Waiting | K.C.GOSWAMI | 9425804976 | ok through sub ld
24 |  |  |  | 220KV-REWA-REWA-MP-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK ( REWA RUMS) |  | 28-Aug-2025 | 10:00 | 28-Aug-2025 | 17:00 |  | ok
25 |  |  |  | 132KV-SHEOPUR-KHANDAR-1 | POWERGRID-NR,MADHYA PRADESH |  | LINE MAINTENANCE WORK |  | 28-Aug-2025 | 09:00 | 28-Aug-2025 | 17:00 |  | ok through sub ld
26 |  |  |  | 400KV-DAMOH-BIRSINGPUR-1 | POWERGRID-WR2 (PGCIL) |  | ATTENDING S/D NATURE DEFECTS IN LINE, A/R OF CKT-2 TO BE KEPT IN NON-AUTO MODE |  | 28-Aug-2025 | 07:00 | 28-Aug-2025 | 18:00 |  | ok
27 |  |  |  | MAIN BAY - 220KV-GWALIOR-MAHALGAON-1 AND GWALIOR - 220KV - BUS 1 at GWALIOR - 220KV | POWERGRID-WR2 (PGCIL) |  | AMP works |  | 28-Aug-2025 | 09:00 | 28-Aug-2025 | 18:00 |  | ok
28 |  |  |  | 400KV-INDORE-MP-ASOJ-1 | POWERGRID-WR2 (PGCIL) |  | Bus-2 Pento Isolator replacement work and PLCC digital protection coupler installation work and Yearly AMP of terminal equipment under Add cap. Dia to be kept open at both ends. |  | 28-Aug-2025 | 07:00 | 28-Aug-2025 | 18:00 |  | ok through sub ld
29 |  |  |  | TIE BAY OF 220KV-SATNA-MP-SATNA-1 AND 400KV/220KV SATNA-ICT-2 @SATNA - 220KV at SATNA - 220KV | POWERGRID-WR2 (PGCIL) |  | AMP of Bay 202 |  | 28-Aug-2025 | 09:00 | 28-Aug-2025 | 18:00 |  | ok
30 |  |  |  | 400KV-DAMOH-BIRSINGPUR-2 | POWERGRID-WR2 (PGCIL) |  | Non Auto mode of ckt #2 is required for attending Shutdown nature defects in line 400KV-DAMOH-BIRSINGPUR-1 |  | 28-Aug-2025 | 07:00 | 28-Aug-2025 | 18:00 |  | ok line to be in service
S/I SLDC JABALPUR