## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-23
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-22 12:57 | MR2507/0314 |  | 132KV_50 MVA BHEL X-mer | 132KV_BANDA | OCCM-MP | Differential relay change | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | P D Goutam | 9425808329 | o&m consent required
2 | 2025-07-22 14:37 | MR2507/0325 |  | 132KV_132kV Barwaha-ChhotiKhargone Line | 220KV_BARWAHA | NON-OCCM-MP | Line Maintenance Work | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | Naresh Pandre | 9425806905 | sub ld
3 | 2025-07-22 16:03 | MR2507/0337 |  | 220KV_220KV Itarsi-Barwaha line | 220KV_BARWAHA | NON-OCCM-MP | F/O disc insulator replacement work | 23-07-2025 10:00:00 | 23-07-2025 17:00:00 | A.R. Kanel | 9425805217 | ok, through sub ld
4 | 2025-07-22 16:40 | MR2507/0343 |  | 220KV_220KV Omkareshwar-Barwaha line | 220KV_BARWAHA | NON-OCCM-MP | Flashover Disc Insulator replacement work | 23-07-2025 10:00:00 | 23-07-2025 17:00:00 | Naresh Pandre | 9425806905 | ok, through sub ld, OSP generation to be minimized to controll the loading on the remaining ckts
5 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
6 | 2025-07-22 16:37 | MR2507/0342 |  | 400KV_315MVA X-Mer-4 Main CB only | 400KV_BHOPAL4 | NON-OCCM-MP | For attending DC leakage. | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | Akram Khan | 9425804695 | ok, ICT to be in service through tie CB
7 | 2025-07-22 15:08 | MR2507/0329 |  | 132KV_50MVA X-mer No. II BHEL | 132KV_BOREGAON | NON-OCCM-MP | Tandelta & capacitance Meassuement work | 23-07-2025 13:30:00 | 23-07-2025 17:00:00 | MR sahu | 9425804982 | o&m consent required
8 | 2025-07-22 15:03 | MR2507/0328 |  | 132KV_40MVA X-mer No.-I | 132KV_BOREGAON | NON-OCCM-MP | Tandelta & Capacitance Messurment work | 23-07-2025 10:00:00 | 23-07-2025 13:00:00 | MR sahu | 9425804982 | o&m consent required
9 | 2025-07-22 14:31 | MR2507/0324 |  | 132KV_132 KV Khaniyadana Rajghat line | 132KV_CHANDERI | NON-OCCM-MP | Flash over disc replacement work | 23-07-2025 10:00:00 | 23-07-2025 17:00:00 | Satish Kumar Bhagat | 9425806916 | ok, through sub ld
10 | 2025-07-22 11:06 | MR2507/0310 |  | 220KV_220Kv Chhegaon-Nimrani Ckt-I | 400KV_CHHEGAON4 | NON-OCCM-MP | For CVT Wiring Work | 23-07-2025 10:30:00 | 23-07-2025 17:00:00 | Shri Ganesh Mansare | 9425802441 | ok, through sub ld
11 | 2025-07-22 14:24 | MR2507/0321 |  | 220KV_220 KV Bina- Datia feeder | 220KV_DATIA | NON-OCCM-WR | Bus-Bar protection testing & relay testing work | 23-07-2025 11:00:00 | 23-07-2025 17:00:00 | Atul Shakya | 9425806928 | ok, through sub ld
12 | 2025-07-22 16:05 | MR2507/0339 |  | 132KV_132kV Dindori-Gorakhpur Line | 132KV_DINDORI | NON-OCCM-MP | Emergency Tree Cutting Work | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | S.K. BHALADHARE | 9425807264 | as opportunity s/d
13 | 2025-07-22 14:24 | MR2507/0322 |  | 132KV_50MVA 132/33KV BBL X-MER | 132KV_GORAKHPUR | NON-OCCM-MP | Second Differential Relay installation Commissioni | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | Dharam pal singh | 9009393895 | ok
14 | 2025-07-22 15:50 | MR2507/0332 |  | 132KV_63 MVA X-mer No.II Make TAL | 132KV_HARDA | NON-OCCM-MP | HV/LV CB IR Value & CB Timing work | 23-07-2025 11:00:00 | 23-07-2025 14:00:00 | Sh.J.D.Khoria | 9425804975 | sub ld
15 | 2025-07-22 14:17 | MR2507/0320 |  | 132KV_132KV Hatta-Bijawar Line | 132KV_HATTA | NON-OCCM-MP | R,Y,B phase LA replacement work | 23-07-2025 11:00:00 | 23-07-2025 17:00:00 | B.K. Sahu | 9425801433 | ok
16 | 2025-07-22 15:57 | MR2507/0333 |  | 220KV_160 MVA BHEL X- MER | 220KV_JABALPUR | NON-OCCM-MP | HOT POINT ATTAND WORK | 23-07-2025 10:00:00 | 23-07-2025 13:00:00 | D.N. PODDAR | 9425805034 | ok
17 | 2025-07-22 16:05 | MR2507/0340 |  | 220KV_220 KV SUKHA NO. 1 | 220KV_JABALPUR | NON-OCCM-MP | HOT POINT ATTAND WORK . | 23-07-2025 14:00:00 | 23-07-2025 17:00:00 | D.N. PODDAR | 9425805034 | real time
18 | 2025-07-22 08:38 | MR2507/0308 |  | 132KV_132 kv Incoming of 160 mva - II | 220KV_JAORA | NON-OCCM-MP | A shutdown on 132 kv Bus Section -II | 23-07-2025 10:00:00 | 23-07-2025 13:00:00 | RAKESH BADGOTYA | 7587951143 | shall be given after normalisation of s/d on 160MVA at Mandsaur, load to be managed by sub ld
19 | 2025-07-22 08:43 | MR2507/0309 |  | 132KV_132 kv Incoming - I of 160 mva - I | 220KV_JAORA | NON-OCCM-MP | A shutdown on 132 kv Bus Section -II | 23-07-2025 10:00:00 | 23-07-2025 13:00:00 | RAKESH BADGOTYA | 7587951143 | shall be given after normalisation of s/d on 160MVA at Mandsaur, load to be managed by sub ld
20 | 2025-06-30 14:52 | MR2506/0617 | Continuous | 400KV_400KV KATNI-DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered, not in WR list
21 | 2025-06-30 15:42 | MR2506/0629 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 21-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered, not in WR list
22 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | Continuous
23 | 2025-07-22 16:48 | MR2507/0346 |  | 220KV_220kV Incoming -1 (315MVA X-MER-1 LV side only) | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-1 connected isolator maintenance wo | 23-07-2025 10:30:00 | 23-07-2025 11:00:00 | RAJESH BHURIA | 9425806920 | ok, through sub ld
24 | 2025-07-22 16:52 | MR2507/0347 |  | 220KV_160MVA X-MER-2 (HV side only) 11:00hrs to 11:30hrs | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-1 connected isolator maintenance wo | 23-07-2025 11:00:00 | 23-07-2025 11:30:00 | RAJESH BHURIA | 9425806920 | ok, through sub ld
25 | 2025-07-22 16:56 | MR2507/0348 |  | 220KV_220KV MANDSAUR-DALODA-1 | 400KV_MANDSOUR4 | OCCM-MP | for 220kV Main Bus-1 connected isolator maintenanc | 23-07-2025 11:30:00 | 23-07-2025 12:00:00 | RAJESH BHURIA | 9425806920 | ok, through sub ld
26 | 2025-07-22 17:02 | MR2507/0349 |  | 220KV_220KV MANDSAUR-DALODA-2 FEEDER | 400KV_MANDSOUR4 | OCCM-MP | for 220kV Main Bus-1 connected isolator maintenanc | 23-07-2025 12:00:00 | 23-07-2025 12:30:00 | RAJESH BHURIA | 9425806920 | ok, through sub ld
27 | 2025-07-22 15:42 | MR2507/0331 |  | 220KV_220kV Main Bus -1 | 400KV_MANDSOUR4 | OCCM-MP | Opportunity 220kV Main Bus -1 Maintenance work | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | Rajesh Bhuria | 9425806920 | ok, as opportunity s/d
28 | 2025-07-22 17:05 | MR2507/0350 |  | 220KV_220KV MANDSAUR - NEEMUCH-I | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-1 connected isolator maintenance wo | 23-07-2025 14:00:00 | 23-07-2025 14:30:00 | RAJESH BHURIA | 9525806920 | ok, through sub ld
29 | 2025-07-21 12:28 | MR2507/0291 | Continuous | 220KV_220 KV Main Bus-1st | 400KV_MANDSOUR4 | NON-OCCM-MP | Stringing work of 220 KV Yard | 22-07-2025 09:00:00 | 24-07-2025 18:00:00 | J.P. Parmar | 9425806919 | Continuous
30 | 2025-07-22 16:18 | MR2507/0341 |  | 220KV_160MVA X-MER-1 (HV side only) | 400KV_MANDSOUR4 | OCCM-MP | 220kV Main Bus-1 connected isolator maintenance wo | 23-07-2025 10:00:00 | 23-07-2025 10:30:00 | RAJESH BHURIA | 9425806920 | ok, through sub ld
31 | 2025-07-22 13:55 | MR2507/0318 |  | 220KV_220 KV Narsinghpur-Pipariya Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Flashover disc replacement workat loc.No.03/R-Phas | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | Ashish Kumar | 9425805935 | ok
32 | 2025-07-22 13:19 | MR2507/0315 | Continuous | 132KV_132KV Neemuch-Budha Line | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Testing & OPGW Splicing | 23-07-2025 08:30:00 | 30-07-2025 18:00:00 | Gaurav Goyal | 9425805120 | sub ld
33 | 2025-07-22 13:27 | MR2507/0316 | Daily | 132KV_132KV Neemuch-Malharagarh | 220KV_NEEMUCH | NON-OCCM-MP | For OPGW Stringing | 23-07-2025 08:00:00 | 24-07-2025 19:00:00 | Gaurav Goyal | 9425805120 | sub ld
34 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
35 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
36 | 2025-07-22 12:40 | MR2507/0312 |  | 220KV_220/132KV 160MVA X-Mer-II BHEL | 220KV_NIMRANI | NON-OCCM-MP | For Remove Bird Next From R Phase CT dom | 23-07-2025 10:30:00 | 23-07-2025 12:30:00 | Mukesh Kumar Yadav | 9425802262 | ok, through sub ld
37 | 2025-07-11 16:44 | MR2507/0157 | Daily | 220KV_Omkareshwar-Khandwa Line (Line#5) | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 21-07-2025 09:00:00 | 23-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered, due to high OSP generation
38 | 2025-07-11 16:53 | MR2507/0159 | Daily | 220KV_Main BUSâ¿¿B and Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenance | 23-07-2025 09:00:00 | 26-07-2025 18:00:00 | PANKAJ SHARMA | 7898703187 | Deffered, due to high OSP generation
39 | 2025-07-22 15:01 | MR2507/0327 |  | 132KV_50MVA Xmer no 02 | 220KV_PICHHORE | NON-OCCM-MP | Gantry beam erection work. | 23-07-2025 09:00:00 | 23-07-2025 18:00:00 | Virendra K ahirwar | 9755024344 | sub ld
40 | 2025-07-22 14:30 | MR2507/0323 |  | 132KV_Shutdown (H/T) of 132 KV Rewa-Mangawan Ckt-II DCDS line | 220KV_REWA | NON-OCCM-WR | Flash over disc replacement at loc. no. 60, 62 &67 | 23-07-2025 10:00:00 | 23-07-2025 17:00:00 | Mr. Ajay Kumar Chaurasia | 9425805081 | ok
41 | 2025-07-17 15:12 | MR2507/0243 | Continuous | 400KV_400 KV MAIN BUS-1 | 400KV_SAGAR | OCCM-MP | FOR EXTENSION OF 400 KV MAIN BUS-1 | 22-07-2025 08:00:00 | 23-07-2025 17:00:00 | ANIL MAHOR | 9425805149 | Continuous
42 | 2025-07-19 17:13 | MR2507/0270 | Daily | 132KV_132kV Seoni Nainpur Ckt-IInd | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
43 | 2025-07-19 17:15 | MR2507/0271 | Daily | 132KV_132kV Seoni Keolari Line | 220KV_SEONI | NON-OCCM-MP | Replacement of damage OPGW of line section 31-37 | 22-07-2025 09:00:00 | 26-07-2025 18:00:00 | S.K. Nadekar | 9425806848 | ok
44 | 2025-07-01 16:52 | MR2507/0018 |  | 400KV_400KV Singaji-Chhegaon feeder-1 | 400KV_SINGHAJI TPS | NON-OCCM-MP | Relay Testing work for 400KV Chhegaon-1 during AOH | 23-07-2025 10:00:00 | 23-07-2025 19:00:00 | Deepak Sharma | 8005696855 | shall be given after normalisation of 400kv SSTPS-Pithampur ckt 1 and real time SSTPS generation
45 | 2025-07-22 14:04 | MR2507/0319 |  | 132KV_132KV JABALPUR - TEJGARH LINE | 132KV_TEJGARH | NON-OCCM-MP | F/O DISC REPLACEMENT AND OTHER MAINTENANCE | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | PANKAJ YADAV | 9406713326 | ok
46 | 2025-07-22 13:41 | MR2507/0317 |  | 220KV_220 KV UJJAIN I/C LINE CKT 3 & 4 | 220KV_UJJAIN | OCCM-WR | LINE MAINTENANCE WORK | 23-07-2025 10:00:00 | 23-07-2025 11:00:00 | KUMAR SACHINDRA SHARMA | 7415651054 | ok, through sub ld
47 | 2025-07-22 12:52 | MR2507/0313 |  | 132KV_132KV Alot-Jharla Ckt-II Line | 132KV_ZARDA | NON-OCCM-MP | F/o Polymer Insulator replacement work | 23-07-2025 10:00:00 | 23-07-2025 18:00:00 | Kamal Solanki | 9425805262 | sub ld
48 |  |  |  | 400KV-BADNAWAR-RAJGARH-1 | POWERGRID-WR2 (PGCIL),MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 08:00 |  |  |  | REAL TIME . ckt-2 (55% sensitivity) and all other lines at 400kV Badnawar to be in service. WR2 to be informed.
49 |  |  |  | 220KV-GWALIOR-MALANPUR-2 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 09:00 |  |  |  | REAL TIME ,All other lines at Manapur to be in service with AR enabled. WR2 to be informed. Load to be managed by SLDC MP
50 |  |  |  | 220KV-BHANPURA-RANPUR-1 | POWERGRID-NR,MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK | 08:00 |  |  |  | REAL TIME, All other lines at Bhanpura will be in service. NLDC consent is required. NR drawl to be restricted up to 150. Load will be managed by SLDC MP.
51 |  |  |  | 220KV-REWA-SINDHI-MP-1 | MADHYA PRADESH |  | FOR LINE MAINTENANCE WORK ( REWA RUMS) | 10:00 |  |  |  | REAL TIME Ckt-2 (sensitivity of 39%) and all other lines at 220kV Sindhi to be in service. In case of contingency load to be managed by SLDC MP.
52 |  |  |  | 400KV-SEONI-KIRNAPUR-1 | MADHYA PRADESH,POWERGRID-WR1 (PGCIL) |  | LINE BAY AMP WORK AT SEONI SS | 09:00 |  |  |  | OK, 400 kV Bhilai-Kirnapur to be in service with AR enabled. SLDC CG/MP to be informed. Load to be managed by SLDC MP
53 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 |  |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 8:00 |  |  |  | OK, A/R in NA, Line to be in service.
S/I, SLDC MPPTCL JABALPUR.