## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-01
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-07-31 14:37 | MR2507/0480 |  | 132KV_50MVA BHEL X-MER | 220KV_ANUPPUR | NON-OCCM-MP | LBB WIRING & TESTING WORK | 01-08-2025 10:00:00 | 01-08-2025 17:00:00 | SUNIL KUMAR BHALAVI | 9425804704 | ok
2 | 2025-07-31 12:16 | MR2507/0474 |  | 132KV_132kV Balaghat Lalbarra Feeder | 132KV_BALAGHAT | NON-OCCM-MP | Replacement of flashover disc insulator | 01-08-2025 10:00:00 | 01-08-2025 13:00:00 | S.K. Nadekar | 9425806848 | Deffered due to s/d on seoni Bus and 220KV SEONI PGCIL_ckt 1
3 | 2025-07-31 12:19 | MR2507/0475 |  | 132KV_132kV Balaghat Waraseoni Feeder | 132KV_BALAGHAT | NON-OCCM-MP | Replacement of flashover disc insulator | 01-08-2025 14:00:00 | 01-08-2025 18:00:00 | S.K. Nadekar | 9425806848 | Deffered due to s/d on seoni Bus and 220KV SEONI PGCIL_ckt 1
4 | 2025-07-31 15:41 | MR2507/0483 |  | 220KV_220/132 kv 160 MVA BHEL X-MER- I | 220KV_CHICHLI | NON-OCCM-MP | S/D for Protection cable replacement work | 01-08-2025 11:00:00 | 01-08-2025 16:00:00 | Rajesh chaturvedi | 9425805203 | ok
5 | 2025-07-29 10:54 | MR2507/0453 | Daily | 220KV_220KV South Zone - Jaitpura Line. | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | replacement existing of 24 Fibre OPGW by 48 Fibre | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | pending
6 | 2025-06-30 15:05 | MR2506/0621 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | SHRI PANKAJ YADAV | 9406713326 | Deffered
7 | 2025-06-30 15:54 | MR2506/0630 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 28-07-2025 09:00:00 | 02-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | Deffered
8 | 2025-07-31 14:04 | MR2507/0478 |  | 132KV_132KV IC KATNI-1 FEEDER | 400KV_KATNI4 | NON-OCCM-MP | TO ATTEND HOT POINT IN YPH CT DROP JUMPER | 01-08-2025 11:00:00 | 01-08-2025 13:00:00 | SK CHATURVEDI | 9425806938 | ok
9 | 2025-07-31 14:07 | MR2507/0479 |  | 132KV_132KV IC KATNI-2 FEEDER | 400KV_KATNI4 | NON-OCCM-MP | TO ATTEND HOT POINT IN RPH CT CLAMP LINE SIDE | 01-08-2025 14:00:00 | 01-08-2025 16:00:00 | SK CHATURVEDI | 9425806938 | ok
10 | 2025-07-31 15:30 | MR2507/0482 |  | 132KV_132/33 Kv 50 MVA BHEL X-mer | 132KV_KATRA | NON-OCCM-MP | For LV CT to CB Y & B Phase conductor replacement | 01-08-2025 08:00:00 | 01-08-2025 11:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
11 | 2025-07-27 14:12 | MR2507/0430 | Continuous | 132KV_132 KV Khurai- Sagar ckt | 132KV_KHURAI | NON-OCCM-MP | For modification work of above line | 27-07-2025 07:00:00 | 03-08-2025 18:00:00 | Sanjay singh thakur | 9425806936 | Continuous
12 | 2025-07-24 12:24 | MR2507/0380 | Continuous | 400KV_400 KV Main Bus-2nd | 400KV_MANDSOUR4 | NON-OCCM-MP | Overhead stringing work | 29-07-2025 09:00:00 | 05-08-2025 18:00:00 | J.P. Parmar | 9425806919 | Deffered
13 | 2025-07-29 10:59 | MR2507/0454 | Daily | 220KV_220KV Indore (400KV) â¿¿ Mangliya Line | 220KV_MANGLIA2 | NON-OCCM-MP | for replacement existing of 24 Fibre OPGW by 48 Fi | 01-08-2025 07:00:00 | 10-08-2025 19:00:00 | A.R.KANEL | 9425805217 | pending
14 | 2025-07-28 18:36 | MR2507/0449 | Daily | 220KV_220 KV Narsinghpur-Chichli-Pipariya Line | 220KV_NARSINGHPUR | NON-OCCM-MP | Rectification/replacement/work between Tower No-33 | 30-07-2025 09:00:00 | 05-08-2025 18:00:00 | Ashish Kumar | 9425805935 | pl confirm if any communication data will be affected during this work or not, if yes then ensure its availabilty through alternate path
15 | 2025-07-22 16:42 | MR2507/0344 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Installation of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | sub ld
16 | 2025-07-22 16:47 | MR2507/0345 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installatin of OPGW | 01-08-2025 07:00:00 | 25-08-2025 19:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
17 | 2025-07-31 14:00 | MR2507/0477 |  | 220KV_220KV PGCIL_CKT-1& 220KV Main Bus -1 | 220KV_SEONI | OCCM-MP | 220KV Main bus-1side isolator Maint. work | 01-08-2025 10:00:00 | 01-08-2025 17:00:00 | Shri C.S.Sanodiya | 900978506 | ok, for bus outage, 220KV PGCIL_CKT-1 s/d shall be taken as opportunity s/d after main s/d by PGCIL
18 | 2025-07-16 11:07 | MR2507/0209 | Continuous | 500MVA_400/220KV_BHEL_Xmer | 400KV_SGTPS | NON-OCCM-MP | Relay testing,Air cell replacement,DCRM and testin | 01-08-2025 08:00:00 | 06-08-2025 18:00:00 | Pramod Mishra | 8989973149 | ok
19 | 2025-07-16 11:13 | MR2507/0210 | Continuous | 400KV_63 MVA 400 Kv/ 11&6.6 KV Station Trf-5B | 400KV_SGTPS | NON-OCCM-MP | Relay test,DCRM,CT testing,Air cell replacement | 31-07-2025 09:00:00 | 02-08-2025 19:00:00 | Pramod Mishra | 8989973149 | Continuous
20 | 2025-07-30 12:44 | MR2507/0468 |  | 132KV_132 KV Sidhi Deosar Ckt-1 | 220KV_SIDHI | NON-OCCM-MP | Stringing work of IInd ckt 132 KV Sidhi Deosar lin | 01-08-2025 10:00:00 | 01-08-2025 17:00:00 | Jagat Narayan Singh | 9425802388 | ok
21 | 2025-07-23 17:12 | MR2507/0374 | Continuous | 400KV_90MVA STATION TRANSFORMER-2 | 400KV_SINGHAJI TPS | NON-OCCM-MP | OVERHAULLING OF 90MVA STATION TRANSFORMER-2 | 28-07-2025 09:30:00 | 06-08-2025 17:30:00 | Yogesh Chouhan | 7999328631 | Continuous
22 |  | 256958 |  | 220KV-AJAYGARH-SATNA-1 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 01-Aug-2025 | 10:00 | 01-Aug-2025 | 17:00 | real time
23 |  | 257235 |  | 220KV-SEONI-MP-SEONI-PG-1 | 220 | POWERGRID_WR1 | LINE BAY AMP WORK AT SEONI SS | 01-Aug-2025 | 09:00 | 01-Aug-2025 | 18:00 | ok
24 |  | 259203 |  | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 01-Aug-2025 | 07:00 | 01-Aug-2025 | 18:59 | ok