## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-07-19 |  |  | APPROVED OUTAGE LIST FOR DTD. 19.07.2025
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-06-30 16:24 | MR2506/0639 | Daily | 220KV_220 KV MUGALIYACHAP ASHTA | 400KV_ASHTA4 | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
2 | 2025-06-30 16:26 | MR2506/0640 | Daily | 220KV_220 KV BAIRAGARH-ASHTA | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
3 | 2025-06-30 16:13 | MR2506/0635 | Daily | 220KV_220 BHOPAL-BAIRAGARH CKT-3 | 220KV_BAIRAGARH | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
4 | 2025-07-02 18:54 | MR2507/0044 | Daily | 132KV_132kV Rewa - Bansagar Lilo Beohari -Lilo Jhinna | 132KV_BEOHARI | NON-OCCM-MP | OPGW Hot Line | 03-07-2025 07:00:00 | 30-07-2025 19:00:00 | G.L Sahu | 9425805102 | ok, line to be in service
5 | 2025-07-18 14:17 | MR2507/0255 |  | 33KV_Main Bus | 220KV_BETUL | NON-OCCM-MP | alignment of main bus isolator of 33kv I/C of 20MV | 19-07-2025 10:00:00 | 19-07-2025 12:00:00 | Vishal Kumar Malviya | 9425804955 | sub ld
6 | 2025-07-18 13:48 | MR2507/0252 |  | 220KV_220kV Bus Tie | 220KV_CHICHLI | NON-OCCM-MP | For CT Testing work . | 19-07-2025 11:00:00 | 19-07-2025 17:00:00 | Rajesh chaturvedi | 9425805203 | deferred due to s/d on 220kv Jbp-narsinghpur ckt
7 | 2025-07-15 17:04 | MR2507/0204 |  | 400KV_400 KV ISP INDORE-I | 400KV_INDIRASAGAR | NON-OCCM-WR | ANNUAL MAINTENANCE | 19-07-2025 10:00:00 | 19-07-2025 17:00:00 | SHRI VINAI MISHRA | 9575074321 | deferred due to high ISP generation
8 | 2025-07-18 14:34 | MR2507/0256 |  | 220KV_220 KV Jabalpur-Narsinghpur line Ckt-I | 220KV_JABALPUR | NON-OCCM-MP | Flashover disc replacement Work at Loc.No. 33/R - | 19-07-2025 10:00:00 | 19-07-2025 18:00:00 | Ashish Kumar | 9425805934 | ok
9 | 2025-07-18 14:09 | MR2507/0253 |  | 132KV_160mva -I | 220KV_JAORA | NON-OCCM-MP | A shutdown 132 kv incoming of 160 mva - I | 19-07-2025 10:00:00 | 19-07-2025 13:00:00 | RAKESH BADGOTYA | 7587951143 | sub ld indore to manage the loading
10 | 2025-07-18 14:13 | MR2507/0254 |  | 132KV_160 mva - II | 220KV_JAORA | NON-OCCM-MP | A shutdown of 132 kv Incoming - II of 160 mva - II | 19-07-2025 10:00:00 | 19-07-2025 13:00:00 | RAKESH BADGOTYA | 7587951143 | sub ld indore to manage the loading
11 | 2024-11-20 16:49 | MR2411/0436 | Continuous | 400KV_400 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-WR | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok
12 | 2024-11-20 16:54 | MR2411/0437 | Continuous | 220KV_220 KV KATNI-DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENGTHENING WORK | 14-07-2025 09:00:00 | 19-07-2025 18:00:00 | MANOJ KUMAR TIWARI | 9425804993 | ok
13 | 2025-07-18 16:14 | MR2507/0262 | Continuous | 132KV_132 KV Khurai- Sagar Ckt | 132KV_KHURAI | NON-OCCM-MP | For modification of 132 Khurai-sagar line | 18-07-2025 07:00:00 | 27-07-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | continuous
14 | 2025-06-30 16:20 | MR2506/0638 | Daily | 220KV_220 KV BHOPAL-MUGALIYACHAP | 220KV_MUGALIYACHAAP | NON-OCCM-MP | HOT LINE PERMIT | 01-07-2025 09:00:00 | 20-07-2025 19:00:00 | NITIN RESHWAL | 9425804890 | ok, line to be in service
15 | 2025-07-05 17:07 | MR2507/0079 | Daily | 132KV_132 kV Nepa - Pipalpani MPPTCL Line | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work Insatallation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | sub ld
16 | 2025-07-05 16:59 | MR2507/0078 | Daily | 132KV_132 kV Nepa - Dharni (MSPTCL) LIne | 220KV_NEPANAGAR | NON-OCCM-WR | Hotline Work For Installation of OPGW | 11-07-2025 08:00:00 | 30-07-2025 18:00:00 | C.H.Namdev | 9425802377 | ok, line to be in service
17 | 2025-07-18 15:30 | MR2507/0260 |  | 132KV_132 KV MAIN BUS | 132KV_NIWARI | NON-OCCM-MP | FOR 132 KV MAIN BUS ISOLATOR JUMPER WORK. | 19-07-2025 10:00:00 | 19-07-2025 13:00:00 | SAMEER PARTE | 9575673359 | ok
18 | 2025-07-18 15:25 | MR2507/0259 |  | 132KV_132 KV MAIN BUS,50 MVA XMER | 132KV_NIWARI | NON-OCCM-MP | 132 KV MAIN BUS ISOLATOR JUMPER WORK. | 19-07-2025 10:00:00 | 19-07-2025 13:00:00 | SAMEER PARTE | 9575673359 | ok
19 | 2025-07-18 15:24 | MR2507/0258 |  | 132KV_132 KV MAIN BUS,50 MVA XMER | 132KV_NIWARI | NON-OCCM-MP | 132 KV MAIN BUS ISOLATOR JUMPER WORK. | 19-07-2025 10:00:00 | 19-07-2025 13:00:00 | SAMEER PARTE | 9575673359 | ok
20 | 2025-07-18 16:09 | MR2507/0261 |  | 132KV_40MVA TRANSFORMER-I BBL | 132KV_PETLAWAD | NON-OCCM-MP | For hot point Atten on B Phase LV side bushing cla | 19-07-2025 11:00:00 | 19-07-2025 13:30:00 | Er Varsingh mohoniya | 7987080020 | sub ld
21 | 2025-07-18 13:39 | MR2507/0251 |  | 220KV_Shutdown (H/T) of 220 kv Rewa-Sidhi line | 220KV_REWA | NON-OCCM-WR | Purpose of flashover disc insulator string replace | 19-07-2025 11:00:00 | 19-07-2025 17:00:00 | Ajay Kumar Chaurasia | 9425805081 | ok
22 | 2025-07-18 16:28 | MR2507/0263 |  | 132KV_132/33KV 63MVA ABB | 132KV_SAGAR1 | NON-OCCM-MP | earth shield wire stringing work over 33kv main bu | 19-07-2025 07:00:00 | 19-07-2025 10:00:00 | S.K. HAZARI | 9425620010 | o&m consent required
23 |  |  |  | 400KV-BINA-MP-BINA-3 | POWERGRID_WR2 |  | Simultaneous ouatge of 765KV/400KV BINA-ICT-2 & 400KV-BINA-MP-BINA-3 has been required for Bay-420 LBB Testing | 2025-07-19 09:00 | 2025-07-19 15:00 |  |  | Ok.400kV BINA-MP -BINA-PG -T4 Sensitivity of 36.71% and All other circuits from Bhopal and Bina to be inservice with A/r enabled. 400kV Bhopal-Bina MP D/C are already out in tower collapse. SLDC MP to be informed.
24 |  |  |  | 400KV-DAMOH-KATNI-1 | MPPTCL |  | TOWER STRENGTHENING WORK | 2025-07-19 09:00 | 2025-07-19 18:00 |  |  | Ok.400kV DAMOH-PG -BIRSINGPUR -T2 Sensitivity of 34.22% and All other lines at Damoh - 400KV and KATNI - 400KV to be in service with A/R Enabled
25 |  |  |  | 132KV-DHARNI-NEPANAGAR-1 |  |  | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 2025-07-19 08:00 | 2025-07-19 18:00 |  |  | OK, A/R in N/A, Line will be in service.
S/ I SLDC MPPTCL JABALPUR