## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-10-30
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-10-29 16:10 | MR2510/0681 |  | 132KV_132 KV and 33 KV main bus | 132KV_AMARPATAN | NON-OCCM-MP | for replacement of higher rating isolator | 30-10-2025 07:30:00 | 30-10-2025 10:00:00 | Arun Kumar | 9131207339 | o&m consent required
2 | 2025-10-29 15:54 | MR2510/0679 |  | 220KV_220KV Ashta-Bairagarh Feeder | 400KV_ASHTA4 | NON-OCCM-MP | Relay testing work | 30-10-2025 11:00:00 | 30-10-2025 17:00:00 | Jitendra Lohana | 9425804978 | ok, through sub ld, line to be in service through TBC
3 | 2025-10-29 13:41 | MR2510/0664 |  | 400KV_315 MVA ICT-2 T&R | 400KV_BADNAWAR | NON-OCCM-MP | POST MANSOON MAINTENANCE & TESTING WORK | 30-10-2025 08:00:00 | 30-10-2025 18:00:00 | ER. ABHISHEK VERMA | 9340855901 | ok, through sub ld
4 | 2025-10-29 15:12 | MR2510/0670 |  | 132KV_132 KV Bina-Sironj Ckt | 220KV_BINA | NON-OCCM-MP | for line maintenance work | 30-10-2025 10:00:00 | 30-10-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | sub ld
5 | 2025-10-29 14:26 | MR2510/0666 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt. Ist Line | 220KV_CHATARPUR | NON-OCCM-MP | AH/VD Provided & other Line maintenance work | 30-10-2025 10:00:00 | 30-10-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | ok
6 | 2025-10-16 17:16 | MR2510/0478 | Continuous | 220KV_220KV DAMOH - KATNI LINE | 220KV_DAMOH | NON-OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | M.M. BAIG | 9425805067 | Deffered
7 | 2025-10-29 13:53 | MR2510/0665 |  | 132KV_132/33 KV 63 MVA x-mer -l | 132KV_DATIA1 | NON-OCCM-MP | Post mansoon maintenance | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | Raksha Chhaparia | 6265080313 | sub ld
8 | 2025-10-02 11:21 | MR2510/0022 | Daily | 132KV_132kV Deolond - Beohari Ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
9 | 2025-10-02 11:19 | MR2510/0021 | Daily | 132KV_132kV Deolond - Jhinna ckt | 132KV_DEVLOND | NON-OCCM-MP | OPGW Work | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
10 | 2025-10-27 11:50 | MR2510/0608 | Daily | 220KV_220 KV Itarsi-Handia Ckt-II | 220KV_ITARSI | NON-OCCM-MP | Replacement of Single to Double disc insut.string | 28-10-2025 09:00:00 | 30-10-2025 18:00:00 | Ashutosh Rai | 9425806902 | ok, through sub ld
11 | 2025-10-29 15:50 | MR2510/0676 |  | 132KV_132 KV BUS COPLER | 220KV_JABALPUR | NON-OCCM-MP | CT REPLECMENT & TESTING WORK | 30-10-2025 10:00:00 | 30-10-2025 18:00:00 | D.N PODDAR | 9425805034 | ok
12 | 2025-10-16 18:15 | MR2510/0483 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 27-10-2025 09:00:00 | 01-11-2025 18:00:00 | M.M. BAIG | 9425805067 | Deffered
13 | 2025-10-29 14:59 | MR2510/0668 |  | 220KV_160MVA Telk xmer | 400KV_KATNI4 | NON-OCCM-MP | For postmonsoon maintenance | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | SK chaturvedi | 9425806938 | ok
14 | 2025-10-29 16:46 | MR2510/0682 |  | 132KV_132 Kv 40 MVA ECE X-mer | 132KV_KATRA | NON-OCCM-MP | Post monsoon maintenance & Testing Work | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | Mr. Indrajeet Singh | 9424734033 | ok
15 | 2025-10-29 15:49 | MR2510/0675 |  | 160MVA_220/132KV_BHEL_X'mer_2 | 220KV_MAHALGAON | NON-OCCM-MP | on line dry out system commising | 30-10-2025 11:00:00 | 30-10-2025 15:00:00 | P.Datey | 9425805110 | ok, through sub ld
16 | 2025-10-29 15:20 | MR2510/0672 |  | 220KV_220/132KV 160MVA X-Mer-III BBL | 220KV_NIMRANI | NON-OCCM-MP | Post Monsoon Maintenance work | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | Er.Pradip Patidar | 9425801217 | ok, through sub ld
17 | 2025-10-29 15:52 | MR2510/0677 |  | 132KV_132/33 kv 40 MVA BBL X-MER -1 | 132KV_PONDER | NON-OCCM-MP | S/D for Post Monsoon Maintenance and Testing work. | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | MUKESH AUGRWALL | 7987152911 | o&m consent required
18 | 2025-10-02 11:16 | MR2510/0020 | Daily | 132KV_132kV Rampur Naikin - Beohari Ckt | 132KV_RAMPUR NAIKEN | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
19 | 2025-10-02 11:14 | MR2510/0019 | Daily | 132KV_132kV Rewa - jhinna | 220KV_REWA | NON-OCCM-MP | OPGW Work. | 03-10-2025 07:00:00 | 30-10-2025 19:00:00 | G.L Sahu | 9425805102 | data confirmation required from communication
20 | 2025-10-29 12:56 | MR2510/0663 |  | 220KV_220 kv Satna â¿¿ Manpur (Adani) line | 220KV_SATNA | NON-OCCM-MP | Line maintenance work | 30-10-2025 11:00:00 | 30-10-2025 16:00:00 | Mr. R.K. Prajapati | 9407070182 | deffered due to multiple outages in Satna area
21 | 2025-09-05 17:39 | MR2509/0127 | Continuous | 400KV_400KV Sarni-Ashta line-II | 400KV_SATPURA TPS | NON-OCCM-MP | Work of complete overhauling & testing of 400KV br | 30-10-2025 09:00:00 | 01-11-2025 18:00:00 | YASHWANT WARATHE | 9425611046 | deffered due to outage on 400KV Sarni-koradi line
22 | 2025-10-29 15:54 | MR2510/0678 |  | 132KV_132KV Seoni -Nainpur Line | 220KV_SEONI | NON-OCCM-MP | RYB CT Tan-Delta measurement & Testing work | 30-10-2025 09:00:00 | 30-10-2025 13:00:00 | Shri C.S.sanodiya | 9009798506 | ok
23 | 2025-10-29 15:59 | MR2510/0680 |  | 132KV_132KV Seoni-Keolari line | 220KV_SEONI | NON-OCCM-MP | RYB ph CT tan-delta Measurement & testing Work | 30-10-2025 14:00:00 | 30-10-2025 17:00:00 | Shri C.S. Sanodiya | 9009798506 | ok, o&m shall be informed
24 | 2025-10-29 15:13 | MR2510/0671 |  | 132KV_40 MVA X-mer-I Make IMP | 132KV_SINGHANA | NON-OCCM-MP | For Post monsoon maintenance work. | 30-10-2025 10:00:00 | 30-10-2025 18:00:00 | Er. Manoj Randha | 9425820034 | sub ld
25 | 2025-09-02 14:10 | MR2509/0043 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | B.C JOSHI | 7587951137 | Continuous
26 | 2025-10-28 17:32 | MR2510/0661 |  | 220KV_132 KV Main Bus section I & II | 220KV_UJJAIN | NON-OCCM-MP | 132 KV Main Bus section I & II for its 02 nos. sec | 30-10-2025 09:00:00 | 30-10-2025 13:00:00 | B.C JOSHI | 7587951137 | discom consent to be taken, then after load management s/d shall be given, through sub ld
27 | 2025-10-29 14:35 | MR2510/0667 |  | 40MVA_132/33KV_BBL_Xmer | 132KV_UMRETH | NON-OCCM-MP | POST MANSOON MAINTENANCE WORK. | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | A A QURESHI | 9425804318 | ok
28 | 2025-10-29 11:58 | MR2510/0662 |  | 220KV_160MVA X-MER-III BHEL | 220KV_VIDISHA | OCCM-MP | for attending suspected DC leakage of NIFPS | 30-10-2025 10:00:00 | 30-10-2025 17:00:00 | K.C. GOSWAMI | 9425804976 | ok, through sub ld
29 |  | 265990 | Daily | 220KV-INDORE-INDORE NORTH ZONE-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 30-Oct-2025 | 08:00 | 30-Oct-2025 | 18:00 | real time
30 |  | 265991 | Daily | 220KV-BINA-MP-BINA-1 | 220 | MP_SLDC | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 30-Oct-2025 | 09:00 | 30-Oct-2025 | 17:00 | real time
31 |  | 272543 | Daily | SATNA - 220KV - BUS 1 | 220 | POWERGRID_WR2 | For integration of relays of upcoming 220kV bays in existing system | 30-Oct-2025 | 09:00 | 30-Oct-2025 | 18:00 | ok
32 |  | 272678 | Daily | 400KV/220KV SATNA-ICT-2 | 400KV/220KV | POWERGRID_WR2 | AMP Work, Dia to be kept open at both sides. | 30-Oct-2025 | 09:00 | 30-Oct-2025 | 18:00 | ok
33 |  | 265241 | Continous | 400KV-KORADI-SATPURA-1 | 400 | POWERGRID_WR2 | For CT Replacement of 400KV-SATPURA-KORADI-1 under ADD CAP at MPGENCO | 29-Oct-2025 | 09:00 | 31-Oct-2025 | 20:00 | ok
34 |  | 272745 | Daily | 220KV-ITARSI-MP-ITARSI-1 | 220 | POWERGRID_WR2 | For Reparing/Replacement of Damaged conductor for Wave Trap of Line | 30-Oct-2025 | 09:00 | 30-Oct-2025 | 17:30 | ok, through sub ld
35
36
37
38
39
40