## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-08-29
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-28 16:33 | MR2508/0394 |  | 220KV_Anuppur No1 | 220KV_AMARKANTAK | NON-OCCM-WR | Control Breaker status not show in DPR | 29-08-2025 09:00:00 | 29-08-2025 14:00:00 | Vijay Kothari | 9425808910 | OK
2 | 2025-08-28 13:36 | MR2508/0381 |  | 220KV_220 kV Amarkantak-Sidhi Circuit | 220KV_AMARKANTAK | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 29-08-2025 13:00:00 | 29-08-2025 17:00:00 | Jitendra Tiwari | 9425805298 | OK AFTER NORMALIZATION OF 220KV ATPS-ANUPPUR CKT-1
3 | 2025-08-28 14:50 | MR2508/0383 |  | 132KV_132 KV Bina-Mungaoli Ckt-2 | 220KV_BINA | NON-OCCM-MP | for f/o disc insulator string replace | 29-08-2025 10:00:00 | 29-08-2025 18:00:00 | Sanjay Singh Thakur | 9425806936 | OK THROUGH SUB LD
4 | 2025-08-28 16:18 | MR2508/0392 |  | 132KV_132 KV Chhatarpur-Nowgong Line | 220KV_CHATARPUR | NON-OCCM-MP | For tan delta Measurement work | 29-08-2025 14:00:00 | 29-08-2025 17:00:00 | Brajendra Soni | 9131327770 | OK, PRIOR TO SD 132 KV CHHATARPUR-BIJAWAR CKT TO BE H/T FROM BIJAAR END, O&M TO BE INTIMATED
5 | 2025-08-28 16:10 | MR2508/0390 |  | 220KV_220kV Chhatarpur-Ajaygarh (TBCB) Ckt.1st Line | 220KV_CHATARPUR | NON-OCCM-MP | Slip VD Removal, AH tightening | 29-08-2025 10:00:00 | 29-08-2025 18:00:00 | Manoj Kumar Tiwari | 9425804993 | DEFERRED DUE TO SD ON 220KV SATNA(PG) - AJAYGARH CKT
6 | 2025-08-28 15:26 | MR2508/0386 |  | 220KV_220 KV Nagda- Daloda ckt-1st | 220KV_DALODA | NON-OCCM-MP | for line maintenance work | 29-08-2025 10:00:00 | 29-08-2025 18:00:00 | Kumar Vishal | 9425805018 | OK THROUGH SUB LD
7 | 2025-08-28 14:40 | MR2508/0382 |  | 220KV_220KV Traction-1 (Karaiya Bhadauli) Feeder | 220KV_DAMOH | NON-OCCM-MP | Bay Maintenance Work | 29-08-2025 10:00:00 | 29-08-2025 14:00:00 | M.K.Choubey | 9425801424 | OK, TIME SHOULD BE MAINTAINED AS PER RTS CONSENT
8 | 2025-08-12 17:39 | MR2508/0176 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
9 | 2025-08-12 17:20 | MR2508/0174 | Daily | 220KV_220KV South Zone (Indore) â¿¿ Jaitpura Line | 220KV_INDORE-II (JETPURA) | NON-OCCM-MP | . Replacement existing of 24 Fibre OPGW by 48 Fibr | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
10 | 2025-08-28 12:20 | MR2508/0376 |  | 132KV_132 KV Itarsi-Pipariya | 220KV_ITARSI | NON-OCCM-MP | Flash over disc replacement | 29-08-2025 10:00:00 | 29-08-2025 17:00:00 | Ashutosh Rai | 9425806902 | SUB LD
11 | 2025-08-26 18:22 | MR2508/0354 | Continuous | 132KV_132 KV JBP-SAHPURA DP LINE | 220KV_JABALPUR | OCCM-MP | REPLACEMENT OF TOWER LOC NO 5 | 28-08-2025 10:00:00 | 02-09-2025 19:00:00 | RAJESH TIWARI | 7898239595 | OK O&M TO INFORM
12 | 2025-06-30 15:28 | MR2506/0625 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENTHENING WORK | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
13 | 2025-06-30 16:11 | MR2506/0634 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 25-08-2025 09:00:00 | 30-08-2025 18:00:00 | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC CONSENT REQUIRED
14 | 2025-08-28 15:59 | MR2508/0387 |  | 132KV_132kV Mandla- Maneri Line | 132KV_MANDLA | NON-OCCM-MP | Bird Guard Instalation Work | 29-08-2025 10:00:00 | 29-08-2025 18:00:00 | S.K. BHALADHARE | 9425807264 | OK
15 | 2025-08-12 17:42 | MR2508/0177 | Daily | 220KV_220KV Mangliya -Jaitpura Line | 220KV_MANGLIA2 | NON-OCCM-MP | 24 Fibre OPGW by 48 Fibre OPGW work | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
16 | 2025-08-12 17:23 | MR2508/0175 | Daily | 220KV_220KV Mangliya -Jaitpura Line. | 220KV_MANGLIA2 | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 14-08-2025 07:00:00 | 31-08-2025 19:00:00 | A.R.KANEL | 9425805217 | OK LINE TO BE IN SERVICE
17 | 2025-08-28 13:00 | MR2508/0378 |  | 132KV_132KV Nagda-Unhel Line | 220KV_NAGDA | NON-OCCM-MP | Line Maintenance work. | 29-08-2025 10:00:00 | 29-08-2025 18:00:00 | Kamal Solanki | 9425805262 | SUB LD
18 | 2025-08-28 16:22 | MR2508/0393 |  | 132KV_132/33KV 63MVA BBL Make X-mer-I | 220KV_NARSINGHPUR | NON-OCCM-MP | Post Mansoon bay maint & relay replacement work | 29-08-2025 10:00:00 | 29-08-2025 18:00:00 | Dinesh Kumar Kushwaha | 9425182413 | OK
19 | 2025-08-28 16:01 | MR2508/0389 |  | 220KV_SARNI ITARSI CKT-4 | 400KV_SATPURA TPS | NON-OCCM-MP | Flash over disc replacement work | 29-08-2025 10:00:00 | 29-08-2025 14:00:00 | SHIV KUMAR | 9425806917 | OK, THROUGH SUB LD, TIME DURATION OF SD SHALL BE MAINTAINED AND FURTHER EXTENSION SHALL BE AVOIDED
20 | 2025-08-28 13:34 | MR2508/0380 |  | 220KV_220 kV SGTPS Brs-Manpur[TBCB] Circuit | 400KV_SGTPS | NON-OCCM-MP | F/o disc stringing replacement & other line maint. | 29-08-2025 09:00:00 | 29-08-2025 13:00:00 | Jitendra Tiwari | 9425805298 | OK
21 | 2025-08-28 12:12 | MR2508/0375 |  | 220KV_220kv sukha-jabalpur ckt-1 | 220KV_SUKHA | NON-OCCM-MP | CT REPLACEMENT DUE TO OIL LEAKAGE&CT ARE VERY OLD | 29-08-2025 08:00:00 | 29-08-2025 18:00:00 | ashish sonkeshariya | 7587951153 | OK
22 | 2025-08-28 16:18 | MR2508/0391 |  | 20MVA_132/33KV_CGL_X'mer_2 | 132KV_WAIDHAN | OCCM-MP | Oil Topping work | 29-08-2025 12:00:00 | 29-08-2025 14:00:00 | R.B. Singh | 9907230394 | OK O&M TO INFORM
23 |  |  |  | 40 MVA APEX X-MER | 132 KV KATNI |  | OIL LEAKAGE ATTENDING WORK | 2025-08-29 11:00 | 29-08-2025 17:00:00 AM |  | 9425801440 | OK
24 |  |  |  | 400 KV BUS TAI | 400 KV PITHAMPUR |  | CT TAN DELTA TESTING WROK | 2025-08-29 14:00 | 2025-08-29 17:00 | anil kumar | 7889605089 | OK , BUT SEPRATE BUS OPRATION NOT CONSIDIRD SO ALL FEEDERS TO BE SHIFTED ON SAME BUS
25 |  | 262359 | Daily | 220KV-AJAYGARH-SATNA-1 | 220 | MP_SLDC | for maintenance & testing work | 29-Aug-2025 | 09:30 | 29-Aug-2025 | 18:30 | OK
26 |  | 257802 | Daily | 400KV-INDORE-MP-ASOJ-2 | 400 | POWERGRID_WR2 | AMP works, Dia to be kept open at both ends. Bus-2 Pento Isolator replacement work under Add cap | 29-Aug-2025 | 07:00 | 29-Aug-2025 | 20:00 | OK THROUGH SUB LD
27 |  | 258479 | Daily | 220KV-BETUL-BETUL-MP-2 | 220 | POWERGRID_WR2 | AMP works of line terminal equipments. And measurement of SF6 due point of CB to complete Corporate SIR Clause B Point 1.Dia to be kept open at both ends. | 29-Aug-2025 | 09:00 | 29-Aug-2025 | 18:00 | OK THROUGH SUB LD
28 |  | 257003 | Daily | 220KV-DAMOH-DAMOH-MP-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK | 29-Aug-2025 | 09:00 | 29-Aug-2025 | 18:00 | OK
29 |  | 257004 | Daily | 220KV-PITHAMPUR-RAJGARH-1 | 220 | MP_SLDC | LINE MAINTENANCE WORK | 29-Aug-2025 | 08:00 | 29-Aug-2025 | 18:00 | OK THROUGH SUB LD
30 |  | 257005 | Daily | 220KV-REWA-REWA-MP-2 | 220 | MP_SLDC | FOR LINE MAINTENANCE WORK ( REWA RUMS) | 29-Aug-2025 | 10:00 | 29-Aug-2025 | 17:00 | OK
31 |  | 259223 | Daily | 132KV-DHARNI-NEPANAGAR-1 | 132 | MP_SLDC | A/R off required for OPGW installation work of 24/48 core OPGW by replacing E/W for implementation of OPGW based reliable communication scheme | 29-Aug-2025 | 07:00 | 29-Aug-2025 | 18:59 | OK LINE TO BE IN SERVICE