## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2025-09-09
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Status | Availing Officer Name & Mob. No. |  | REMARK
1 | 2025-08-25 15:12 | MR2508/0327 | Daily | 220KV_220KV Anuppur Kotmikala ckt-I | 220KV_ANUPPUR | NON-OCCM-MP | Low Ground clearance maintenance work at loc. 371- | 09-09-2025 08:00:00 | 17-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK
2 | 2025-09-08 13:46 | MR2509/0181 |  | 40MVA_132/33KV_EMCO_X'mer_1 | 132KV_ARON | NON-OCCM-MP | post mansoon | 09-09-2025 11:00:00 | 09-09-2025 17:00:00 | Waiting | Rakesh suman | 7587951093 | SUB LD
3 | 2025-09-08 13:39 | MR2509/0180 |  | 132KV_132KV Badnagar-Depalpur Line | 220KV_BADNAGAR | NON-OCCM-MP | F/o disc Insulator replacement work. | 09-09-2025 10:00:00 | 09-09-2025 18:00:00 | Waiting | Kamal Solanki | 9425805262 | SUB LD
4 | 2025-09-08 09:48 | MR2509/0169 |  | 220KV_160 MVA XMER 2 MAKE AREVA | 220KV_BAIRAGARH | NON-OCCM-MP | POST MONSOON MAINTENANCE | 09-09-2025 09:00:00 | 09-09-2025 18:00:00 | Accepted | AMBARISH SHRIPAD JOSHI | 7587951085 | OK THROUGH SUB LD
5 | 2025-09-08 14:49 | MR2509/0184 |  | 132KV_40 MVA X-mer - 1 (NGEF) | 132KV_BALAGHAT | NON-OCCM-MP | diff. relay replacement work | 09-09-2025 10:00:00 | 09-09-2025 17:00:00 | Waiting | SWATI BISEN | 9425801737 | OK O&M TO BE INTIMATED
6 | 2025-09-08 15:40 | MR2509/0190 |  | 132KV_132 KV Bilpank - Badnagar line | 132KV_BILPANK | NON-OCCM-MP | for line maintenance work | 09-09-2025 10:00:00 | 09-09-2025 18:00:00 | Waiting | Kumar Vishal | 9425805018 | SUB LD
7 | 2025-09-06 15:08 | MR2509/0153 | Daily | 132KV_132 kV Shahdol-Birsingpur Circuit I | 220KV_BIRSINGHPUR | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK, DATA COMMUNICATION SHALL NOT BE INTERRUPTED
8 | 2025-09-08 15:52 | MR2509/0191 |  | 220KV_220 kV Seoni-Chhindwara Ckt-I | 220KV_CHHINDWARA | OCCM-MP | J/C tightening & Bird guard provide | 09-09-2025 09:00:00 | 09-09-2025 17:00:00 | Waiting | A.M.Shende | 7587951136 | OK
9 | 2025-09-06 15:08 | MR2509/0154 | Daily | 132KV_132 kV Shahdol-Dindori Circuit II | 132KV_DINDORI | NON-OCCM-MP | Replacement of damaged OPGW | 07-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | Jitendra Tiwari | 9425805298 | OK, DATA COMMUNICATION SHALL NOT BE INTERRUPTED
10 | 2025-09-08 14:57 | MR2509/0187 |  | 132KV_132kv Dongrital -Anupppur bay | 132KV_DONGRITAL | OCCM-MP | Replacement of 132kv CT all 3 phase (R,Y&B) | 09-09-2025 08:00:00 | 09-09-2025 17:00:00 | Waiting | Mr. Sabhapati Prajapati | 9039634660 | OK, PROTECTION UNDERTAKING TO BE SUBMITTED
11 | 2025-09-02 18:32 | MR2509/0063 | Daily | 220KV_220KV North Zone- Hatuniya(PGCIL) Ckt.-1& ckt-2 | 220KV_INDORE-NZ | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | RESCHEDULED FROM 11.09.2025
12 | 2025-09-08 16:20 | MR2509/0192 |  | 400KV_315 MVA X-mer-II (EMCO) | 400KV_JULWANIYA4 | NON-OCCM-MP | Post monsoon maintenance & Testing work | 09-09-2025 10:00:00 | 09-09-2025 18:00:00 | Waiting | Er. Mannalal Badole | 9131865464 | OK THROUGH SUB LD
13 | 2025-06-30 16:18 | MR2506/0637 | Continuous | 220KV_220KV KATNI - DAMOH LINE | 400KV_KATNI4 | NON-OCCM-MP | TOWER STRENTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 18:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC APPROVAL REQUIRED
14 | 2025-06-30 15:35 | MR2506/0627 | Continuous | 400KV_400KV KATNI - DAMOH LINE | 400KV_KATNI4 | OCCM-MP | TOWER STRENGTHENING WORK | 08-09-2025 09:00:00 | 13-09-2025 08:00:00 | Waiting | PANKAJ YADAV | 9406713326 | DEFERRED, WRPC APPROVAL REQUIRED
15 | 2025-09-08 12:41 | MR2509/0177 |  | 132KV_63 MVA BBL XMER | 132KV_KHAJURAHO | NON-OCCM-MP | ATTENDING HOT PIONT OF CT | 09-09-2025 11:00:00 | 09-09-2025 13:00:00 | Waiting | BRAJENDRA SONI | 9893772214 | OK O&M TO BE INTIMATED
16 | 2025-09-04 15:58 | MR2509/0099 |  | 132KV_132 KV Nimarani-III | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 09-09-2025 12:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
17 | 2025-09-04 16:12 | MR2509/0103 | Daily | 132KV_132 KV Nimarani-II | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 09-09-2025 11:00:00 | 10-09-2025 18:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
18 | 2025-09-04 15:47 | MR2509/0096 |  | 132KV_63 MVA X-mer-II make BBL | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 09-09-2025 12:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
19 | 2025-09-04 16:01 | MR2509/0100 |  | 132KV_132 KV Ultratech-II Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 09-09-2025 12:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
20 | 2025-09-04 16:07 | MR2509/0102 | Daily | 132KV_132 KV Singhana Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 10-09-2025 18:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
21 | 2025-09-04 15:39 | MR2509/0094 |  | 132KV_63 MVA X-mer-I make BBL | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 09-09-2025 18:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
22 | 2025-09-04 16:14 | MR2509/0104 | Daily | 132KV_132 KV Ultratech-I Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old | 09-09-2025 11:00:00 | 10-09-2025 18:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
23 | 2025-09-04 15:55 | MR2509/0098 |  | 132KV_132 KV Dhamnod Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 09-09-2025 12:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
24 | 2025-09-04 15:43 | MR2509/0095 |  | 132KV_132 KV Kukshi Feeder | 132KV_MANAWAR | NON-OCCM-MP | 132 KV Main Bus for replacement of single old pant | 09-09-2025 11:00:00 | 09-09-2025 18:00:00 | Waiting | Er. Manoj Randha | 9425820034 | SUB LD, EI APPROVAL TO BE SUBMITTED PRIOR TO CHARGING
25 | 2025-09-08 12:06 | MR2509/0176 |  | 220KV_220kV Mandideep-Hoshangabad line | 220KV_MANDIDEEP | NON-OCCM-MP | Disc replacement work | 09-09-2025 11:00:00 | 09-09-2025 15:00:00 | Waiting | Ankit Mehroliya | 9425804506 | OK THROUGH SUB LD
26 | 2025-09-02 18:36 | MR2509/0064 | Daily | 132KV_132KV North Zone â¿¿ Niranjanpur Line.&132KV Niranjanpur - Jaitpura Line &132KV North Zone- Jaitpura Line | 132KV_NIRANJANPUR | NON-OCCM-MP | Replacement existing of 24 Fibre OPGW by 48 Fibre | 05-09-2025 07:00:00 | 25-09-2025 19:00:00 | Waiting | A.R.KANEL | 9425805217 | SUB LD
27 | 2025-09-08 11:00 | MR2509/0173 |  | 132KV_132 KV Pipariya-Bareli CKT- I | 220KV_PIPARIYA | NON-OCCM-MP | Flash over disc replacement work | 09-09-2025 10:00:00 | 09-09-2025 17:00:00 | Waiting | Ashutosh Rai | 9425806902 | SUB LD
28 | 2025-09-07 17:18 | MR2509/0168 |  | 132KV_50MVA XMER BBL | 132KV_REHLI | NON-OCCM-MP | Post monsoon maintenance and testing work | 09-09-2025 10:00:00 | 09-09-2025 18:00:00 | Waiting | P D Goutam | 9425808329 | OK O&M TO BE INTIMATED
29 | 2025-09-08 16:24 | MR2509/0193 |  | 132KV REWA - REWA IC-2 | 132KV_REWA1 | NON-OCCM-MP | CKT TO BE SHIFTED ON BC FOR RYB ph CT replacement | 09-09-2025 10:00:00 | 09-09-2025 18:00:00 | Waiting | Kanishka Singh | 9425804656 | OK LINE TO BE IN SERVICE THROUGH TBC
30 | 2025-09-06 14:37 | MR2509/0152 |  | 132KV_132kv Sagar-Rehli line (Redial feeder) | 400KV_SAGAR | NON-OCCM-MP | Line maintenance work | 09-09-2025 10:00:00 | 09-09-2025 18:00:00 | Waiting | J.P. Asati | 9424445533 | O&M CONSENT REQUIRED
31 | 2025-09-08 16:30 | MR2509/0194 |  | 220KV_220 kV Bus Tie | 220KV_SATNA | NON-OCCM-MP | For attending hot point in R phase clamp of CB | 09-09-2025 09:00:00 | 09-09-2025 15:00:00 | Waiting | Ravi Pandey | 9425805296 | SD APPROVED, BUT SEPERATE BUS OPERATION NOT CONSENTED, HENCE ALL FEEDERS TO BE SHIFT ON ONE BUS.
32 | 2025-09-08 11:08 | MR2509/0174 |  | 400KV_SARNI SEONI PGCIL | 400KV_SATPURA TPS | OCCM-WR | BROKEN DISC REPLACEMENT WORK | 09-09-2025 09:00:00 | 09-09-2025 17:00:00 | Waiting | SHIV KUMAR | 9425806917 | OK
33 | 2025-09-08 13:07 | MR2509/0179 |  | 400KV_400kV Seoni Sarni (Satpura) Line | 765KV_SEONI-PG | OCCM-WR | Work for tightening of S/C, A/H, V/D & Emer. T/C | 09-09-2025 10:00:00 | 09-09-2025 16:00:00 | Waiting | S.K. Nadekar | 9425806848 | OK
34 | 2025-09-08 14:51 | MR2509/0185 |  | 132KV_132 KV Suwasara I/C -I line | 220KV_SUWASRA2 | NON-OCCM-MP | for OPGW stringing work | 09-09-2025 10:00:00 | 09-09-2025 14:00:00 | Waiting | Ravindra Kumar Marskole | 9425814080 | SUB LD
35 | 2025-09-08 14:55 | MR2509/0186 |  | 132KV_132 KV Suwasara- Badod ckt-II line | 220KV_SUWASRA2 | NON-OCCM-MP | For OPGW stringing work | 09-09-2025 10:00:00 | 09-09-2025 14:00:00 | Waiting | Ravindra Kumar Marskole | 9425814080 | SUB LD
36 | 2025-09-08 15:16 | MR2509/0188 |  | 220KV_220KV Suwasra - Barod Ckt-2 | 220KV_SUWASRA2 | NON-OCCM-MP | Providing M2 DPR Relay Work | 09-09-2025 09:00:00 | 09-09-2025 18:00:00 | Waiting | SUNIL PAWAR | 9425804939 | OK THROUGH SUB LD
37 | 2025-09-08 15:25 | MR2509/0189 |  | 220KV_220kv bus-tie | 220KV_TIKAMGARH | NON-OCCM-MP | Bay maintenance | 09-09-2025 10:00:00 | 09-09-2025 13:00:00 | Waiting | Pushpendra Kumar soni | 9425806398 | SD APPROVED, BUT SEPERATE BUS OPERATION NOT CONSENTED, HENCE ALL FEEDERS TO BE SHIFT ON ONE BUS
38 | 2025-09-02 14:10 | MR2509/0042 | Continuous | 220KV_160 MVA NGEF | 220KV_UJJAIN | NON-OCCM-MP | X-MER REPLACEMENT WORK BY NEW 160 MAV XMER | 03-09-2025 09:00:00 | 03-11-2025 18:00:00 | Accepted | B.C JOSHI | 7587951137 | CONTINUE
39 | 2025-09-08 14:38 | MR2509/0182 |  | 220KV_160 MVA X-MER-I EMCO | 220KV_VIDISHA | OCCM-MP | POST MONSOON MAINTENANCE WORK | 09-09-2025 09:00:00 | 09-09-2025 18:00:00 | Waiting | K.C. GOSWAMI | 9425804976 | OK THROUGH SUB LD
40 | 2025-09-01 16:04 | MR2509/0027 | Continuous | 132KV_132 KV VINOBA BHAVE TAPE LINE | 132KV_VINOBA BHAVE | NON-OCCM-MP | UPGRADATION OF 132 KV VINOBA BHAVE LINE | 02-09-2025 08:00:00 | 25-09-2025 18:00:00 | Accepted | RAJESH TIWARI | 7898239595 | CONTINUE
41 |  | 262502 |  | 220KV-ANNUPUR-KOTMIKALA-1 | MP_SLDC | WR | For Re-sagging work due to Low Ground clearance at loc. 371-379 & 464- 475 | 08:00 | 17:59 |  |  |  | OK
42 |  | 260548 |  | 400KV-BADNAWAR-RAJGARH-2 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08:00 | 18:00 |  |  |  | OK THROUGH SUB LD
43 |  | 260577 |  | 220KV-GWALIOR-GWALIOR-II-1 | MP_SLDC | WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 09:00 | 17:00 |  |  |  | OK THROUGH SUB LD
44 |  | 260578 |  | 220KV-KHANDWA-CHHANERA-1 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 08:00 | 18:00 |  |  |  | OK THROUGH SUB LD
45 |  | 260579 |  | 220KV-SEONI-PG-CHINDWARA-1 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09:00 | 18:00 |  |  |  | OK
46 |  | 260546 |  | 400KV-BHOPAL-MP-BHOPAL-BDTCL-1 | MP_SLDC | WR | FOR BAY MAINTENANCE & TESTING WORK AT SUBSTASTION, REPLACEMENT OF DAMAGED CLAMPS/JUMPERS ETC. | 09:00 | 18:00 |  |  |  | OK THROUGH SUB LD
47 |  | 260547 |  | 400KV-SEONI-PG-SATPURA-1 | MP_SLDC | WR | FOR LINE MAINTENANCE WORK i.e. CLEANING OF DISC INSULATORS DURING LINE PATROLLING , REPLACEMENT OF FLASHOVERED DISC INSULATORS, TREE BRANCH CUTTING ETC AT VARIOUS TOWER LOCATIONS | 09:00 | 18:00 |  |  |  | OK
48 |  | 261537 |  | 400KV/220KV SATNA-ICT-3 | POWERGRID_WR2 | WR | For excavation work related to construction of cable trench for 220 kV EHT cable associated with upcoming 400/220 kV ICT#4, Dia to be kept open at both sides. | 09:00 | 18:00 |  |  |  | OK
49 |  | 261655 |  | 400KV-BINA-MP-BINA-4 | POWERGRID_WR2 | WR | Simultaneous ouatge of 765KV/400KV BINA-ICT-1 & 400KV-BINA-MP-BINA-4 required for Bay-423 LBB Testing.Dia to be kept open. | 09:00 | 17:30 |  |  |  | OK